## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Intelligent Document Processing
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Description | Acceptance Criteria | Source | Owner | Status | Dependencies | Test Method | Compliance | Notes | Estimated Effort
REQ-001 | Functional | Document Processing | Critical | System must support PDF document processing using Amazon Textract | Process PDF documents with 95%+ accuracy for text extraction | Business Stakeholder | AI/ML Team | Draft | AWS Textract availability | Automated testing |  | Core IDP functionality | 40 hours
REQ-002 | Functional | Document Processing | Critical | System must support JPEG and PNG image processing | Process scanned images with OCR accuracy above 90% | Business Stakeholder | AI/ML Team | Draft | REQ-001 | Automated testing |  | Image quality dependent | 32 hours
REQ-003 | Functional | Document Processing | High | System must classify documents into predefined types | Automatically classify documents with 95%+ accuracy | Business Stakeholder | Data Science Team | Draft | Document samples | ML model testing |  | Requires custom model training | 80 hours
REQ-004 | Functional | Data Extraction | Critical | Extract structured data from invoices | Extract vendor name amount date with 95%+ accuracy | Business User | AI/ML Team | Draft | REQ-001 | Field validation testing |  | Invoice-specific extraction rules | 60 hours
REQ-005 | Functional | Data Extraction | Critical | Extract data from contracts and agreements | Extract parties dates terms with 90%+ accuracy | Legal Team | AI/ML Team | Draft | REQ-003 | Legal review testing | Compliance | Complex legal language processing | 100 hours
REQ-006 | Functional | Data Extraction | High | Extract data from forms and applications | Extract form fields with 95%+ accuracy | Business User | AI/ML Team | Draft | REQ-002 | Form validation testing |  | Various form layouts | 70 hours
REQ-007 | Functional | API | Critical | Provide REST API for document submission | API accepts documents and returns processing job ID | Technical Team | Backend Developer | Draft |  | API testing | Security | Authentication required | 40 hours
REQ-008 | Functional | API | Critical | Provide REST API for results retrieval | API returns extracted data in JSON format | Technical Team | Backend Developer | Draft | REQ-007 | API testing | Security | Rate limiting implemented | 32 hours
REQ-009 | Functional | Batch Processing | High | Support batch processing of multiple documents | Process up to 100 documents in single batch | Business User | Backend Developer | Draft | REQ-007 | Load testing |  | Async processing required | 50 hours
REQ-010 | Functional | Real-time Processing | High | Support real-time document processing | Process single document within 30 seconds | Business User | Backend Developer | Draft | REQ-007 | Performance testing |  | Sync processing option | 45 hours
REQ-011 | Non-Functional | Performance | Critical | System must process documents within performance thresholds | Average processing time under 10 seconds per page | Business Stakeholder | Technical Lead | Draft | AWS services | Performance testing | SLA | Depends on document complexity
REQ-012 | Non-Functional | Accuracy | Critical | AI models must meet minimum accuracy requirements | Overall extraction accuracy above 95% | Business Stakeholder | Data Science Team | Draft | Model training | Accuracy testing | Quality | Continuous monitoring required
REQ-013 | Non-Functional | Scalability | High | System must handle increasing document volumes | Scale to process 10000+ documents per day | Technical Team | Cloud Architect | Draft | AWS infrastructure | Load testing |  | Auto-scaling configuration
REQ-014 | Non-Functional | Availability | High | System must maintain high availability | 99.5% uptime during business hours | Technical Team | DevOps Engineer | Draft | Multi-AZ deployment | Uptime monitoring | SLA | Redundancy and failover
REQ-015 | Security | Data Protection | Critical | All documents must be encrypted at rest | AES-256 encryption for stored documents | Security Team | Security Architect | Draft | KMS configuration | Security audit | GDPR | S3 bucket encryption | 24 hours
REQ-016 | Security | Data Protection | Critical | All data must be encrypted in transit | TLS 1.2+ for all API communications | Security Team | Security Architect | Draft | SSL certificates | Security testing | SOC2 | API Gateway SSL termination | 16 hours
REQ-017 | Security | Access Control | Critical | Implement role-based access control | Users access only authorized document types | Security Team | Backend Developer | Draft | IAM configuration | Access testing | RBAC | Principle of least privilege | 40 hours
REQ-018 | Security | Authentication | Critical | Implement API key authentication | All API calls require valid authentication | Security Team | Backend Developer | Draft | API Gateway | Authentication testing | Security | API key management | 32 hours
REQ-019 | Security | Audit Logging | High | Log all document processing activities | Complete audit trail for compliance | Compliance Team | Backend Developer | Draft | CloudWatch setup | Audit review | SOX | Immutable logging | 24 hours
REQ-020 | Security | Data Retention | High | Implement configurable data retention policies | Automatic deletion based on retention rules | Compliance Team | Backend Developer | Draft | S3 lifecycle | Compliance testing | GDPR | Configurable retention periods | 32 hours
REQ-021 | Integration | External Systems | High | Integrate with existing document management system | Bi-directional data sync with DMS | IT Team | Integration Specialist | Draft | DMS API access | Integration testing |  | Custom API development | 60 hours
REQ-022 | Integration | External Systems | Medium | Integrate with ERP system for invoice processing | Send extracted invoice data to ERP | Finance Team | Integration Specialist | Draft | ERP API access | End-to-end testing |  | ERP-specific data mapping | 50 hours
REQ-023 | Integration | Notification | Medium | Send processing completion notifications | Email/SMS notifications for job completion | Business User | Backend Developer | Draft | SNS configuration | Notification testing |  | Configurable notification rules | 30 hours
REQ-024 | Usability | User Interface | High | Provide web interface for document upload | Drag-and-drop document upload interface | End User | Frontend Developer | Draft | Web framework | Usability testing | Accessibility | Mobile-responsive design | 80 hours
REQ-025 | Usability | User Interface | High | Provide interface for results review and correction | Users can review and correct extracted data | End User | Frontend Developer | Draft | REQ-024 | User testing |  | Human-in-the-loop workflow | 90 hours
REQ-026 | Usability | User Interface | Medium | Provide dashboard for processing statistics | Real-time dashboard showing processing metrics | Manager | Frontend Developer | Draft | REQ-024 | Dashboard testing |  | Analytics and reporting | 60 hours
REQ-027 | AI/ML | Model Management | High | Support model versioning and rollback | Deploy new models with rollback capability | Data Science Team | ML Engineer | Draft | SageMaker setup | Model testing |  | A/B testing framework | 70 hours
REQ-028 | AI/ML | Model Monitoring | High | Monitor model performance and accuracy drift | Automated alerts for accuracy degradation | Data Science Team | ML Engineer | Draft | CloudWatch setup | Monitoring testing |  | Continuous model evaluation | 50 hours
REQ-029 | AI/ML | Model Retraining | Medium | Support automated model retraining | Retrain models when accuracy drops below threshold | Data Science Team | ML Engineer | Draft | REQ-028 | Retraining testing |  | MLOps pipeline implementation | 100 hours
REQ-030 | AI/ML | Confidence Scoring | High | Provide confidence scores for extractions | Return confidence level for each extracted field | Business User | Data Science Team | Draft | Model implementation | Confidence testing | Quality | Threshold-based routing | 40 hours
REQ-031 | Operational | Monitoring | Critical | Implement comprehensive system monitoring | Monitor all system components and AWS services | Operations Team | DevOps Engineer | Draft | CloudWatch setup | Monitoring validation | SLA | Proactive alerting | 40 hours
REQ-032 | Operational | Backup | Critical | Implement automated backup procedures | Daily backup of all critical data and configurations | Operations Team | DevOps Engineer | Draft | S3 configuration | Backup testing | Data protection | Cross-region backup option | 32 hours
REQ-033 | Operational | Disaster Recovery | High | Implement disaster recovery procedures | RTO 4 hours RPO 1 hour for critical functions | Operations Team | Cloud Architect | Draft | Multi-region setup | DR testing | Business continuity | Documented recovery procedures | 60 hours
REQ-034 | Compliance | Data Privacy | Critical | Comply with GDPR requirements | Right to erasure and data portability | Compliance Team | Backend Developer | Draft | Legal review | Compliance audit | GDPR | Data subject rights implementation | 50 hours
REQ-035 | Compliance | Document Retention | High | Comply with industry document retention standards | Configurable retention based on document type | Compliance Team | Backend Developer | Draft | REQ-020 | Compliance testing | Industry standards | Legal hold capability | 40 hours
REQ-036 | Infrastructure | AWS Services | Critical | AWS account with administrative access and appropriate permissions | Full administrative access to required AWS services | Infrastructure Team | Cloud Architect | Draft |  | Access validation | Security | Required for service provisioning | 8 hours
REQ-037 | Infrastructure | AWS Services | Critical | Amazon Textract service enabled with sufficient quotas | Service available with quotas for expected document volume | Infrastructure Team | Cloud Architect | Draft | REQ-036 | Service testing | AWS | Check service limits for document processing | 4 hours
REQ-038 | Infrastructure | AWS Services | Critical | Amazon Comprehend service enabled with sufficient quotas | Service available for entity extraction and analysis | Infrastructure Team | Cloud Architect | Draft | REQ-036 | Service testing | AWS | Natural language processing capability | 4 hours
REQ-039 | Infrastructure | AWS Services | High | Amazon SageMaker service enabled for custom models | Service available for custom model training and deployment | Infrastructure Team | Data Science Team | Draft | REQ-036 | Service testing | AWS | Custom ML model development | 4 hours
REQ-040 | Infrastructure | Compute Resources | High | Lambda compute resources sized for expected workloads | Sufficient Lambda concurrency and memory allocation | Infrastructure Team | DevOps Engineer | Draft | Workload analysis | Load testing | Performance | Scale based on document volume | 16 hours
REQ-041 | Infrastructure | Storage Resources | Critical | S3 storage capacity for documents and results | Sufficient storage with appropriate access patterns | Infrastructure Team | Cloud Architect | Draft | Data volume estimates | Storage testing |  | Include cross-region replication | 8 hours
REQ-042 | Infrastructure | Network Connectivity | High | Network connectivity with sufficient bandwidth for document processing | Adequate bandwidth for document upload and processing | Network Team | Network Engineer | Draft | Bandwidth analysis | Network testing |  | Consider document sizes and volumes | 12 hours
REQ-043 | Skills | Technical Team | Critical | Lead Architect with 5+ years cloud architecture experience | Proven AWS architecture design and implementation experience | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Essential for technical leadership
REQ-044 | Skills | Technical Team | Critical | Data Science expertise with 3+ years ML experience | Proven machine learning model development and deployment | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Critical for AI/ML implementation
REQ-045 | Skills | Technical Team | High | AWS Security specialist with 3+ years security experience | Proven AWS security and compliance implementation | HR Team | Project Manager | Draft | Team recruitment | Skill assessment | Security | Essential for security architecture
REQ-046 | Skills | Development Team | High | Python/Node.js developers with 3+ years experience | Proven serverless development and API design experience | HR Team | Technical Lead | Draft | Team recruitment | Skill assessment |  | Core development capability
REQ-047 | Budget | Project Costs | Critical | Infrastructure budget approved for expected AWS costs | Monthly AWS costs $10000-$50000 approved and allocated | Finance Team | Project Sponsor | Draft | Cost estimates | Budget approval | Financial | Based on document processing volume
REQ-048 | Budget | Project Costs | Critical | Professional services budget approved for implementation | Implementation costs $75000-$200000 approved | Finance Team | Project Sponsor | Draft | SOW approval | Budget approval | Financial | Includes training and knowledge transfer
REQ-049 | Security | Access Controls | Critical | Identity and access management framework implemented | IAM roles and policies following least privilege principle | Security Team | Security Architect | Draft | AWS account setup | Security audit | Security | Role-based access control | 24 hours
REQ-050 | Security | Data Protection | Critical | Data classification and protection policies defined | Clear policies for handling sensitive document data | Compliance Team | Security Architect | Draft | Data analysis | Policy review | GDPR | Include PII and PHI handling | 16 hours
REQ-051 | Compliance | Regulatory | High | Regulatory compliance frameworks identified and validated | SOC 2 ISO 27001 GDPR compliance requirements documented | Compliance Team | Compliance Officer | Draft | Legal review | Compliance audit | Multiple | Industry-specific requirements | 20 hours
REQ-052 | Testing | Environment | High | Development and testing environments available | Isolated environments for development testing and staging | Infrastructure Team | DevOps Engineer | Draft | REQ-036 | Environment testing |  | Multi-environment strategy | 24 hours
REQ-053 | Testing | Procedures | High | User acceptance testing procedures and criteria defined | Clear UAT processes with business user involvement | QA Team | Business Analyst | Draft | Business requirements | UAT planning |  | Include real document scenarios | 16 hours
REQ-054 | Operations | Support | High | Operations team prepared for day-2 operations | Trained operations team with documented procedures | Operations Team | Operations Manager | Draft | Training completion | Operational readiness | SLA | 24/7 support capability | 32 hours
REQ-055 | Training | Certification | Medium | AWS certifications for key technical team members | Solutions Architect and Security Specialty certifications | HR Team | Project Manager | Draft | Team skill gaps | Certification validation | AWS | Maintain technical expertise