## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Onpremise To Cloud Migration
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Priority | Requirement Description | Acceptance Criteria | Source | Status | Assigned To | Due Date | Notes
MIG-REQ-001 | Migration Scope | Critical | Complete server inventory and discovery | All on-premise servers identified with OS and applications documented | Migration Assessment | Draft | Migration Architect | [DATE] | Use AWS Application Discovery Service and manual inventory
MIG-REQ-002 | Migration Scope | Critical | Application portfolio analysis | All applications categorized using 6 Rs migration strategy with recommendations | Application Assessment | Draft | Application Architect | [DATE] | Include complexity scoring and migration approach per application
MIG-REQ-003 | Migration Scope | High | Database migration requirements | All databases identified with migration approach and data volume analysis | Data Assessment | Draft | Database Specialist | [DATE] | Include database dependencies and integration points
MIG-REQ-004 | Migration Scope | High | Network connectivity assessment | Current network topology documented with bandwidth and connectivity requirements | Network Assessment | Draft | Network Engineer | [DATE] | Include WAN links and critical network dependencies
MIG-REQ-005 | Migration Strategy | Critical | Migration wave planning | Applications sequenced into migration waves based on dependencies and business priority | Migration Planning | Draft | Migration Strategist | [DATE] | Include rollback procedures and business impact analysis
MIG-REQ-006 | Migration Strategy | Critical | Zero data loss requirement | All data migration must achieve 100% data integrity with validation | Business Requirements | Draft | Data Migration Lead | [DATE] | Include data validation checkpoints and rollback procedures
MIG-REQ-007 | Migration Strategy | High | Minimal downtime requirement | Application downtime not to exceed 4 hours per migration window | Business Requirements | Draft | Migration Team Lead | [DATE] | Include cutover procedures and rollback time considerations
MIG-REQ-008 | Migration Strategy | High | Pilot migration requirement | Execute pilot migration with low-risk applications before production waves | Risk Management | Draft | Migration Project Manager | [DATE] | Include lessons learned capture and process refinement
AWS Environment | Infrastructure | Critical | Multi-account AWS setup | AWS Organizations with separate accounts for security logging production and non-production | AWS Best Practices | Draft | Cloud Architect | [DATE] | Follow AWS Control Tower implementation guidelines
AWS Environment | Infrastructure | Critical | Landing zone implementation | Secure baseline AWS environment with networking monitoring and security controls | AWS Well-Architected | Draft | Cloud Engineer | [DATE] | Include AWS Config rules and security baselines
AWS Environment | Infrastructure | High | Network connectivity setup | Establish hybrid connectivity between on-premise and AWS via VPN or Direct Connect | Hybrid Requirements | Draft | Network Engineer | [DATE] | Include redundancy and bandwidth sizing requirements
AWS Environment | Infrastructure | High | Identity and access management | Implement IAM roles policies and federated access for cloud resources | Security Requirements | Draft | Security Architect | [DATE] | Follow least privilege principle and role-based access control
AWS Environment | Security | Critical | Data encryption requirements | All data encrypted at rest and in transit using AWS KMS or customer-managed keys | Compliance Requirements | Draft | Security Engineer | [DATE] | Include key management and rotation policies
AWS Environment | Security | Critical | Network security controls | Implement security groups NACLs and AWS WAF for network protection | Security Framework | Draft | Security Engineer | [DATE] | Include network segmentation and micro-segmentation
AWS Environment | Security | High | Compliance framework implementation | Ensure AWS environment meets SOC 2 ISO 27001 and industry-specific compliance | Compliance Requirements | Draft | Compliance Officer | [DATE] | Include audit trail and compliance monitoring
AWS Environment | Security | High | Monitoring and alerting setup | Comprehensive monitoring using CloudWatch CloudTrail and AWS Config | Operational Requirements | Draft | Cloud Operations | [DATE] | Include custom metrics and automated alerting
Performance | Non-Functional | High | Application performance baselines | Migrated applications must meet or exceed on-premise performance baselines | Performance Requirements | Draft | Performance Engineer | [DATE] | Include response time throughput and resource utilization metrics
Performance | Non-Functional | High | Database performance requirements | Database performance must maintain or improve current query response times | Performance Requirements | Draft | Database Administrator | [DATE] | Include connection pooling and query optimization
Performance | Non-Functional | Medium | Auto-scaling configuration | Implement auto-scaling for applications to handle variable workloads | Scalability Requirements | Draft | Cloud Engineer | [DATE] | Include scaling policies and performance thresholds
Performance | Non-Functional | Medium | Load balancing requirements | Configure application load balancers for high availability and performance | Availability Requirements | Draft | Infrastructure Engineer | [DATE] | Include health checks and traffic distribution algorithms
Migration Process | Operational | Critical | Migration testing procedures | Comprehensive testing plan for each migration wave including rollback testing | Quality Assurance | Draft | QA Lead | [DATE] | Include functional performance and security testing
Migration Process | Operational | Critical | Cutover procedures documentation | Detailed step-by-step procedures for application cutover and rollback | Migration Planning | Draft | Migration Team Lead | [DATE] | Include timing communication and validation steps
Migration Process | Operational | High | Data validation procedures | Automated and manual data validation processes to ensure migration accuracy | Data Quality | Draft | Data Migration Specialist | [DATE] | Include data integrity checks and business rule validation
Migration Process | Operational | High | Rollback procedures | Documented and tested rollback procedures for each migration wave | Risk Management | Draft | Migration Project Manager | [DATE] | Include rollback triggers and recovery time objectives
Backup and Recovery | Infrastructure | Critical | AWS backup strategy implementation | Automated backup solution using AWS Backup for all critical workloads | Business Continuity | Draft | Backup Administrator | [DATE] | Include cross-region backup for disaster recovery
Backup and Recovery | Infrastructure | Critical | Disaster recovery testing | Regular DR testing to validate recovery procedures and meet RTO/RPO requirements | Business Continuity | Draft | DR Specialist | [DATE] | Include quarterly DR tests and annual full failover
Backup and Recovery | Infrastructure | High | Backup retention policies | Implement backup retention policies aligned with business and compliance requirements | Data Governance | Draft | Data Governance Team | [DATE] | Include long-term retention and legal hold capabilities
Backup and Recovery | Infrastructure | High | Point-in-time recovery capability | Database and application data recovery to specific points in time | Recovery Requirements | Draft | Database Administrator | [DATE] | Include transaction log backup and recovery procedures
Cost Management | Financial | Critical | Cost optimization requirements | Implement right-sizing reserved instances and cost monitoring for cloud resources | Cost Control | Draft | FinOps Analyst | [DATE] | Include cost allocation tags and budget alerts
Cost Management | Financial | High | Cost allocation and tagging | Comprehensive tagging strategy for cost allocation and resource management | Financial Management | Draft | Cloud Operations | [DATE] | Include automated tagging policies and cost center allocation
Cost Management | Financial | High | Reserved instance strategy | Optimize costs through strategic use of reserved instances and savings plans | Cost Optimization | Draft | FinOps Analyst | [DATE] | Include usage analysis and commitment planning
Cost Management | Financial | Medium | Cost monitoring and alerting | Real-time cost monitoring with alerts for budget overruns and anomalies | Cost Control | Draft | FinOps Team | [DATE] | Include daily cost reports and threshold-based alerts
Training and Knowledge | Skills | Critical | Cloud operations training | Train IT staff on AWS cloud operations management and troubleshooting | Operational Readiness | Draft | Training Manager | [DATE] | Include AWS certification preparation and hands-on labs
Training and Knowledge | Skills | High | Application-specific training | Train application teams on cloud-native operations and new capabilities | User Enablement | Draft | Business Trainer | [DATE] | Include workflow changes and cloud-enabled features
Training and Knowledge | Skills | High | Security operations training | Train security team on cloud security monitoring and incident response | Security Readiness | Draft | Security Training Lead | [DATE] | Include cloud security tools and compliance procedures
Training and Knowledge | Skills | Medium | End user training | Train business users on any application changes and new cloud capabilities | User Adoption | Draft | Business Trainer | [DATE] | Include change management and user support procedures
Access and Permissions | Access | Critical | AWS account access setup | Establish appropriate access levels for migration team and ongoing operations | Access Management | Draft | IAM Administrator | [DATE] | Include temporary migration access and permanent operations access
Access and Permissions | Access | Critical | Source system access | Secure access to all on-premise systems and applications for migration | Migration Access | Draft | Security Team | [DATE] | Include read-only access for assessment and write access for migration
Access and Permissions | Access | High | Network access permissions | Required firewall rules and network access for migration tools and processes | Network Access | Draft | Network Security | [DATE] | Include temporary migration access and permanent hybrid connectivity
Access and Permissions | Access | High | Third-party tool access | Access to migration tools AWS services and partner solutions | Tool Access | Draft | Migration Project Manager | [DATE] | Include licensing and service account management
Compliance and Governance | Compliance | Critical | Data residency requirements | Ensure data placement and processing comply with geographic and regulatory requirements | Legal Requirements | Draft | Compliance Officer | [DATE] | Include data classification and geographic restrictions
Compliance and Governance | Compliance | Critical | Audit trail requirements | Comprehensive audit logging for all migration activities and ongoing operations | Audit Requirements | Draft | Audit Team | [DATE] | Include CloudTrail and application-level logging
Compliance and Governance | Compliance | High | Change management process | Formal change management process for all cloud infrastructure and application changes | Governance Requirements | Draft | Change Manager | [DATE] | Include emergency change procedures and approval workflows
Compliance and Governance | Compliance | High | Risk management framework | Ongoing risk assessment and management for cloud operations | Risk Management | Draft | Risk Manager | [DATE] | Include risk register maintenance and mitigation tracking