## Cover
Project Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Document Intelligence
Customer Name: | Data table for project plan
Version: | 1.0

## Project Plan
Phase | Task_ID | Task_Name | Description | Duration_Days | Start_Date | End_Date | Dependencies | Assigned_To | Priority | Status | Deliverables | Delivery_Documents | Milestones | Risk_Level
Planning | T001 | Project Initiation | Project kickoff and team formation | 5 | 2025-01-15 | 2025-01-20 |  | EO Project Manager | High | Not Started | Project charter team assignments stakeholder matrix | Project Kickoff Complete | Low
Planning | T002 | Requirements Gathering | Collect and document business and technical requirements | 10 | 2025-01-21 | 2025-02-01 | T001 | EO Sales Engineer | High | Not Started | Requirements specification user stories acceptance criteria | Requirements Approved | Medium
Planning | T003 | Solution Architecture Design | Design technical architecture and integration approach | 15 | 2025-02-02 | 2025-02-20 | T002 | EO Quarterback | High | Not Started | Architecture document technical specifications integration design | Architecture Approved | Medium
Planning | T004 | Risk Assessment | Identify analyze and plan mitigation for project risks | 5 | 2025-02-21 | 2025-02-27 | T003 | EO Project Manager | Medium | Not Started | Risk register mitigation plans contingency procedures | Risk Plan Approved | Low
Planning | T005 | Project Plan Finalization | Complete detailed project plan with schedules and resources | 5 | 2025-02-28 | 2025-03-05 | T004 | EO Project Manager | Medium | Not Started | Detailed project plan resource allocation communication plan | Planning Phase Complete | Low
Environment Setup | T006 | Azure Subscription Setup | Configure Azure subscription and establish resource groups | 3 | 2025-03-06 | 2025-03-10 | T005 | EO Engineer | High | Not Started | Azure subscription configuration resource groups naming standards | Environment Foundation Ready | Low
Environment Setup | T007 | Core Infrastructure Deployment | Deploy storage accounts Key Vault and foundational services | 5 | 2025-03-11 | 2025-03-17 | T006 | EO Engineer | High | Not Started | Storage accounts Key Vault network security configurations | Core Infrastructure Deployed | Medium
Environment Setup | T008 | AI Services Provisioning | Deploy and configure Form Recognizer and Cognitive Services | 7 | 2025-03-18 | 2025-03-26 | T007 | EO Engineer | High | Not Started | Form Recognizer service Computer Vision service API configurations | AI Services Ready | Medium
Environment Setup | T009 | Development Environment Setup | Configure development and testing environments | 5 | 2025-03-27 | 2025-04-02 | T008 | EO Engineer | Medium | Not Started | Development environment testing environment CI/CD pipeline setup | Development Ready | Low
Environment Setup | T010 | Monitoring and Logging Setup | Configure Application Insights and monitoring infrastructure | 4 | 2025-04-03 | 2025-04-08 | T009 | EO Engineer | Medium | Not Started | Application Insights Log Analytics monitoring dashboards | Monitoring Infrastructure Ready | Low
Development | T011 | API Development | Develop REST APIs for document processing and system integration | 15 | 2025-04-09 | 2025-04-29 | T010 | EO Engineer | High | Not Started | REST API implementation API documentation SDK development | APIs Developed | Medium
Development | T012 | Document Processing Logic | Implement core document processing workflows and business logic | 20 | 2025-04-30 | 2025-05-25 | T011 | EO Engineer | High | Not Started | Processing workflows error handling validation logic | Core Processing Complete | High
Development | T013 | User Interface Development | Develop web interface for document upload and monitoring | 12 | 2025-05-26 | 2025-06-10 | T012 | EO Engineer | Medium | Not Started | Web interface responsive design user experience | UI Development Complete | Low
Development | T014 | Integration Development | Develop integrations with ERP and other enterprise systems | 18 | 2025-06-11 | 2025-07-04 | T013 | EO Engineer | High | Not Started | ERP integration API connectors data mapping | Integration Development Complete | High
Development | T015 | Security Implementation | Implement authentication authorization and security controls | 10 | 2025-07-05 | 2025-07-18 | T014 | EO Engineer | High | Not Started | Authentication system RBAC implementation audit logging | Security Implementation Complete | Medium
Testing | T016 | Unit Testing | Conduct comprehensive unit testing of all components | 8 | 2025-07-19 | 2025-07-30 | T015 | EO Engineer | High | Not Started | Unit test results code coverage reports defect tracking | Unit Testing Complete | Low
Testing | T017 | Integration Testing | Test end-to-end workflows and system integrations | 12 | 2025-07-31 | 2025-08-15 | T016 | EO Engineer | High | Not Started | Integration test results system validation end-to-end testing | Integration Testing Complete | Medium
Testing | T018 | Performance Testing | Conduct load testing and performance validation | 10 | 2025-08-16 | 2025-08-29 | T017 | EO Engineer | High | Not Started | Performance test results load testing reports optimization recommendations | Performance Testing Complete | Medium
Testing | T019 | Security Testing | Perform security testing and vulnerability assessments | 8 | 2025-08-30 | 2025-09-10 | T018 | EO Engineer | High | Not Started | Security test results vulnerability assessment penetration testing | Security Testing Complete | Medium
Testing | T020 | User Acceptance Testing | Conduct UAT with business stakeholders and end users | 15 | 2025-09-11 | 2025-10-01 | T019 | EO Engineer | High | Not Started | UAT results user feedback acceptance criteria validation | UAT Complete | Low
Training | T021 | Training Material Development | Create comprehensive training materials and documentation | 12 | 2025-10-02 | 2025-10-17 | T020 | EO Engineer | Medium | Not Started | Training materials user guides admin documentation | Training Materials Ready | Low
Training | T022 | Administrator Training | Train system administrators and support staff | 5 | 2025-10-18 | 2025-10-24 | T021 | EO Engineer | Medium | Not Started | Administrator training completion certifications support procedures | Administrator Training Complete | Low
Training | T023 | End User Training | Conduct end user training sessions and competency validation | 8 | 2025-10-25 | 2025-11-05 | T022 | EO Engineer | Medium | Not Started | User training completion competency assessments feedback | End User Training Complete | Medium
Training | T024 | Train-the-Trainer Program | Prepare internal trainers for ongoing support | 5 | 2025-11-06 | 2025-11-12 | T023 | EO Engineer | Low | Not Started | Internal trainer certification training procedures ongoing support plan | Train-the-Trainer Complete | Low
Deployment | T025 | Production Environment Preparation | Prepare and validate production environment for deployment | 7 | 2025-11-13 | 2025-11-21 | T024 | EO Engineer | High | Not Started | Production environment validation security configuration performance verification | Production Ready | Medium
Deployment | T026 | Data Migration and Setup | Migrate configuration data and setup production workflows | 5 | 2025-11-22 | 2025-11-28 | T025 | EO Engineer | Medium | Not Started | Data migration configuration setup workflow validation | Data Migration Complete | Medium
Deployment | T027 | Production Deployment | Execute production deployment and cutover procedures | 3 | 2025-11-29 | 2025-12-03 | T026 | EO Engineer | High | Not Started | Production deployment system validation cutover completion | Production Deployment Complete | High
Deployment | T028 | Go-Live Support | Provide intensive support during initial production period | 10 | 2025-12-04 | 2025-12-17 | T027 | EO Engineer | High | Not Started | Go-live support incident resolution user assistance | Go-Live Support Complete | Medium
Closure | T029 | Performance Optimization | Monitor and optimize system performance post-deployment | 15 | 2025-12-18 | 2026-01-07 | T028 | EO Engineer | Medium | Not Started | Performance optimization recommendations system tuning documentation | Optimization Complete | Low
Closure | T030 | Project Closure | Complete project closure activities and handover to operations | 5 | 2026-01-08 | 2026-01-14 | T029 | EO Project Manager | Medium | Not Started | Project closure report lessons learned operations handover | Project Complete | Low
Support Setup | T031 | Support Model Implementation | Establish ongoing support model and procedures | 10 | Parallel to T025 | 2025-12-03 | T025 | EO Engineer | Medium | Not Started | Support procedures escalation matrix SLA definitions | Support Model Ready | Low
Support Setup | T032 | Monitoring and Alerting Configuration | Configure production monitoring and alerting systems | 7 | Parallel to T026 | 2025-12-05 | T026 | EO Engineer | Medium | Not Started | Monitoring configuration alert setup dashboard creation | Monitoring Complete | Low
Documentation | T033 | Technical Documentation | Complete all technical documentation and procedures | 15 | Parallel to T021 | 2025-10-31 | T021 | EO Engineer | Medium | Not Started | Technical documentation API documentation troubleshooting guides | Documentation Complete | Low
Documentation | T034 | User Documentation | Finalize user guides and help documentation | 10 | Parallel to T022 | 2025-10-29 | T022 | EO Engineer | Medium | Not Started | User guides quick reference cards FAQ documentation | User Documentation Complete | Low
Quality Assurance | T035 | Quality Gate Reviews | Conduct quality gates and milestone reviews | Ongoing | 2025-01-15 | 2026-01-14 | All phases | EO Engineer | High | Not Started | Quality gate reports milestone reviews compliance validation | Quality Gates Passed | Low
Change Management | T036 | Change Management Activities | Execute change management and user adoption strategies | Ongoing | 2025-02-01 | 2025-12-17 | T002 | EO Engineer | Medium | Not Started | Change readiness assessment communication plan user adoption metrics | Change Management Complete | Medium
Vendor Management | T037 | Vendor Coordination | Coordinate with Microsoft and other vendors for support | Ongoing | 2025-01-15 | 2026-01-14 | T001 | EO Engineer | Medium | Not Started | Vendor agreements support coordination escalation procedures | Vendor Management Complete | Low