## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Sentinel Siem
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive Security Status | Executive Sponsors | SIEM project status and security posture improvements | Weekly | Email Report | EO Project Manager | Email distribution list |  | Security metrics, threat detection improvements, key decisions needed | EO Quarterback and CISO | Executive | Report delivered on time and security KPIs improved | Active | [DATE] | Include security dashboard and threat landscape updates
COMM-002 | Security Steering Committee | Project Steering Committee | Strategic direction and scope decisions for SIEM implementation | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | SIEM strategy, detection coverage, budget, timeline, scope changes | EO Quarterback and Security Leaders | Strategic | Meeting attendance >80% and critical security decisions documented | Active | [DATE] | Decision authority for security requirements and budget
COMM-003 | SOC Team Standup | Core SIEM Development Team | Daily coordination for SIEM development and integration | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | Azure Sentinel deployment, detection rules, integration blockers | SOC Team and Security Engineers | Operational | Daily attendance >90% and technical blockers resolved | Active | [DATE] | Focus on SIEM development coordination and security impediments
COMM-004 | Security Architecture Review | Technical and Security Teams | SIEM architecture and security detection optimization | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | Detection rules, log sources, incident response workflows | EO Sales Engineer (Solution Architecture) and Security Architects | Technical | Security decisions documented and detection targets achieved | Active | [DATE] | Include threat detection metrics and security validation results
COMM-005 | Security Risk Review | Risk Management Team | SIEM security risks and threat detection monitoring | Bi-weekly | Risk Meeting | EO Quarterback | Meeting invitation | 45 minutes | Detection coverage gaps, false positive rates, threat landscape changes | EO Project Manager and EO Engineer (Technical Leadership) | Management | Risk register updated and security-specific mitigations tracked | Active | [DATE] | Focus on cybersecurity operational risks and threat detection
COMM-006 | Security Team Training | SOC and Security Operations | SIEM training and security operations preparation | Weekly | Workshop Session | EO Sales Engineer | Workshop invitation | 120 minutes | SIEM operation, incident response, threat hunting procedures | Security Operations and SOC Analysts | Business | Security team sign-off on SIEM procedures and incident response | Active | [DATE] | Include hands-on SIEM training and incident simulation
COMM-007 | SIEM Sprint Review | SIEM Development Team | Security detection progress and SIEM demonstrations | Bi-weekly | Demo Meeting | EO Quarterback | Video conference | 60 minutes | Detection rules deployment, security analytics, threat hunting results | Security Team and Product Owner | Team | Security detection goals achieved and feedback incorporated | Active | [DATE] | Live demonstration of threat detection and incident response
COMM-008 | Azure Security Coordination | Microsoft Security Teams | Azure security service optimization and integration coordination | Weekly | Technical Call | EO Engineer | Conference call | 45 minutes | Sentinel performance, Defender integration, security service optimization | Microsoft Security Team and EO Sales Engineer (Solution Architecture) | Technical | Azure security service performance targets met and issues resolved | Active | [DATE] | Track Sentinel/Defender SLAs and security optimization opportunities
COMM-009 | Security Quality Review | Quality Assurance and Security Operations | SIEM quality and security detection validation | Weekly | QA Meeting | EO Quarterback | Meeting invitation | 45 minutes | Detection accuracy testing, security quality assessment, validation results | QA Team and Security Analysts | Quality | Quality gates met and detection accuracy within tolerance | Active | [DATE] | Include security validation metrics and detection quality analysis
COMM-010 | Testing Coordination | QA and Testing Teams | Testing progress and quality validation | Weekly | QA Meeting | EO Quarterback | Meeting invitation | 45 minutes | Test execution, quality metrics, defect resolution | QA Team and Test Engineers | Quality | Quality gates met and testing within tolerance | Active | [DATE] | Include testing metrics and quality validation results
COMM-011 | Deployment Planning | Deployment Teams | Production deployment planning and coordination | Weekly | Deployment Meeting | EO Project Manager | Meeting invitation | 60 minutes | Deployment readiness, rollback procedures, go-live coordination | Deployment Team and Operations | Deployment | Deployment readiness achieved and procedures validated | Active | [DATE] | Include deployment checklist and risk mitigation
COMM-012 | Stakeholder Updates | Business Stakeholders | Business impact and readiness updates | Bi-weekly | Business Meeting | EO Sales Engineer | Meeting invitation | 45 minutes | Business readiness, training status, change management | Business Leaders and Change Management | Business | Business stakeholder engagement and readiness achieved | Active | [DATE] | Include business impact assessment and training progress