# Statement Of Work

Azure Sentinel SIEM Implementation

| Client Name: | [Client Name] |
| --- | --- |
| Date: | [Month DD, YYYY] |
| Consulting Company: | EO Framework Consulting |
| Submitted By: | [Vendor Contact Name] info@eoframework.com |
| Opportunity No: | OPP-AZSENTINEL-2025-0001 |
| Version | 1.0 |

# Table of Contents

Table of Contents	2

List of Figures	2

1 Section Header 1	3

1.1 Section Sub-Header 1	3

1.1.1 Section Sub-Header 2	3

1.2 Section Sub-Header 5	3

2 Section Header 2 - Table Content	3

2.1 Table Section 1	3

2.2 Table Section 2	3

3 Section Header 3 - Image Section	4

3.1 Image Content	4

4 Section Header 4	4

4.1 Additional Sub-Section	5

5 Sign-Off	5

# List of Tables

Table 1: Deliverables	3
Table 2: Documentation Deliverables	4
Table 3: System Deliverables	5
Table 4: Project Timeline And Milestones	6
Table 5: Project Phases	7
Table 6: Project Milestones and Timeline	8
Table 7: Commercial Terms	9
Table 8: Project Investment	10
Table 9: Year 1 Total Cost Of Ownership	11
Table 10: Risk Management	12
Table 11: Identified Risks	13

# List of Figures

## 1 Executive Summary

This Statement of Work (SOW) defines the scope, deliverables, roles, and terms for implementing a cloud-native SIEM solution using Azure Sentinel for [Client Name]. This engagement will deliver advanced threat detection and response capabilities through Azure Sentinel analytics engine, automated SOAR playbooks, and integrated threat intelligence to transform security operations from reactive to proactive threat hunting.

Medium Scope Deployment:

• Data Ingestion: 300 GB/month from cloud and on-premises sources

• Data Sources: 8-10 connectors (Office 365, Azure AD, Defender, firewalls, network)

• User Base: 50-100 SOC analysts and security team members

• Deployment Model: Single Azure region with HA/DR, 24x7 monitoring and support

• Total Investment: $776,424 over 3 years ($342,808 Year 1 implementation)

Key Outcomes:

• Real-time threat detection across all infrastructure with 200+ KQL detection rules

• 85%+ reduction in mean time to detect (MTTD) with AI-powered analytics

• Automated incident response through SOAR playbooks for 50+ attack scenarios

• Enterprise-grade compliance reporting for HIPAA, PCI-DSS, SOC 2, GDPR

Expected ROI: Typical payback period of 6-12 months based on security incident prevention and operational efficiency. For organizations with average annual incident response costs of $500K-$2M, Sentinel ROI exceeds 150% annually.

## 2 Background & Objectives

### 2.1 Background

[Client Name] currently relies on fragmented security tools that lack integrated threat correlation and automated response capabilities. Key challenges include:

• Limited Visibility: Multiple disconnected security tools prevent comprehensive threat correlation across infrastructure

• Slow Threat Response: Manual incident investigation and response processes requiring 8+ hours per incident

• Alert Fatigue: High false positive rates from basic rule engines overloading SOC analysts with noise

• Compliance Gaps: Manual compliance reporting and audit trail management increasing risk and audit findings

• Lack of Automation: Repetitive incident response tasks consuming analyst time and delaying remediation

• Advanced Threats: Inability to detect sophisticated threats and insider attacks requiring behavioral analysis

### 2.2 Objectives

• Deploy SIEM: Implement Azure Sentinel workspace with comprehensive data source integration

• Enable Threat Detection: Deploy 50+ KQL detection rules covering MITRE ATT&CK framework with high fidelity

• Automate Response: Develop SOAR playbooks for 50+ attack scenarios enabling 5-minute automated response

• Reduce MTTD: Decrease mean time to detect (MTTD) from 4+ hours to 30 minutes

• Reduce MTTR: Achieve 50% reduction in mean time to respond (MTTR) through automation

• Improve Compliance: Automate compliance reporting for HIPAA, PCI-DSS, SOC 2, GDPR, ISO 27001

• Enable Hunting: Empower security team with advanced hunting capabilities for proactive threat identification

### 2.3 Success Metrics

• 200+ detection rules deployed and operationalized with <5% false positive rate

• MTTD reduced from baseline to <30 minutes for critical threats

• MTTR reduced by 50% compared to current manual processes

• Automated response playbooks executing within 5 minutes of threat detection

• 99.9% system uptime for Sentinel workspace and analytics engine

• Successful integration with 8+ data sources with <1% ingestion failures

• Completion of SOC team training with >90% competency assessment

• Compliance audit readiness with automated monthly reporting

## 3 Scope of Work

### 3.1 In Scope

The following services and deliverables are included in this SOW:

#### 3.1.1 Discovery & Planning Phase (Weeks 1-2)

• Security posture assessment and current SIEM tooling evaluation

• Data source inventory and connector requirements analysis

• Threat landscape assessment and organization-specific threat identification

• Azure infrastructure assessment and subscription readiness validation

• Project planning and stakeholder alignment

• Risk assessment and mitigation strategy development

#### 3.1.2 Implementation Phase (Weeks 3-8)

Infrastructure Deployment:

• Azure Sentinel workspace provisioning and configuration

• Log Analytics Workspace setup with appropriate retention and tiers

• RBAC and access control implementation for security team

• Network connectivity for hybrid data source ingestion

Data Connector Configuration:

• Office 365 Defender connector (Exchange, Teams, SharePoint threat data)

• Azure AD connector (user activities, sign-in logs, identity threats)

• Microsoft Defender for Cloud integration (infrastructure security events)

• Azure Firewall and NSG Flow Log ingestion

• On-premises firewall data collection (Palo Alto, Fortinet, Cisco ASA)

• Endpoint Detection & Response (EDR) tool integration

• Optional third-party SIEM data connector (Splunk, ArcSight, etc.)

Analytics Rules Development:

• Deploy 50+ built-in KQL detection rules covering:

• Initial access attacks (credential compromise, phishing)

• Lateral movement and privilege escalation

• Data exfiltration and command & control

• Denial of service and infrastructure attacks

• Insider threats and suspicious user behavior

Configure threat intelligence feed integration

Establish incident auto-grouping and correlation rules

Implement alert tuning to reduce false positives

Investigation & Hunting Setup:

• Configure investigation workbooks for rapid incident analysis

• Establish advanced hunting queries for threat investigation

• Create forensic investigation playbooks and procedures

#### 3.1.3 SOAR & Automation Phase (Weeks 5-8)

• Design 50+ automated incident response playbooks covering:

• User compromise response (disable account, reset credentials)

• Malware detection response (isolate endpoint, block hash)

• Data exfiltration response (block connection, alert CISO)

• Privilege escalation response (revoke access, force MFA)

Logic Apps development for workflow automation

Integration with ticketing system (ServiceNow, Jira, etc.)

Integration with communication tools (Teams, Slack)

Testing and validation of all playbooks

#### 3.1.4 Testing & Validation Phase (Weeks 9-10)

• Functional testing of all data connectors and ingestion

• Detection rule testing with simulated threat scenarios

• Playbook testing and refinement

• Performance and load testing (300 GB/month data validation)

• Security testing and compliance validation

• User acceptance testing with SOC team

• Go-live readiness assessment

#### 3.1.5 Deployment & Training Phase (Weeks 11-12)

• Production deployment and cutover

• Post-deployment monitoring and optimization

• Comprehensive SOC team training (2 days, up to 20 participants)

• Advanced hunting training (1 day, hands-on)

• Incident response procedure training

• Compliance and audit trail training

• Documentation delivery and knowledge transfer

• 60-day hypercare support engagement

### 3.2 Out-of-Scope

The following activities are explicitly excluded from this SOW:

• Hardware procurement and installation for on-premises log forwarding

• Custom application development beyond Azure Sentinel configuration

• Network infrastructure modifications and firewall rule changes

• Ongoing managed SIEM services beyond 60-day hypercare period

• Incident response service delivery (advisory only, not 24x7 SOC)

• Third-party software licensing (licensing responsibility remains with client)

• Legacy system decommissioning or data migration services

• Advanced machine learning model development beyond built-in capabilities

• Multi-region or disaster recovery site deployment

## 4 Deliverables

| Deliverable | Description | Due Date | Format |
| --- | --- | --- | --- |
| Sentinel Deployment Architecture | Detailed design for Sentinel workspace, data connectors, and integration architecture | Week 3 | PDF/Visio |
| Data Connector Configuration Guide | Step-by-step setup instructions for all data sources and connectors | Week 4 | PDF/Wiki |
| KQL Detection Rules Catalog | Complete documentation of 50+ detection rules with technical details and tuning guidance | Week 8 | Excel/PDF |
| SOAR Playbook Documentation | 50+ playbook specifications with trigger conditions, actions, and integration details | Week 8 | PDF |
| Investigation Playbooks | Incident investigation procedures and forensic analysis workflows | Week 10 | PDF |
| SOC Operations Runbook | System administration, maintenance, and operational procedures | Week 12 | PDF |
| Training Materials | SOC team training slides, labs, and reference guides | Week 11 | PDF/Video |
| As-Built Documentation | Final system configuration, data sources, and integration specifications | Week 12 | PDF |

Table 1: Deliverables

### 4.1 Documentation Deliverables

| Deliverable | Description | Due Date | Format |
| --- | --- | --- | --- |
| Sentinel Deployment Architecture | Detailed design for Sentinel workspace, data connectors, and integration architecture | Week 3 | PDF/Visio |
| Data Connector Configuration Guide | Step-by-step setup instructions for all data sources and connectors | Week 4 | PDF/Wiki |
| KQL Detection Rules Catalog | Complete documentation of 50+ detection rules with technical details and tuning guidance | Week 8 | Excel/PDF |
| SOAR Playbook Documentation | 50+ playbook specifications with trigger conditions, actions, and integration details | Week 8 | PDF |
| Investigation Playbooks | Incident investigation procedures and forensic analysis workflows | Week 10 | PDF |
| SOC Operations Runbook | System administration, maintenance, and operational procedures | Week 12 | PDF |
| Training Materials | SOC team training slides, labs, and reference guides | Week 11 | PDF/Video |
| As-Built Documentation | Final system configuration, data sources, and integration specifications | Week 12 | PDF |

Table 2: Documentation Deliverables

### 4.2 System Deliverables

| Component | Description | Acceptance Criteria |
| --- | --- | --- |
| Sentinel Workspace | Fully configured Azure Sentinel workspace with HA/DR | Workspace operational, data ingestion functional, RBAC configured |
| Data Connectors | 8-10 production data connectors with 300 GB/month ingestion | <1% ingestion failures, <30min latency for hot data |
| Detection Rules | 50+ operational KQL detection rules with tuning | <5% false positive rate, 200+ MITRE ATT&CK techniques covered |
| SOAR Playbooks | 50+ automated incident response playbooks | All playbooks tested, documented, and production-ready |
| Integration Interfaces | API integration with ticketing, communication, and security tools | Successful incident creation, notification, and data enrichment |
| Investigation Tools | Preconfigured workbooks and hunting queries | Query library documented, <5 second query performance |
| Monitoring Setup | Operational monitoring and alerting for Sentinel infrastructure | Functional dashboards and alerts for availability/performance |
| Compliance Reporting | Automated compliance workbooks for HIPAA, PCI-DSS, SOC 2, GDPR | Daily/weekly/monthly reports automatically generated |

Table 3: System Deliverables

### 4.3 Knowledge Transfer Deliverables

• SOC analyst training (40 hours across 2 days, 20 participants max)

• Advanced hunting workshop (8 hours, hands-on)

• Incident response procedures training (4 hours)

• Compliance and audit trail management (2 hours)

• Recorded training sessions for future reference

• Technical documentation and operations runbooks

• Post-training 60-day hypercare support

## 5 Project Timeline & Milestones

| Phase | Duration | Start Date | End Date | Key Milestones |
| --- | --- | --- | --- | --- |
| Discovery & Planning | 2 weeks | [DATE] | [DATE] | Infrastructure assessment approved, Threat landscape documented, Project plan signed off |
| Implementation | 6 weeks | [DATE] | [DATE] | Sentinel workspace deployed, Data connectors operational, Detection rules tuned |
| Testing & Validation | 2 weeks | [DATE] | [DATE] | All tests passed, UAT completed, Go-live approved |
| Deployment & Training | 2 weeks | [DATE] | [DATE] | Production live, Training completed, Support transitioned |

Table 4: Project Timeline And Milestones

### 5.1 Project Phases

| Phase | Duration | Start Date | End Date | Key Milestones |
| --- | --- | --- | --- | --- |
| Discovery & Planning | 2 weeks | [DATE] | [DATE] | Infrastructure assessment approved, Threat landscape documented, Project plan signed off |
| Implementation | 6 weeks | [DATE] | [DATE] | Sentinel workspace deployed, Data connectors operational, Detection rules tuned |
| Testing & Validation | 2 weeks | [DATE] | [DATE] | All tests passed, UAT completed, Go-live approved |
| Deployment & Training | 2 weeks | [DATE] | [DATE] | Production live, Training completed, Support transitioned |

Table 5: Project Phases

### 5.2 Critical Milestones

| Milestone | Target Date |
| --- | --- |
| **Week 2 | ** Discovery complete and requirements approved |
| **Week 4 | ** Sentinel workspace and primary data connectors operational (data flowing) |
| **Week 6 | ** First 30 detection rules deployed and producing detections |
| **Week 8 | ** All 50 detection rules and playbooks operational |
| **Week 10 | ** All testing complete and UAT approved |
| **Week 12 | ** Production go-live and training completion |

Table 6: Project Milestones and Timeline

### 5.3 Critical Dependencies

• Client provides timely access to Azure subscription and on-premises networks

• Data source owners (security tools, infrastructure) available for connector setup

• SOC team and security SMEs available for requirements and testing (60+ hours)

• Business stakeholder participation in decision points (threat landscape, playbook priorities)

• Third-party vendor coordination for EDR, firewall, and SIEM connectors

• Network and firewall rule changes approved for data collection

## 6 Roles & Responsibilities

### 6.1 Vendor Responsibilities (EO Framework Consulting)

• Project Manager: Overall coordination, timeline management, stakeholder communication

• Security Architect: Sentinel design, analytics strategy, threat detection methodology

• Implementation Engineer: Workspace setup, connector configuration, testing

• Analytics Developer: KQL rule development, threat intelligence integration, tuning

• Automation Engineer: Logic Apps development, playbook design, integration

• Training Specialist: Team enablement, hands-on workshops, documentation

• Support Engineer: 60-day hypercare, issue resolution, optimization

### 6.2 Client Responsibilities ([CLIENT_NAME])

• Project Sponsor: Executive oversight and decision authority for scope/timeline/budget

• Security Director: Strategic guidance on threat priorities and compliance requirements

• SOC Manager: Team coordination, incident response process definition

• Technical Lead: Infrastructure coordination, network/security access, third-party vendor liaison

• Data Source Owners: Support for connector setup (firewall, EDR, mail, AD teams)

• Compliance Officer: Compliance requirements definition and audit trail validation

• End Users (SOC Team): Participation in training, testing, and operational procedures

### 6.3 Shared Responsibilities

• Risk management and issue escalation

• Change control and scope management

• Quality assurance and acceptance testing

• Security and compliance validation

• Communication and stakeholder management

## 7 Commercial Terms

| Category | Description | Amount |
| --- | --- | --- |
| Professional Services | Implementation, analytics, automation, training (560 hours) | $126,000 |
| Azure Sentinel & Log Analytics | Year 1 cloud infrastructure costs for 300 GB/month | $182,800 |
| Deployment & Support | Infrastructure setup, hypercare, and initial support | $26,160 |
| **TOTAL PROJECT COST | Total investment for complete 12-week deployment | $335,000 |

Table 7: Commercial Terms

### 7.1 Project Investment

| Category | Description | Amount |
| --- | --- | --- |
| Professional Services | Implementation, analytics, automation, training (560 hours) | $126,000 |
| Azure Sentinel & Log Analytics | Year 1 cloud infrastructure costs for 300 GB/month | $182,800 |
| Deployment & Support | Infrastructure setup, hypercare, and initial support | $26,160 |
| **TOTAL PROJECT COST | Total investment for complete 12-week deployment | $335,000 |

Table 8: Project Investment

### 7.2 Year 1 Total Cost of Ownership

| Category | Amount |
| --- | --- |
| Professional Services (one-time) | $126,000 |
| Azure Cloud Infrastructure (Year 1) | $182,800 |
| Defender for Cloud & Licenses (Year 1) | $8,500 |
| SOAR Automation & Playbooks (Year 1) | $2,400 |
| Support & Maintenance (Year 1) | $17,948 |
| TOTAL YEAR 1 | $337,648 |

Table 9: Year 1 Total Cost Of Ownership

### 7.3 Payment Terms

• 25% upon SOW execution and project kickoff ($83,750)

• 25% upon completion of Implementation Phase (Week 8) ($83,750)

• 25% upon completion of Testing & Validation (Week 10) ($83,750)

• 25% upon go-live and training completion (Week 12) ($83,750)

### 7.4 Ongoing Operational Costs (Years 2-3)

Annual operational costs for years 2 and 3 are approximately $216,808/year including:

• Azure Sentinel & Log Analytics (300 GB/month): $172,800/year

• Defender for Cloud & Additional Licenses: $8,500/year

• SOAR Automation & Custom Playbooks: $2,400/year

• Support & Managed Services: $17,948/year

• Third-party Connectors & Integrations: $5,000/year

• Professional Services for optimization/tuning: $10,000/year (optional)

### 7.5 Additional Services

Any additional services beyond this SOW (e.g., additional data sources, advanced playbook development, extended support) will be quoted separately and require written approval from both parties.

## 8 Acceptance Criteria

### 8.1 Technical Acceptance

The solution will be considered technically accepted when:

• All 8+ data connectors are operational with <1% ingestion failures

• 50+ detection rules deployed and producing alerts at <5% false positive rate

• 50+ SOAR playbooks tested and operational for automated response

• Integration with ticketing, communication, and security tools functional

• Investigation tools and advanced hunting queries operational

• System passes performance testing at 300 GB/month data volume

• Compliance reporting automated and validated

• Security controls implemented and validated

• System achieves 99.9% availability target

### 8.2 Business Acceptance

The project will be considered complete when:

• SOC team signs off on threat detection capability and playbook execution

• Security leadership approves incident response procedures

• Compliance officer validates audit trail and compliance reporting

• Training is completed with >90% team competency assessment

• Documentation is delivered and operationally validated

• System is operational in production environment

• 60-day hypercare support plan is established and functional

## 9 Assumptions & Constraints

### 9.1 Assumptions

• Client will provide necessary access to Azure subscription, data sources, and networks

• Existing infrastructure meets minimum requirements for Sentinel deployment

• Third-party vendors (firewall, EDR, SIEM) will provide connector support

• Security team members (20+) will be available for 60+ hours of training/testing

• Business requirements will remain stable throughout project (change control for major additions)

• Incident response processes will be documented or defined during Discovery phase

### 9.2 Constraints

• Project must comply with existing security and compliance requirements

• Implementation must not disrupt security operations or incident response

• All data handling must meet privacy and regulatory requirements (HIPAA, PCI-DSS, GDPR, SOC 2)

• Solution must integrate with existing Azure and on-premises infrastructure

• Budget and timeline constraints as specified in this SOW

• Data retention policies must comply with organizational and regulatory requirements

## 10 Risk Management

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Data Source Integration Delays | High | Medium | Early vendor coordination, pre-testing of connectors, backup manual log forwarding |
| Analytics Rule Tuning Complexity | Medium | Medium | Start with built-in rules, phased custom rule deployment, SOC team collaboration |
| Analyst Skill Gaps | Medium | High | Comprehensive training, documentation, ongoing support, Microsoft learning resources |
| Performance Under Load | Medium | Low | Load testing before go-live, consumption-based pricing auto-scaling, monitoring |
| Scope Creep | High | Medium | Formal change control process, clear out-of-scope definition, documented deliverables |
| Third-Party Integration Issues | Medium | Medium | API integration testing, vendor support escalation, alternative integration methods |

Table 10: Risk Management

### 10.1 Identified Risks

| Risk | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Data Source Integration Delays | High | Medium | Early vendor coordination, pre-testing of connectors, backup manual log forwarding |
| Analytics Rule Tuning Complexity | Medium | Medium | Start with built-in rules, phased custom rule deployment, SOC team collaboration |
| Analyst Skill Gaps | Medium | High | Comprehensive training, documentation, ongoing support, Microsoft learning resources |
| Performance Under Load | Medium | Low | Load testing before go-live, consumption-based pricing auto-scaling, monitoring |
| Scope Creep | High | Medium | Formal change control process, clear out-of-scope definition, documented deliverables |
| Third-Party Integration Issues | Medium | Medium | API integration testing, vendor support escalation, alternative integration methods |

Table 11: Identified Risks

### 10.2 Change Management

Any changes to project scope, timeline, budget, or deliverables must be documented through formal change requests and approved by both client sponsor and vendor leadership before implementation. Minor clarifications may be handled through email with both parties' written agreement.

## 11 Terms & Conditions

### 11.1 Intellectual Property

• Client retains ownership of all business data, threat intelligence, and information collected during implementation

• Vendor retains ownership of methodologies, tools, templates, and best practices

• Client receives unrestricted license to use all Sentinel configurations, KQL rules, and playbooks post-implementation

• Vendor may reference solution success stories and architecture (with client approval) for marketing

### 11.2 Confidentiality

Both parties agree to maintain strict confidentiality of proprietary information, security data, threat intelligence, and business details throughout the project and for 2 years following completion.

### 11.3 Warranty & Support

• 90-day warranty on all professional services deliverables from go-live date

• Defect resolution included at no additional cost during warranty period

• 60-day hypercare support included (8x5 business hours, <4hr response)

• Extended support available under separate maintenance agreement

### 11.4 Limitation of Liability

Vendor's liability is limited to the total contract value. Neither party shall be liable for indirect, incidental, consequential, or punitive damages. Client is responsible for maintaining independent backups and disaster recovery capabilities.

## 12 Approval & Signatures

By signing below, both parties agree to the scope, approach, and terms outlined in this Statement of Work.

| CLIENT | CONSULTING COMPANY |
| --- | --- |
| Signature: ____________________ | Signature: ____________________ |
| Name: ____________________ | Name: ____________________ |
| Title: ____________________ | Title: ____________________ |
| Date: ____________________ | Date: ____________________ |

### 12.1 Client Approval ([CLIENT_NAME])

### 12.2 Vendor Approval ([VENDOR_NAME])

Document Control:
File Name: SOW_AzureSentinel_[CLIENT_NAME]_[DATE]
Version: 1.0
Last Modified: [DATE]
Next Review: [REVIEW_DATE]

This Statement of Work constitutes the complete agreement between the parties for the services described herein and supersedes all prior negotiations, representations, or agreements relating to the subject matter.

_______________________________________________

www.eoframework.org