## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Virtual Desktop
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Description | Acceptance Criteria | Source | Owner | Status | Dependencies | Test Method | Compliance | Notes | Estimated Effort
REQ-001 | Functional | Virtual Desktop | Critical | System must provide Windows 11 multi-session virtual desktops | Deploy scalable Windows 11 multi-session environments with 95%+ availability | Business Stakeholder | Cloud Architect | Draft | Azure AVD service | Availability testing |  | Core virtual desktop functionality | 40 hours
REQ-002 | Functional | Virtual Desktop | Critical | System must support personal and pooled desktop configurations | Provide both dedicated and shared virtual desktop options | Business Stakeholder | Cloud Architect | Draft | REQ-001 | Configuration testing |  | Different user experience models | 32 hours
REQ-003 | Functional | Application Delivery | High | System must support MSIX app attach for application virtualization | Deploy applications using MSIX packages with instant availability | Business Stakeholder | Application Engineer | Draft | Application inventory | Application testing |  | Modern application delivery model | 80 hours
REQ-004 | Functional | User Profiles | Critical | Implement FSLogix profile containers for consistent user experience | Seamless roaming profiles across sessions with 99%+ reliability | Business User | Profile Engineer | Draft | REQ-001 | Profile testing |  | Essential for user experience continuity | 60 hours
REQ-005 | Functional | Application Access | Critical | Provide access to business-critical applications via virtual desktop | All business applications accessible with native performance | Department Managers | Application Engineer | Draft | REQ-003 | Application performance testing |  | Business continuity requirement | 100 hours
REQ-006 | Functional | Remote Access | High | Enable secure remote access from any device and location | Support Windows Mac iOS Android with consistent experience | IT Security | Security Architect | Draft | REQ-002 | Multi-device testing | Security | BYOD and remote work enablement | 70 hours
REQ-007 | Functional | Session Management | Critical | Provide seamless session management and reconnection | Automatic session recovery and reconnection capabilities | Business User | Technical Lead | Draft |  | Session testing |  | User productivity requirement | 40 hours
REQ-008 | Functional | File Access | Critical | Integrate with existing file shares and cloud storage | Native access to network drives and cloud storage services | Business User | Storage Engineer | Draft | REQ-004 | File access testing |  | Business data accessibility | 32 hours
REQ-009 | Functional | Printing | High | Support network and local printing from virtual sessions | Print to any accessible printer with driver management | Business User | Desktop Engineer | Draft | REQ-001 | Printing testing |  | Standard business functionality | 50 hours
REQ-010 | Functional | Audio/Video | High | Provide high-quality audio and video capabilities | HD video conferencing and multimedia playback support | Business User | Desktop Engineer | Draft | REQ-001 | AV testing |  | Modern workplace collaboration | 45 hours
REQ-011 | Non-Functional | Performance | Critical | Virtual desktops must meet response time requirements | Login time under 30 seconds application launch under 10 seconds | Business Stakeholder | Performance Engineer | Draft | Host pool configuration | Performance testing | SLA | User experience critical
REQ-012 | Non-Functional | Scalability | Critical | System must auto-scale based on user demand | Automatic host pool scaling with 95%+ user accommodation | Business Stakeholder | Cloud Architect | Draft | Azure auto-scaling | Load testing |  | Cost optimization and performance
REQ-013 | Non-Functional | Availability | High | System must maintain high availability for business hours | 99.9% uptime during business hours with redundancy | Technical Team | Cloud Architect | Draft | Multi-region deployment | Uptime monitoring | SLA | Business continuity requirement
REQ-014 | Non-Functional | Capacity | High | Support concurrent user sessions based on business needs | Handle 500+ concurrent users with consistent performance | Technical Team | Capacity Engineer | Draft | Performance testing | Load testing |  | Business growth accommodation
REQ-015 | Security | Identity Management | Critical | Integrate with Azure Active Directory for authentication | Single sign-on with existing corporate credentials | Security Team | Identity Architect | Draft | Azure AD setup | Authentication testing | Compliance | Zero trust security model | 24 hours
REQ-016 | Security | Access Control | Critical | Implement conditional access policies for virtual desktop access | Multi-factor authentication and device compliance enforcement | Security Team | Security Architect | Draft | REQ-015 | Security testing | Zero Trust | Advanced security posture | 16 hours
REQ-017 | Security | Data Protection | Critical | Ensure data remains secure within Azure boundaries | No data persistence on local devices with encryption | Security Team | Security Architect | Draft | Azure encryption | Data protection audit | GDPR | Data residency and protection | 40 hours
REQ-018 | Security | Network Security | Critical | Implement network segmentation and secure connectivity | Virtual desktop traffic isolation with encrypted connections | Security Team | Network Security Engineer | Draft | Network design | Security testing | Compliance | Network zero trust implementation | 32 hours
REQ-019 | Security | Session Security | High | Implement session timeout and security policies | Automatic session timeout and secure session management | Security Team | Security Engineer | Draft | REQ-007 | Security testing | Compliance | Session-based security controls | 24 hours
REQ-020 | Security | Audit Logging | High | Log all virtual desktop access and activities | Complete audit trail for compliance and security monitoring | Compliance Team | Security Engineer | Draft | Azure Monitor setup | Audit review | SOX | Regulatory compliance requirement | 32 hours
REQ-021 | Integration | Active Directory | High | Integrate with on-premises Active Directory infrastructure | Seamless domain join and GPO application | IT Team | Directory Services Engineer | Draft | AD connectivity | Integration testing |  | Existing infrastructure integration | 60 hours
REQ-022 | Integration | File Services | Medium | Integrate with existing file server infrastructure | Native access to network file shares and DFS | IT Team | Storage Engineer | Draft | Network connectivity | File access testing |  | Business data accessibility | 50 hours
REQ-023 | Integration | Backup Systems | Medium | Integrate with enterprise backup solutions | Automated backup of user profiles and application data | IT Team | Backup Administrator | Draft | Backup infrastructure | Backup testing | Data protection | Data protection requirement | 30 hours
REQ-024 | Usability | User Experience | High | Provide intuitive virtual desktop access interface | One-click access with minimal user training required | End User | UX Designer | Draft | Web portal development | Usability testing | Accessibility | User adoption critical | 80 hours
REQ-025 | Usability | Application Experience | High | Ensure applications perform like local installations | Native application experience without virtualization awareness | End User | Application Engineer | Draft | REQ-003 | Application testing |  | User productivity requirement | 90 hours
REQ-026 | Usability | Mobile Access | Medium | Provide mobile device access to virtual desktops | Optimized experience for tablets and smartphones | Mobile Users | Mobile Developer | Draft | REQ-006 | Mobile testing |  | Modern workplace flexibility | 60 hours
REQ-027 | Management | Host Pool Management | High | Provide centralized management of virtual desktop resources | Azure portal-based management with role-based access | IT Administrator | Azure Administrator | Draft | Azure RBAC | Management testing |  | Operational efficiency | 70 hours
REQ-028 | Management | Image Management | High | Support automated image updates and patching | Automated Windows updates and application patching | IT Administrator | Image Engineer | Draft | Image pipeline | Update testing | Security | Security and compliance maintenance | 50 hours
REQ-029 | Management | Monitoring | Medium | Implement comprehensive monitoring and alerting | Real-time monitoring with proactive alerting capabilities | Operations Team | Monitoring Engineer | Draft | Azure Monitor setup | Monitoring validation |  | Operational visibility | 100 hours
REQ-030 | Management | Cost Management | High | Provide cost visibility and optimization controls | Resource usage tracking with cost optimization recommendations | Finance Team | Cost Engineer | Draft | Azure Cost Management | Cost reporting |  | Budget control and optimization | 40 hours
REQ-031 | Operational | Backup | Critical | Implement automated backup for user data and profiles | Daily backup of FSLogix profiles with point-in-time recovery | Operations Team | Backup Engineer | Draft | Backup solution | Backup testing | Data protection | Data loss prevention | 40 hours
REQ-032 | Operational | Disaster Recovery | Critical | Implement disaster recovery procedures | RTO 4 hours RPO 2 hours for virtual desktop services | Operations Team | DR Engineer | Draft | Multi-region setup | DR testing | Business continuity | Business resilience requirement | 32 hours
REQ-033 | Operational | Capacity Planning | High | Implement automated capacity planning and forecasting | Predictive scaling based on usage patterns and growth | Operations Team | Capacity Engineer | Draft | Monitoring data | Capacity testing |  | Performance and cost optimization | 60 hours
REQ-034 | Compliance | Data Residency | Critical | Ensure data remains within specified geographic boundaries | All user data and sessions within approved Azure regions | Compliance Team | Cloud Architect | Draft | Azure region selection | Compliance audit | GDPR | Regulatory compliance requirement | 50 hours
REQ-035 | Compliance | Access Auditing | High | Maintain detailed access logs for compliance reporting | Complete audit trail of user access and administrative actions | Compliance Team | Audit Engineer | Draft | REQ-020 | Compliance testing | Multiple | Regulatory compliance requirement | 40 hours
REQ-036 | Infrastructure | Azure Subscription | Critical | Azure subscription with appropriate service quotas and permissions | Administrative access to Azure with AVD service availability | Infrastructure Team | Cloud Administrator | Draft |  | Service validation |  | Foundation requirement for implementation | 8 hours
REQ-037 | Infrastructure | Network Connectivity | Critical | Reliable network connectivity between on-premises and Azure | Dedicated connection with sufficient bandwidth for user traffic | Infrastructure Team | Network Engineer | Draft | REQ-036 | Connectivity testing |  | User experience and performance critical | 4 hours
REQ-038 | Infrastructure | Storage Performance | Critical | High-performance storage for virtual desktop workloads | Premium SSD storage with IOPS sufficient for user load | Infrastructure Team | Storage Engineer | Draft | REQ-036 | Storage testing |  | Virtual desktop performance requirement | 4 hours
REQ-039 | Infrastructure | Compute Resources | High | Azure compute resources sized for expected virtual desktop workloads | VM families optimized for virtual desktop with auto-scaling | Infrastructure Team | Capacity Engineer | Draft | Workload analysis | Load testing | Performance | Scale based on user concurrency | 16 hours
REQ-040 | Infrastructure | Identity Services | Critical | Azure Active Directory with appropriate licensing | Azure AD Premium licensing for conditional access features | Infrastructure Team | Identity Administrator | Draft | Licensing procurement | Service testing | Security | Essential for security features | 8 hours
REQ-041 | Infrastructure | Monitoring Services | High | Azure Monitor and Log Analytics for comprehensive monitoring | Monitoring workspace with appropriate data retention | Infrastructure Team | Monitoring Engineer | Draft | Azure subscription | Monitoring setup |  | Operational visibility requirement | 12 hours
REQ-042 | Skills | Technical Team | Critical | Azure Virtual Desktop architect with 3+ years AVD experience | Proven AVD design and implementation experience | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Essential for technical leadership
REQ-043 | Skills | Technical Team | Critical | Windows virtualization expertise with 5+ years VDI experience | Proven virtual desktop and application virtualization experience | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Critical for implementation success
REQ-044 | Skills | Technical Team | High | Azure security specialist with 3+ years cloud security experience | Proven Azure security and compliance implementation | HR Team | Project Manager | Draft | Team recruitment | Skill assessment | Security | Essential for security implementation
REQ-045 | Skills | Development Team | High | PowerShell and automation experts with 3+ years experience | Proven infrastructure automation and scripting experience | HR Team | Technical Lead | Draft | Team recruitment | Skill assessment |  | Automation and efficiency requirement
REQ-046 | Budget | Project Costs | Critical | Infrastructure budget approved for Azure virtual desktop costs | Monthly Azure costs $15000-$75000 approved and allocated | Finance Team | Project Sponsor | Draft | Cost estimates | Budget approval | Financial | Based on user count and usage patterns
REQ-047 | Budget | Project Costs | Critical | Professional services budget approved for AVD implementation | Implementation costs $125000-$300000 approved | Finance Team | Project Sponsor | Draft | SOW approval | Budget approval | Financial | Includes training and knowledge transfer
REQ-048 | Security | Endpoint Protection | Critical | Endpoint protection for virtual desktop sessions | Anti-malware and endpoint detection response for sessions | Security Team | Security Engineer | Draft | Security solution | Security testing | Security | Virtual desktop security requirement | 24 hours
REQ-049 | Security | Data Loss Prevention | Critical | Data loss prevention policies for virtual desktop environment | DLP policies preventing data exfiltration from sessions | Security Team | DLP Administrator | Draft | DLP solution | Security testing | Compliance | Data protection and compliance | 16 hours
REQ-050 | Compliance | Regulatory Compliance | High | Compliance frameworks validated for virtual desktop environment | SOC 2 ISO 27001 HIPAA compliance requirements addressed | Compliance Team | Compliance Officer | Draft | Compliance assessment | Compliance audit | Multiple | Industry-specific compliance requirements | 20 hours
REQ-051 | Testing | User Acceptance | High | User acceptance testing with business representatives | UAT process with real business scenarios and workflows | QA Team | Business Analyst | Draft | Business requirements | UAT execution |  | Business validation requirement | 16 hours
REQ-052 | Testing | Performance | High | Performance testing under realistic user loads | Load testing with expected concurrent user scenarios | QA Team | Performance Engineer | Draft | Performance tools | Performance testing | SLA | Performance validation requirement | 24 hours
REQ-053 | Operations | Service Desk | High | Service desk procedures for virtual desktop support | Support procedures and escalation paths for AVD issues | Operations Team | Service Desk Manager | Draft | Support processes | Support testing | SLA | User support requirement | 32 hours
REQ-054 | Training | User Training | Medium | Comprehensive user training for virtual desktop adoption | Training materials and sessions for all virtual desktop users | Training Team | Training Manager | Draft | Training development | Training evaluation |  | User adoption and productivity
REQ-055 | Training | Administrator Training | High | Technical training for IT administrators on AVD management | Admin training on Azure portal management and troubleshooting | Training Team | Technical Trainer | Draft | Solution deployment | Training validation |  | Operational readiness requirement