## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Virtual Wan Global
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Description | Acceptance Criteria | Source | Owner | Status | Dependencies | Test Method | Compliance | Notes | Estimated Effort
REQ-001 | Functional | Global Connectivity | Critical | System must provide global hub-and-spoke connectivity via Azure Virtual WAN | Deploy scalable Virtual WAN with 99.9%+ availability | Business Stakeholder | Network Architect | Draft | Azure Virtual WAN service | Connectivity testing |  | Core global networking functionality | 40 hours
REQ-002 | Functional | Hub Deployment | Critical | System must deploy regional Virtual WAN hubs for optimal performance | Minimum 4 regional hubs with automatic routing | Business Stakeholder | Network Architect | Draft | REQ-001 | Hub testing |  | Regional performance optimization | 32 hours
REQ-003 | Functional | Branch Connectivity | High | System must connect all branch offices via site-to-site VPN | 25+ branch sites with redundant connectivity | Business Stakeholder | Network Engineer | Draft | Site requirements | Connectivity testing |  | Business continuity requirement | 80 hours
REQ-004 | Functional | ExpressRoute Integration | Critical | Implement ExpressRoute connectivity for primary data center connections | Private dedicated connectivity with 99.95% SLA | Network Team | Network Architect | Draft | REQ-001 | Circuit testing |  | Mission-critical connectivity | 60 hours
REQ-005 | Functional | Traffic Routing | Critical | Implement intelligent traffic routing and optimization | Automatic optimal path selection with load balancing | Network Team | Network Engineer | Draft | REQ-002 | Routing testing |  | Performance optimization requirement | 100 hours
REQ-006 | Functional | Security Integration | High | Integrate Azure Firewall for centralized security enforcement | Unified security policy across all connections | Security Team | Security Architect | Draft | REQ-002 | Security testing | Security | Network security requirement | 70 hours
REQ-007 | Functional | Redundancy | Critical | Provide redundant connectivity for business continuity | Multiple path redundancy with automatic failover | Business Stakeholder | Network Architect | Draft |  | Failover testing |  | Business continuity critical | 40 hours
REQ-008 | Functional | Bandwidth Management | Critical | Implement dynamic bandwidth allocation and optimization | Automatic bandwidth scaling based on demand | Network Team | Network Engineer | Draft | REQ-005 | Bandwidth testing |  | Cost and performance optimization | 32 hours
REQ-009 | Functional | Inter-Hub Connectivity | High | Enable seamless connectivity between all Virtual WAN hubs | Any-to-any connectivity with optimized routing | Network Team | Network Engineer | Draft | REQ-002 | Inter-hub testing |  | Global communication requirement | 50 hours
REQ-010 | Functional | SD-WAN Integration | High | Integrate with SD-WAN solutions for branch optimization | Support for major SD-WAN vendors and protocols | Network Team | SD-WAN Specialist | Draft | REQ-003 | SD-WAN testing |  | Branch optimization and flexibility | 45 hours
REQ-011 | Non-Functional | Performance | Critical | Network must meet latency and throughput requirements | Inter-hub latency <50ms globally application response <100ms | Business Stakeholder | Performance Engineer | Draft | Hub placement | Performance testing | SLA | User experience critical
REQ-012 | Non-Functional | Scalability | Critical | System must scale to accommodate growth and demand | Support 100+ sites with automatic scaling | Business Stakeholder | Network Architect | Draft | Azure scaling | Load testing |  | Business growth accommodation
REQ-013 | Non-Functional | Availability | High | Network must maintain high availability for business operations | 99.9% uptime with redundant paths | Technical Team | Network Architect | Draft | Redundant design | Uptime monitoring | SLA | Business continuity requirement
REQ-014 | Non-Functional | Throughput | High | Network must support required bandwidth and traffic volumes | Aggregate throughput 50+ Gbps with burst capability | Technical Team | Capacity Engineer | Draft | Bandwidth planning | Throughput testing |  | Application performance requirement
REQ-015 | Security | Network Security | Critical | Implement comprehensive network security controls | Azure Firewall with threat intelligence and DDoS protection | Security Team | Security Architect | Draft | Firewall deployment | Security testing | Compliance | Network security posture | 24 hours
REQ-016 | Security | Traffic Inspection | Critical | Implement deep packet inspection and threat detection | Advanced threat protection with real-time blocking | Security Team | Security Engineer | Draft | REQ-015 | Security testing | Security | Threat protection requirement | 16 hours
REQ-017 | Security | Access Control | Critical | Implement network access controls and segmentation | Micro-segmentation with zero trust principles | Security Team | Security Architect | Draft | Network design | Access testing | Zero Trust | Network security architecture | 40 hours
REQ-018 | Security | Encryption | Critical | Ensure all network traffic is encrypted in transit | IPSec VPN tunnels and TLS encryption | Security Team | Encryption Specialist | Draft | VPN configuration | Encryption testing | Compliance | Data protection requirement | 32 hours
REQ-019 | Security | Monitoring | High | Implement security monitoring and logging | Comprehensive network security event logging | Security Team | Security Engineer | Draft | Monitoring setup | Security audit | SOC2 | Security visibility requirement | 24 hours
REQ-020 | Security | Compliance | High | Ensure network design meets regulatory compliance | Compliance with industry standards and regulations | Compliance Team | Compliance Engineer | Draft | Security controls | Compliance audit | Multiple | Regulatory requirement | 32 hours
REQ-021 | Integration | Legacy Systems | High | Integrate with existing network infrastructure and systems | Seamless integration with current MPLS and systems | IT Team | Integration Specialist | Draft | Current network | Integration testing |  | Business continuity during migration | 60 hours
REQ-022 | Integration | DNS Services | Medium | Integrate with existing DNS infrastructure | Support for internal DNS resolution and forwarding | IT Team | DNS Administrator | Draft | DNS infrastructure | DNS testing |  | Application functionality requirement | 50 hours
REQ-023 | Integration | Monitoring Systems | Medium | Integrate with existing network monitoring solutions | SNMP and API integration with current tools | IT Team | Monitoring Engineer | Draft | Monitoring tools | Integration testing |  | Operational visibility requirement | 30 hours
REQ-024 | Usability | Management Interface | High | Provide intuitive network management interface | Azure portal-based management with RBAC | Network Administrator | UI/UX Designer | Draft | Azure portal | Usability testing | Accessibility | Operational efficiency | 80 hours
REQ-025 | Usability | Monitoring Dashboard | High | Provide comprehensive network monitoring dashboards | Real-time visibility with customizable views | Network Operations | Dashboard Developer | Draft | Monitoring data | Dashboard testing |  | Operational visibility requirement | 90 hours
REQ-026 | Usability | Troubleshooting Tools | Medium | Provide network troubleshooting and diagnostic tools | Built-in diagnostics with guided troubleshooting | Network Support | Tools Developer | Draft | Network deployment | Tool testing |  | Support efficiency requirement | 60 hours
REQ-027 | Management | Configuration Management | High | Implement infrastructure as code for network configurations | Automated deployment with version control | DevOps Team | DevOps Engineer | Draft | IaC templates | Config testing |  | Consistency and repeatability | 70 hours
REQ-028 | Management | Change Management | High | Implement network change management procedures | Controlled change process with approval workflows | Network Operations | Change Manager | Draft | Process definition | Change testing | ITIL | Operational stability | 50 hours
REQ-029 | Management | Capacity Planning | Medium | Implement automated capacity planning and forecasting | Predictive analytics for network capacity | Operations Team | Capacity Engineer | Draft | Monitoring data | Capacity testing |  | Performance and cost optimization | 100 hours
REQ-030 | Management | Cost Optimization | High | Provide network cost visibility and optimization | Real-time cost tracking with optimization recommendations | Finance Team | Cost Engineer | Draft | Azure billing | Cost reporting |  | Budget control requirement | 40 hours
REQ-031 | Operational | Backup | Critical | Implement automated backup of network configurations | Daily backup of all network device configurations | Operations Team | Backup Engineer | Draft | Configuration management | Backup testing | Data protection | Configuration recovery capability | 40 hours
REQ-032 | Operational | Disaster Recovery | Critical | Implement network disaster recovery procedures | RTO 2 hours RPO 15 minutes for network services | Operations Team | DR Engineer | Draft | Multi-region setup | DR testing | Business continuity | Business resilience requirement | 32 hours
REQ-033 | Operational | Performance Monitoring | High | Implement continuous network performance monitoring | Real-time performance metrics with alerting | Operations Team | Performance Engineer | Draft | Monitoring deployment | Performance testing |  | Proactive issue detection | 60 hours
REQ-034 | Compliance | Data Residency | Critical | Ensure network traffic remains within approved geographic boundaries | All traffic routing within specified regions | Compliance Team | Network Architect | Draft | Regional design | Compliance testing | GDPR | Regulatory compliance requirement | 50 hours
REQ-035 | Compliance | Audit Logging | High | Maintain detailed network access and configuration logs | Complete audit trail for compliance reporting | Compliance Team | Audit Engineer | Draft | Logging setup | Audit review | Multiple | Regulatory compliance requirement | 40 hours
REQ-036 | Infrastructure | Azure Subscription | Critical | Azure subscription with Virtual WAN service and appropriate quotas | Administrative access with Virtual WAN service enabled | Infrastructure Team | Cloud Administrator | Draft |  | Service validation |  | Foundation requirement | 8 hours
REQ-037 | Infrastructure | Network Connectivity | Critical | High-speed internet connectivity at all sites | Sufficient bandwidth for VPN and application traffic | Infrastructure Team | ISP Coordinator | Draft | Site surveys | Connectivity testing |  | Site connectivity requirement | 4 hours
REQ-038 | Infrastructure | ExpressRoute Circuits | Critical | ExpressRoute circuits with sufficient bandwidth | Dedicated circuits with redundancy and SLA | Infrastructure Team | Circuit Manager | Draft | REQ-036 | Circuit testing |  | Mission-critical connectivity | 4 hours
REQ-039 | Infrastructure | Compute Resources | High | Azure compute resources for Virtual WAN hubs and gateways | Hub gateways sized for expected traffic loads | Infrastructure Team | Capacity Engineer | Draft | Traffic analysis | Load testing | Performance | Scale based on traffic requirements | 16 hours
REQ-040 | Infrastructure | Storage Resources | Medium | Azure storage for configuration backup and logging | Sufficient storage with appropriate retention policies | Infrastructure Team | Storage Engineer | Draft | Data retention | Storage testing |  | Operational data storage | 8 hours
REQ-041 | Infrastructure | Monitoring Resources | High | Azure Monitor and Log Analytics for network monitoring | Monitoring workspace with appropriate data retention | Infrastructure Team | Monitoring Engineer | Draft | Azure subscription | Monitoring setup |  | Operational visibility requirement | 12 hours
REQ-042 | Skills | Technical Team | Critical | Network architect with 5+ years WAN and Azure experience | Proven Azure networking and Virtual WAN expertise | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Essential for technical leadership
REQ-043 | Skills | Technical Team | Critical | Security engineer with 3+ years Azure security experience | Proven Azure Firewall and network security implementation | HR Team | Project Manager | Draft | Team recruitment | Skill assessment | Security | Critical for security implementation
REQ-044 | Skills | Technical Team | High | Field engineers with 3+ years site deployment experience | Proven site-to-site VPN and equipment deployment | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Essential for site deployment
REQ-045 | Skills | Operations Team | High | Network operations engineers with 3+ years Azure experience | Proven Azure networking monitoring and troubleshooting | HR Team | Technical Lead | Draft | Team recruitment | Skill assessment |  | Operational readiness requirement
REQ-046 | Budget | Project Costs | Critical | Infrastructure budget approved for Azure Virtual WAN costs | Monthly Azure costs $25000-$100000 approved | Finance Team | Project Sponsor | Draft | Cost estimates | Budget approval | Financial | Based on hub count and traffic volume
REQ-047 | Budget | Project Costs | Critical | Professional services budget approved for implementation | Implementation costs $200000-$500000 approved | Finance Team | Project Sponsor | Draft | SOW approval | Budget approval | Financial | Includes training and knowledge transfer
REQ-048 | Security | Threat Protection | Critical | Advanced threat protection for network traffic | Real-time threat detection and automatic blocking | Security Team | Threat Engineer | Draft | Security deployment | Security testing | Security | Network threat protection | 24 hours
REQ-049 | Security | DDoS Protection | Critical | DDoS protection for all Virtual WAN endpoints | Azure DDoS Protection Standard with monitoring | Security Team | DDoS Specialist | Draft | Service enablement | DDoS testing | Security | Service availability protection | 16 hours
REQ-050 | Compliance | Network Compliance | High | Network design compliance with industry standards | SOC 2 ISO 27001 PCI DSS compliance validation | Compliance Team | Compliance Officer | Draft | Compliance assessment | Compliance audit | Multiple | Industry-specific compliance | 20 hours
REQ-051 | Testing | Integration Testing | High | Comprehensive integration testing of all network components | End-to-end connectivity and application testing | QA Team | Test Engineer | Draft | Component deployment | Integration testing |  | System validation requirement | 16 hours
REQ-052 | Testing | Performance Testing | High | Network performance testing under realistic loads | Load testing with expected traffic patterns | QA Team | Performance Engineer | Draft | Performance tools | Performance testing | SLA | Performance validation requirement | 24 hours
REQ-053 | Operations | Support Procedures | High | Network support procedures and escalation processes | 24/7 support capability with clear escalation | Operations Team | Support Manager | Draft | Support processes | Support testing | SLA | User support requirement | 32 hours
REQ-054 | Training | Network Training | Medium | Comprehensive training for network administrators | Training on Virtual WAN management and troubleshooting | Training Team | Training Manager | Draft | Solution deployment | Training evaluation |  | Operational readiness
REQ-055 | Training | Security Training | High | Security training for network and security teams | Training on Azure Firewall and threat protection | Training Team | Security Trainer | Draft | Security deployment | Training validation | Security | Security operational readiness