## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Network Analytics
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive Status Report | Executive Sponsors | AI network analytics project status and intelligence transformation progress | Weekly | Email Report | EO Project Manager | Email distribution list |  | "AI model performance, network insights, anomaly detection results, key decisions" | EO Quarterback and IT Director | Executive | Report delivered on time and strategic decisions made | Active | [DATE] | Include AI accuracy metrics and operational impact
COMM-002 | AI Analytics Steering Committee | Project Steering Committee | Strategic direction for AI-driven network operations implementation | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | "AI strategy, model performance, network insights, budget, timeline" | EO Quarterback and Department Heads | Strategic | Meeting attendance >80% and critical decisions documented | Active | [DATE] | Decision authority for AI model requirements
COMM-003 | Development Team Standup | Core AI Analytics Team | Daily coordination for AI model development and platform deployment | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | "Model training progress, data ingestion status, platform integration" | Development Team and Data Scientists | Operational | Daily attendance >90% and technical blockers resolved | Active | [DATE] | Focus on AI model development and data pipeline
COMM-004 | AI Architecture Review | Technical and Data Science Teams | AI model architecture and network analytics optimization | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | "Model architecture, training data quality, anomaly detection accuracy" | EO Sales Engineer (Solution Architecture) and Data Scientists | Technical | AI decisions documented and performance targets achieved | Active | [DATE] | Include model validation and network analytics results
COMM-005 | Network Analytics Risk Review | Risk Management Team | AI model risks and network monitoring performance | Bi-weekly | Risk Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Model accuracy risks, false positive rates, network blind spots" | EO Project Manager and EO Delivery Engineer (Technical Leadership) | Management | Risk register updated and AI-specific mitigations tracked | Active | [DATE] | Focus on AI operational risks and model reliability
COMM-006 | Network Operations Feedback | Network Engineers and Operations | AI insights validation and network analytics feedback | Weekly | Workshop Session | EO Sales Engineer | Workshop invitation | 120 minutes | "Anomaly detection accuracy, insights relevance, operational workflow" | Network Operations Team and NOC Engineers | Business | User sign-off on AI insights accuracy and operational value | Active | [DATE] | Include hands-on testing of analytics platform
COMM-007 | AI Model Sprint Review | AI Development Team | Model training progress and analytics demonstrations | Bi-weekly | Demo Meeting | EO Quarterback | Video conference | 60 minutes | "Model training results, anomaly detection demos, performance metrics" | Data Science Team and Product Owner | Team | Model accuracy goals achieved and feedback incorporated | Active | [DATE] | Live demonstration of network anomaly detection
COMM-008 | Cisco Platform Coordination | Cisco Technical Teams | Cisco AI platform optimization and integration coordination | Weekly | Technical Call | EO Engineer | Conference call | 45 minutes | "Platform performance, model deployment, integration optimization" | Cisco Technical Team and EO Sales Engineer (Solution Architecture) | Technical | Cisco platform performance targets met and issues resolved | Active | [DATE] | Track platform SLAs and optimization opportunities
COMM-009 | Data Quality Review | Data Engineering and Network Teams | Network data quality and AI model input validation | Weekly | Quality Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Data collection quality, telemetry validation, model input accuracy" | Data Engineers and Network SMEs | Quality | Data quality gates met and model inputs validated | Active | [DATE] | Include network telemetry analysis and data validation
COMM-010 | Change Control Board | Change Control Board | AI model updates and network analytics modifications | As Needed | Change Meeting | EO Engineer | Meeting invitation | 60 minutes | "Model updates, detection rules, platform configuration changes" | Change Control Board Members | Governance | Change requests processed within SLA and impact assessed | Active | [DATE] | Include AI model versioning and rollback procedures
COMM-011 | User Training Update | Training and Network Operations Teams | AI platform training progress and adoption readiness | Bi-weekly | Training Call | EO Engineer | Conference call | 30 minutes | "Training material development, user competency, platform adoption" | Training Team and Network Managers | Operational | Training materials ready and user competency validated | Active | [DATE] | Include hands-on AI platform training sessions
COMM-012 | Security and Compliance Review | Security and Network Teams | AI platform security and network data protection | Monthly | Security Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Data protection, model security, compliance validation, access controls" | Security Team and Compliance Officer | Security | Security requirements met and compliance validated | Active | [DATE] | Include network data security and AI model protection
COMM-013 | Platform Infrastructure Update | Infrastructure and DevOps Teams | AI platform infrastructure performance and scaling | Weekly | Infrastructure Call | EO Engineer | Conference call | 30 minutes | "Platform performance, resource utilization, scaling requirements" | Infrastructure Team and Platform Engineers | Technical | Infrastructure performance targets met and scaling optimized | Active | [DATE] | Include compute resource monitoring and optimization
COMM-014 | Business Value Assessment | Business Stakeholders | Network performance improvements and operational benefits | Bi-weekly | Business Meeting | EO Quarterback | Meeting invitation | 45 minutes | "Network reliability improvements, operational efficiency, cost benefits" | Business Managers and Network Directors | Business | Business value criteria met and benefits quantified | Active | [DATE] | Include network uptime improvements and cost savings
COMM-015 | Go-Live Preparation | Go-Live Coordination Team | Production deployment and AI platform go-live readiness | Daily (2 weeks before) | Go-Live Meeting | EO Project Manager | Video conference | 30 minutes | "Deployment checklist, production readiness, monitoring procedures" | All Team Leads and Operations Manager | Critical | Go-live criteria met and AI platform deployment ready | Planned | [DATE] | Intensive coordination for AI platform production deployment
COMM-016 | Post-Implementation Review | Project and Operations Teams | AI platform performance review and optimization opportunities | Monthly (3 months) | Review Meeting | EO Quarterback | Meeting invitation | 90 minutes | "Model accuracy trends, operational efficiency, enhancement opportunities" | Core Project Team and Business Stakeholders | Review | Performance improvements identified and AI roadmap created | Planned | [DATE] | Include model drift analysis and continuous improvement
COMM-017 | Critical Issue Escalation | Emergency Response Team | Critical AI platform failures and network monitoring issues | As Needed | Emergency Call | EO Sales Engineer | Emergency notification | Variable | "Platform failures, model accuracy degradation, monitoring outages" | Incident Response Team and Management | Emergency | Critical issues resolved within SLA and service restored | Active | [DATE] | Include AI platform emergency procedures
COMM-018 | Stakeholder Briefing | All Project Stakeholders | General AI analytics project updates and network intelligence progress | Monthly | All-Hands Meeting | EO Project Manager | Town hall meeting | 45 minutes | "AI implementation progress, network insights, operational improvements" | All Project Stakeholders | Informational | Stakeholder engagement maintained and AI value communicated | Active | [DATE] | Include AI achievements and network intelligence success stories
COMM-019 | Technical Deep Dive | Technical and Data Science Teams | AI technical knowledge sharing and network analytics optimization | As Needed | Technical Session | EO Quarterback | Meeting invitation | 90 minutes | "Model architecture challenges, training optimization, analytics solutions" | Technical Team Members and Data Scientists | Technical | Technical challenges resolved and AI knowledge shared | Active | [DATE] | Include AI best practices and model optimization guides
COMM-020 | Client Update Call | External Client | Client AI analytics progress and network intelligence value | Bi-weekly | Client Call | EO Project Manager | Client meeting | 45 minutes | "AI implementation progress, network insights, operational value" | Client Stakeholders and Account Manager | Client | Client satisfaction maintained and AI value proposition communicated | Active | [DATE] | Professional communication with clear AI business value
COMM-021 | Model Performance Review | Data Science and Operations | AI model accuracy monitoring and retraining planning | Weekly | Performance Meeting | EO Quarterback | Video conference | 45 minutes | "Accuracy trends, model drift detection, retraining requirements" | Data Scientists and Operations Team | Technical | Model performance maintained above thresholds and drift detected | Active | [DATE] | Include model monitoring dashboards and training schedules
COMM-022 | Network Intelligence Review | Network and Business Teams | Network insights and analytics value assessment | Bi-weekly | Intelligence Meeting | EO Quarterback | Meeting invitation | 60 minutes | "Network insights quality, operational impact, analytics effectiveness" | Network SMEs and Business Analysts | Business | Analytics value validated and insights actionable | Active | [DATE] | Include network intelligence examples and operational improvements
COMM-023 | Integration Status Review | Integration and Platform Teams | AI platform integration with network tools and systems | Weekly | Integration Meeting | EO Engineer | Meeting invitation | 45 minutes | "Integration health, API performance, data flow validation" | Integration Team and Platform Engineers | Technical | Integration performance targets met and data flows validated | Active | [DATE] | Include ITSM integration and automation workflows
COMM-024 | Anomaly Detection Review | Detection and Response Teams | Anomaly detection accuracy and response effectiveness | Weekly | Detection Meeting | EO Project Manager | Meeting invitation | 30 minutes | "Detection accuracy, false positive rates, response effectiveness" | Detection Team and Network Operations | Operational | Detection targets met and response effectiveness validated | Active | [DATE] | Include anomaly examples and response time analysis