## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Network Analytics
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Description | Acceptance Criteria | Source | Owner | Status | Dependencies | Test Method | Compliance | Notes | Estimated Effort
REQ-001 | Functional | Network Monitoring | Critical | System must collect network telemetry from multi-vendor devices | Comprehensive data collection from 95%+ network infrastructure | Business Stakeholder | Network Engineer | Draft | Network device access | Data collection testing |  | Core network visibility requirement | 40 hours
REQ-002 | Functional | AI Analytics | Critical | System must provide AI-powered network anomaly detection | Anomaly detection with 95%+ accuracy and <5% false positive rate | Business Stakeholder | Data Scientist | Draft | REQ-001 | AI model testing |  | Intelligent network monitoring | 32 hours
REQ-003 | Functional | Predictive Analytics | High | System must predict network failures and performance issues | Failure prediction 72+ hours in advance with 85%+ accuracy | Business Stakeholder | AI Engineer | Draft | Historical data | Predictive testing |  | Proactive network management | 80 hours
REQ-004 | Functional | Real-time Analytics | Critical | Provide real-time network analytics and insights | Real-time processing with <5 minute detection latency | Network Team | Analytics Engineer | Draft | REQ-001 | Performance testing |  | Immediate issue detection | 60 hours
REQ-005 | Functional | Root Cause Analysis | Critical | System must provide automated root cause analysis for network issues | Accurate root cause identification for 80%+ of network events | Network Operations | AI Specialist | Draft | REQ-002 | Analysis testing |  | Accelerated troubleshooting | 100 hours
REQ-006 | Functional | Dashboard Visualization | High | Provide comprehensive network analytics dashboards | Intuitive dashboards with customizable views and drill-down | End Users | UI Developer | Draft | REQ-004 | Usability testing | Accessibility | Operational visibility | 70 hours
REQ-007 | Functional | Automated Remediation | Critical | Implement automated response to common network issues | Automated resolution of 90%+ routine network problems | Network Operations | Automation Engineer | Draft | Integration with tools | Automation testing |  | Operational efficiency | 40 hours
REQ-008 | Functional | Alert Management | Critical | Provide intelligent alerting with severity classification | Context-aware alerts with 95%+ relevance rating | Network Team | Alert Engineer | Draft | REQ-002 | Alert testing |  | Reduced alert fatigue | 32 hours
REQ-009 | Functional | Historical Analysis | High | Support historical network data analysis and trending | Access to 12+ months historical data with trend analysis | Business User | Data Engineer | Draft | Data retention | Historical testing |  | Long-term insights and planning | 50 hours
REQ-010 | Functional | Multi-Vendor Support | High | Support telemetry collection from diverse network vendors | Unified data collection from Cisco Juniper Arista HP vendors | Network Team | Integration Specialist | Draft | Vendor protocols | Integration testing |  | Comprehensive network coverage | 45 hours
REQ-011 | Non-Functional | Performance | Critical | AI analytics platform must meet response time requirements | Dashboard load time <3 seconds AI analysis <5 minutes | Business Stakeholder | Performance Engineer | Draft | Platform deployment | Performance testing | SLA | User experience critical
REQ-012 | Non-Functional | Accuracy | Critical | AI models must maintain high accuracy for network analytics | Anomaly detection accuracy >95% prediction accuracy >85% | Business Stakeholder | Data Science Team | Draft | Model training | Accuracy testing | Quality | Operational reliability critical
REQ-013 | Non-Functional | Scalability | High | System must scale to handle growing network infrastructure | Support 10000+ network devices with linear performance scaling | Technical Team | Platform Architect | Draft | Architecture design | Scalability testing |  | Future growth accommodation
REQ-014 | Non-Functional | Availability | High | AI analytics platform must maintain high availability | 99.5% uptime with redundancy and failover capabilities | Technical Team | Infrastructure Engineer | Draft | Redundant architecture | Uptime monitoring | SLA | Business continuity requirement
REQ-015 | Security | Data Protection | Critical | Ensure network data is protected throughout analytics pipeline | End-to-end encryption with secure data handling practices | Security Team | Security Architect | Draft | Security controls | Security testing | Compliance | Network data sensitivity | 24 hours
REQ-016 | Security | Access Control | Critical | Implement role-based access control for analytics platform | Granular RBAC with principle of least privilege | Security Team | Access Control Specialist | Draft | Identity system | Access testing | Security | Secure platform access | 16 hours
REQ-017 | Security | Audit Logging | Critical | Maintain comprehensive audit logs for all platform activities | Complete audit trail for compliance and security monitoring | Security Team | Audit Engineer | Draft | Logging infrastructure | Audit testing | SOC2 | Regulatory compliance | 40 hours
REQ-018 | Security | Network Segmentation | High | Implement network segmentation for analytics platform | Isolated network segment with controlled access | Security Team | Network Security Engineer | Draft | Network design | Segmentation testing | Security | Platform security isolation | 32 hours
REQ-019 | Security | API Security | High | Secure all API endpoints with authentication and authorization | OAuth/JWT authentication with rate limiting | Security Team | API Security Engineer | Draft | API development | Security testing | Security | API security protection | 24 hours
REQ-020 | Security | Data Retention | High | Implement secure data retention and disposal policies | Configurable retention with secure data deletion | Compliance Team | Data Protection Officer | Draft | Data lifecycle | Retention testing | GDPR | Data privacy compliance | 32 hours
REQ-021 | Integration | ITSM Integration | High | Integrate with existing IT service management systems | Bi-directional integration with ServiceNow/Remedy | IT Team | Integration Engineer | Draft | ITSM API access | Integration testing |  | Automated incident management | 60 hours
REQ-022 | Integration | Monitoring Tools | Medium | Integrate with existing network monitoring solutions | Data sharing with Nagios SolarWinds PRTG systems | IT Team | Tools Integration Specialist | Draft | Monitoring APIs | Tool testing |  | Unified monitoring ecosystem | 50 hours
REQ-023 | Integration | Automation Platforms | Medium | Integrate with network automation and orchestration tools | Integration with Ansible Terraform network automation | IT Team | Automation Specialist | Draft | Automation APIs | Automation testing |  | Automated response capability | 30 hours
REQ-024 | Usability | User Experience | High | Provide intuitive user experience for network operations teams | User-friendly interface requiring minimal training | End User | UX Designer | Draft | UI development | Usability testing | Accessibility | User adoption critical | 80 hours
REQ-025 | Usability | Customization | High | Support dashboard and alert customization for different user roles | Role-based customizable views and personalization | End User | Frontend Developer | Draft | Dashboard framework | Customization testing |  | User productivity requirement | 90 hours
REQ-026 | Usability | Mobile Access | Medium | Provide mobile access to critical network analytics | Mobile-responsive design with core functionality | Mobile Users | Mobile Developer | Draft | Responsive design | Mobile testing | Accessibility | On-the-go network management | 60 hours
REQ-027 | AI/ML | Model Management | High | Support AI model versioning lifecycle management and updates | Model deployment pipeline with A/B testing capability | Data Science Team | MLOps Engineer | Draft | ML platform | Model testing |  | Continuous model improvement | 70 hours
REQ-028 | AI/ML | Model Monitoring | High | Monitor AI model performance and detect model drift | Automated model performance monitoring with drift detection | Data Science Team | ML Engineer | Draft | Monitoring infrastructure | Model monitoring |  | Model reliability assurance | 50 hours
REQ-029 | AI/ML | Explainable AI | Medium | Provide explanations for AI-generated insights and decisions | Human-readable explanations for AI recommendations | Business User | AI Explainability Engineer | Draft | Model development | Explainability testing |  | AI transparency and trust | 100 hours
REQ-030 | AI/ML | Continuous Learning | High | Support continuous model improvement with new network data | Automated retraining pipeline with performance validation | Data Science Team | ML Pipeline Engineer | Draft | ML infrastructure | Learning testing |  | Adaptive AI capability | 40 hours
REQ-031 | Operational | Backup | Critical | Implement automated backup for AI models and configuration data | Daily backup with point-in-time recovery capability | Operations Team | Backup Engineer | Draft | Backup infrastructure | Backup testing | Data protection | AI asset protection | 40 hours
REQ-032 | Operational | Disaster Recovery | Critical | Implement disaster recovery for AI analytics platform | RTO 4 hours RPO 1 hour for analytics capabilities | Operations Team | DR Engineer | Draft | DR infrastructure | DR testing | Business continuity | Platform resilience | 32 hours
REQ-033 | Operational | Monitoring | High | Implement comprehensive platform monitoring and alerting | End-to-end platform monitoring with proactive alerting | Operations Team | Platform Monitoring Engineer | Draft | Monitoring tools | Monitoring testing |  | Platform health visibility | 60 hours
REQ-034 | Compliance | Data Privacy | Critical | Comply with data privacy regulations for network data | GDPR compliance with data subject rights implementation | Compliance Team | Privacy Officer | Draft | Privacy controls | Privacy audit | GDPR | Regulatory compliance | 50 hours
REQ-035 | Compliance | Industry Standards | High | Ensure platform complies with relevant industry standards | SOC 2 ISO 27001 compliance for analytics platform | Compliance Team | Compliance Engineer | Draft | Compliance framework | Compliance audit | Multiple | Industry compliance requirement | 40 hours
REQ-036 | Infrastructure | Compute Resources | Critical | Sufficient compute resources for AI model training and inference | High-performance compute with GPU acceleration for ML workloads | Infrastructure Team | Compute Engineer | Draft | Resource planning | Performance testing |  | AI processing capability | 8 hours
REQ-037 | Infrastructure | Storage Resources | Critical | High-performance storage for network data and model artifacts | SSD storage with IOPS suitable for real-time analytics | Infrastructure Team | Storage Engineer | Draft | Data volume estimates | Storage testing |  | Data processing performance | 4 hours
REQ-038 | Infrastructure | Network Connectivity | Critical | High-bandwidth network connectivity for data collection | Sufficient bandwidth for network telemetry collection | Infrastructure Team | Network Engineer | Draft | Bandwidth analysis | Connectivity testing |  | Data collection capability | 4 hours
REQ-039 | Infrastructure | Platform Software | High | AI analytics platform software with appropriate licensing | Cisco AI platform with required feature licensing | Infrastructure Team | License Manager | Draft | License procurement | Software testing |  | Platform functionality enablement | 16 hours
REQ-040 | Infrastructure | Database Systems | Critical | High-performance database for network data storage | Time-series database optimized for network telemetry | Infrastructure Team | Database Engineer | Draft | Database design | Database testing |  | Data storage and retrieval performance | 8 hours
REQ-041 | Infrastructure | Monitoring Infrastructure | High | Infrastructure monitoring for AI analytics platform | Comprehensive infrastructure monitoring with alerting | Infrastructure Team | Infrastructure Monitoring Engineer | Draft | Monitoring tools | Infrastructure monitoring |  | Platform health monitoring | 12 hours
REQ-042 | Skills | Technical Team | Critical | AI/ML engineer with 5+ years network analytics experience | Proven AI model development for network operations | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Essential for AI development
REQ-043 | Skills | Technical Team | Critical | Network engineer with 5+ years multi-vendor experience | Deep network protocols and device expertise | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Critical for network data understanding
REQ-044 | Skills | Technical Team | High | Data scientist with 3+ years time-series analytics experience | Proven time-series analysis and anomaly detection | HR Team | Project Manager | Draft | Team recruitment | Skill assessment |  | Essential for network data analysis
REQ-045 | Skills | Operations Team | High | Network operations engineers with AI platform experience | Experience with AI-driven network monitoring tools | HR Team | Technical Lead | Draft | Team recruitment | Skill assessment |  | Operational readiness requirement
REQ-046 | Budget | Project Costs | Critical | Platform licensing budget approved for Cisco AI analytics | Annual licensing costs $150000-$300000 approved | Finance Team | Project Sponsor | Draft | Cost estimates | Budget approval | Financial | Based on device count and features
REQ-047 | Budget | Project Costs | Critical | Professional services budget approved for AI implementation | Implementation costs $300000-$600000 approved | Finance Team | Project Sponsor | Draft | SOW approval | Budget approval | Financial | Includes training and customization
REQ-048 | Security | Threat Detection | Critical | AI-powered threat detection for network security | Network security anomaly detection with threat intelligence | Security Team | Threat Detection Engineer | Draft | Security integration | Threat testing | Security | Network security enhancement | 24 hours
REQ-049 | Security | Incident Response | High | Automated incident response integration with security tools | Security incident automation with SOAR platforms | Security Team | Incident Response Engineer | Draft | SOAR integration | Incident testing | Security | Security operation efficiency | 16 hours
REQ-050 | Compliance | Audit Requirements | High | Support for compliance auditing and reporting | Automated compliance reporting for network operations | Compliance Team | Audit Specialist | Draft | Compliance framework | Audit testing | Multiple | Regulatory audit support | 20 hours
REQ-051 | Testing | AI Model Testing | High | Comprehensive testing framework for AI model validation | Automated testing for model accuracy and performance | QA Team | AI Test Engineer | Draft | Testing framework | Model testing | Quality | AI quality assurance | 16 hours
REQ-052 | Testing | Integration Testing | High | End-to-end integration testing with network infrastructure | Complete workflow testing with real network data | QA Team | Integration Test Engineer | Draft | Integration development | Integration testing |  | System validation | 24 hours
REQ-053 | Operations | Support Procedures | High | Operational support procedures for AI analytics platform | 24/7 support capability with escalation procedures | Operations Team | Support Manager | Draft | Support framework | Support testing | SLA | Platform support capability | 32 hours
REQ-054 | Training | User Training | Medium | Comprehensive training for network operations teams | Training on AI insights interpretation and response | Training Team | Training Manager | Draft | Platform deployment | Training evaluation |  | User competency development
REQ-055 | Training | Technical Training | High | Technical training for AI platform administrators | Advanced training on platform administration and tuning | Training Team | Technical Trainer | Draft | Platform deployment | Training validation |  | Technical operational readiness