## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Hybrid Infrastructure
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Status Report | Executive Sponsors | High-level infrastructure project status and key decisions | Weekly | Email Report | Project Manager | Email distribution list |  | Infrastructure health, milestones, risks, decisions needed | Executive Sponsor and Infrastructure Director | Executive | Report delivered on time and decisions made | Active | [DATE] | Executive summary format with infrastructure dashboard
COMM-002 | Steering Committee | Infrastructure Steering Committee | Strategic direction and infrastructure investment decisions | Bi-weekly | In-Person Meeting | Project Manager | Meeting invitation | 60 minutes | Strategic decisions, major infrastructure risks, budget, timeline | Executive Sponsor and IT Leadership | Strategic | Meeting attendance >80% and decisions documented | Active | [DATE] | Decision-making authority for infrastructure scope and budget
COMM-003 | Infrastructure Team Standup | Core Infrastructure Team | Daily coordination and technical impediment removal | Daily | Virtual Meeting | Infrastructure Lead | Video conference | 15 minutes | Yesterday's progress, today's plan, technical blockers | Infrastructure Team and Network Engineers | Operational | Daily attendance >90% and blockers resolved | Active | [DATE] | Focus on infrastructure configuration and integration issues
COMM-004 | Architecture Review | Infrastructure Stakeholders | Cisco architecture design review and approval | Weekly | Technical Meeting | Solution Architect | Meeting invitation | 90 minutes | HyperFlex decisions, ACI configuration, network design changes | Infrastructure Architect and Cisco Specialists | Technical | Design decisions made and documented | Active | [DATE] | Include Cisco architectural decision records and best practices
COMM-005 | Infrastructure Risk Review | Infrastructure Risk Team | Infrastructure risk assessment and mitigation planning | Bi-weekly | Risk Meeting | Infrastructure Manager | Meeting invitation | 45 minutes | New infrastructure risks, mitigation status, escalation | Project Manager and Infrastructure Committee | Management | Risk register updated and infrastructure mitigations on track | Active | [DATE] | Focus on high and critical infrastructure risks
COMM-006 | Network Configuration Review | Network Engineering Team | Network design validation and configuration approval | Weekly | Technical Session | Network Architect | Workshop invitation | 120 minutes | ACI fabric review, routing design, security policies | Network Engineers and Security Team | Technical | Network configuration approved and security validated | Active | [DATE] | Include hands-on ACI configuration and validation
COMM-007 | HyperFlex Performance Review | Infrastructure Operations | HyperFlex cluster performance and optimization | Bi-weekly | Performance Meeting | Infrastructure Operations Lead | Video conference | 60 minutes | Cluster health, performance metrics, optimization opportunities | Infrastructure Team and Operations Manager | Technical | Performance targets achieved and optimization implemented | Active | [DATE] | Include live HyperFlex monitoring and performance analysis
COMM-008 | Cisco Vendor Coordination | Cisco Professional Services | Cisco implementation progress and technical coordination | Weekly | Vendor Call | Integration Specialist | Conference call | 45 minutes | Cisco deliverables, technical progress, integration issues | Cisco Representatives and Technical Lead | Vendor | Cisco commitments met and technical issues resolved | Active | [DATE] | Track Cisco SLAs and technical deliverables
COMM-009 | Infrastructure Quality Review | Infrastructure QA Team | Infrastructure testing and validation progress | Weekly | QA Meeting | Infrastructure QA Lead | Meeting invitation | 45 minutes | Test execution status, infrastructure validation, readiness gates | QA Team and Infrastructure Lead | Quality | Quality gates met and infrastructure tests within tolerance | Active | [DATE] | Include infrastructure test coverage and validation metrics
COMM-010 | Change Control | Infrastructure Change Board | Infrastructure change request review and approval | As Needed | Change Meeting | Change Manager | Meeting invitation | 60 minutes | Infrastructure changes, impact assessment, approval decisions | Infrastructure Change Board Members | Governance | Infrastructure change requests processed within SLA | Active | [DATE] | Follow formal infrastructure change management process
COMM-011 | Migration Planning | Migration Team | Infrastructure migration progress and readiness | Bi-weekly | Migration Call | Migration Manager | Conference call | 45 minutes | Migration planning, cutover schedule, rollback procedures | Migration Team and Business Managers | Operational | Migration plan ready and business impact minimized | Active | [DATE] | Include migration timeline and business continuity planning
COMM-012 | Security and Compliance Review | Infrastructure Security Team | Infrastructure security compliance and risk assessment | Monthly | Security Meeting | Security Architect | Meeting invitation | 60 minutes | Security assessments, compliance status, vulnerabilities | Security Team and Compliance Officer | Security | Infrastructure security requirements met and risks mitigated | Active | [DATE] | Include infrastructure security testing and compliance audits
COMM-013 | Data Center Operations | Infrastructure Operations Team | Data center readiness and operational coordination | Weekly | Operations Call | Data Center Manager | Conference call | 30 minutes | Facility status, power and cooling, rack space planning | Infrastructure Team and Facilities Manager | Operational | Data center ready and infrastructure requirements met | Active | [DATE] | Include facility capacity planning and environmental monitoring
COMM-014 | Business Impact Assessment | Business Stakeholders | Business readiness for infrastructure changes | Bi-weekly | Business Meeting | Change Manager | Meeting invitation | 45 minutes | Business impact, downtime windows, user communication | Business Managers and End Users | Business | Business readiness criteria met and users prepared for changes | Active | [DATE] | Include user communication and business continuity metrics
COMM-015 | Cutover Preparation | Cutover Team | Infrastructure cutover planning and readiness validation | Daily (1 week before) | Cutover Meeting | Project Manager | Video conference | 30 minutes | Cutover checklist, readiness validation, rollback planning | All Team Leads and Operations Manager | Critical | Cutover criteria met and rollback plans ready | Planned | [DATE] | Intensive coordination before infrastructure cutover
COMM-016 | Post-Implementation | Infrastructure Team | Post-implementation review and optimization opportunities | Monthly (3 months) | Review Meeting | Project Manager | Meeting invitation | 90 minutes | Infrastructure performance, lessons learned, optimization opportunities | Core Infrastructure Team and Business Stakeholders | Review | Lessons captured and infrastructure improvement actions identified | Planned | [DATE] | Include infrastructure benefits realization and performance optimization
COMM-017 | Infrastructure Incident Escalation | Incident Response Team | Critical infrastructure issue communication and resolution | As Needed | Emergency Call | Incident Owner | Emergency notification | Variable | Incident description, infrastructure impact, resolution actions | Infrastructure Response Team and Management | Emergency | Infrastructure incident resolved within SLA and communication timely | Active | [DATE] | Follow infrastructure incident management procedures
COMM-018 | Infrastructure Stakeholder Briefing | All Infrastructure Stakeholders | General infrastructure project updates and milestone communication | Monthly | All-Hands Meeting | Project Manager | Town hall meeting | 45 minutes | Infrastructure progress, upcoming milestones, team recognition | All Infrastructure Project Stakeholders | Informational | Infrastructure stakeholder engagement and awareness maintained | Active | [DATE] | Include infrastructure project achievements and team recognition
COMM-019 | Technical Deep Dive | Infrastructure Technical Teams | Infrastructure technical knowledge sharing and problem solving | As Needed | Technical Session | Technical Lead | Meeting invitation | 90 minutes | Technical challenges, HyperFlex/ACI configuration, knowledge transfer | Infrastructure Technical Team Members | Technical | Infrastructure technical issues resolved and knowledge shared | Active | [DATE] | Include Cisco architectural decisions and infrastructure best practices
COMM-020 | Operations Handover | Infrastructure Operations Team | Infrastructure operations transition and knowledge transfer | Weekly (final month) | Operations Meeting | Infrastructure Manager | Meeting invitation | 60 minutes | Operations procedures, monitoring setup, support escalation | Operations Team and Infrastructure Team | Operational | Operations team ready for infrastructure support and management | Planned | [DATE] | Comprehensive infrastructure operations documentation and training