## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Secure Access
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Stakeholder | Role | Communication Type | Frequency | Method | Content | Timing | Owner | Status\n\"Executive Sponsor\" | \"C-Level Executive\" | \"Strategic Update\" | \"Monthly\" | \"Executive Brief\" | \"High-level progress | ROI metrics | risk status\" | \"First Monday\" | \"Project Manager\" | \"Active\"\n\"CISO\" | \"Security Leadership\" | \"Security Status\" | \"Weekly\" | \"Security Report\" | \"Threat landscape | security posture | incidents\" | \"Friday EOD\" | \"Security Architect\" | \"Active\"\n\"CTO\" | \"Technology Leadership\" | \"Technical Progress\" | \"Bi-weekly\" | \"Technical Review\" | \"Architecture updates | performance metrics | integration status\" | \"Every other Wednesday\" | \"Technical Lead\" | \"Active\"\n\"Project Steering Committee\" | \"Decision Makers\" | \"Governance Update\" | \"Monthly\".1 | \"Steering Meeting\" | \"Milestone status | budget | resource allocation | decisions\" | \"Third Thursday\" | \"Project Manager\".1 | \"Active\"\n\"IT Security Team\" | \"Implementation Team\" | \"Daily Standup\" | \"Daily\" | \"Team Meeting\" | \"Progress updates | blockers | daily priorities\" | \"9:00 AM\" | \"Security Lead\" | \"Active\"\n\"Network Operations\" | \"Operations Team\" | \"Operational Impact\" | \"Weekly\".1 | \"Operations Brief\" | \"Network changes | performance impact | maintenance windows\" | \"Tuesday 2 PM\" | \"Network Engineer\" | \"Active\"\n\"Helpdesk Team\" | \"Support Team\" | \"Support Readiness\" | \"Bi-weekly\".1 | \"Training Session\" | \"New procedures | troubleshooting guides | escalation paths\" | \"Thursday 10 AM\" | \"Support Manager\" | \"Active\"\n\"End Users\" | \"Business Users\" | \"User Communication\" | \"Monthly\".2 | \"Newsletter\" | \"Feature updates | security awareness | training opportunities\" | \"First Friday\" | \"Change Manager\" | \"Active\"\n\"IT Administrators\" | \"Technical Users\" | \"Technical Update\" | \"Weekly\".2 | \"Technical Brief\" | \"Configuration changes | policy updates | best practices\" | \"Wednesday 3 PM\" | \"Platform Engineer\" | \"Active\"\n\"Compliance Team\" | \"Compliance Officers\" | \"Compliance Status\" | \"Monthly\".3 | \"Compliance Report\" | \"Regulatory status | audit findings | remediation plans\" | \"Last Tuesday\" | \"Compliance Lead\" | \"Active\"\n\"Risk Management\" | \"Risk Officers\" | \"Risk Assessment\" | \"Quarterly\" | \"Risk Review\" | \"Security risk posture | threat assessment | mitigation strategies\" | \"Quarter End\" | \"Security Architect\".1 | \"Active\"\n\"Business Unit Leaders\" | \"Department Heads\" | \"Business Impact\" | \"Monthly\".4 | \"Business Brief\" | \"Productivity metrics | user experience | process changes\" | \"Second Tuesday\" | \"Business Analyst\" | \"Active\"\n\"Procurement Team\" | \"Vendor Management\" | \"Vendor Coordination\" | \"Bi-weekly\".2 | \"Vendor Meeting\" | \"Contract status | support issues | renewal planning\" | \"Every other Friday\" | \"Procurement Lead\" | \"Active\"\n\"Legal Team\" | \"Legal Counsel\" | \"Legal Review\" | \"As Needed\" | \"Legal Brief\" | \"Contract reviews | compliance requirements | liability assessment\" | \"On Request\" | \"Legal Counsel\".1 | \"Active\"\n\"HR Leadership\" | \"Human Resources\" | \"Training Coordination\" | \"Monthly\".5 | \"HR Meeting\" | \"Training schedules | user adoption metrics | support needs\" | \"Third Monday\" | \"Training Manager\" | \"Active\"\n\"External Auditors\" | \"Audit Firm\" | \"Audit Updates\" | \"Quarterly\".1 | \"Audit Report\" | \"Compliance status | control effectiveness | findings\" | \"Quarter End\".1 | \"Compliance Lead\".1 | \"Active\"\n\"Board of Directors\" | \"Board Members\" | \"Board Report\" | \"Quarterly\".2 | \"Board Presentation\" | \"Strategic security posture | investment ROI | risk mitigation\" | \"Board Meeting\" | \"CISO\" | \"Active\"\n\"Cisco TAC Support\" | \"Vendor Support\" | \"Technical Support\" | \"As Needed\".1 | \"Support Case\" | \"Technical issues | escalations | platform updates\" | \"On Request\".1 | \"Technical Lead\".1 | \"Active\"\n\"Security Consultant\" | \"External Expert\" | \"Expert Review\" | \"Monthly\".6 | \"Consultation Call\" | \"Security assessment | best practices | industry trends\" | \"Last Friday\" | \"Security Architect\".2 | \"Active\"\n\"Change Advisory Board\" | \"Change Governance\" | \"Change Approval\" | \"Weekly\".3 | \"CAB Meeting\" | \"Change requests | impact assessment | approval status\" | \"Thursday 2 PM\" | \"Change Manager\".1 | \"Active\"\n\"Incident Response Team\" | \"Emergency Response\" | \"Incident Communication\" | \"As Needed\".2 | \"Emergency Alert\" | \"Security incidents | response actions | impact assessment\" | \"Immediate\" | \"Incident Commander\" | \"Active\"\n\"Data Protection Officer\" | \"Privacy Officer\" | \"Privacy Impact\" | \"Monthly\".7 | \"Privacy Review\" | \"Data protection compliance | privacy risks | GDPR status\" | \"Second Friday\" | \"Privacy Officer\".1 | \"Active\"\n\"Business Continuity Team\" | \"Continuity Planning\" | \"BC Impact Assessment\" | \"Quarterly\".3 | \"BC Review\" | \"Business continuity testing | recovery procedures | impact analysis\" | \"Quarter Start\" | \"BC Manager\" | \"Active\"\n\"Training Coordinators\" | \"Learning Team\" | \"Training Progress\" | \"Bi-weekly\".3 | \"Training Report\" | \"Training completion rates | effectiveness metrics | feedback\" | \"Every other Monday\" | \"Training Manager\".1 | \"Active\"\n\"Communication Team\" | \"Internal Comms\" | \"Internal Communications\" | \"Weekly\".4 | \"Comms Brief\" | \"Message coordination | stakeholder feedback | communication effectiveness\" | \"Monday 11 AM\" | \"Communications Lead\" | \"Active\"\n\"Quality Assurance\" | \"QA Team\" | \"Testing Updates\" | \"Daily\".1 | \"QA Standup\" | \"Testing progress | defect status | quality metrics\" | \"10:00 AM\" | \"QA Lead\" | \"Active\"\n\"Performance Team\" | \"Performance Engineers\" | \"Performance Metrics\" | \"Weekly\".5 | \"Performance Report\" | \"System performance | capacity planning | optimization opportunities\" | \"Friday 4 PM\" | \"Performance Lead\" | \"Active\"\n\"Integration Team\" | \"Integration Engineers\" | \"Integration Status\" | \"Bi-weekly\".4 | \"Integration Review\" | \"API integrations | data flows | system connectivity\" | \"Every other Tuesday\" | \"Integration Lead\" | \"Active\"\n\"User Experience Team\" | \"UX Designers\" | \"User Feedback\" | \"Weekly\".6 | \"UX Review\" | \"User experience metrics | feedback analysis | improvement recommendations\" | \"Thursday 11 AM\" | \"UX Lead\" | \"Active\"\n\"Architecture Review Board\" | \"Enterprise Architects\" | \"Architecture Approval\" | \"Monthly\".8 | \"ARB Meeting\" | \"Architecture changes | design reviews | compliance validation\" | \"Fourth Wednesday\" | \"Enterprise Architect\" | \"Active\""}]