## Cover
Project Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Secure Access
Customer Name: | Data table for project plan
Version: | 1.0

## Project Plan
Phase | Task | Description | Start Date | End Date | Duration | Dependencies | Assigned To | Status | Deliverables | Risks | Mitigation\n\"Phase 1: Foundation\" | \"P1.1 - Project Initiation\" | \"Project charter | team assembly | and stakeholder alignment\" | \"2025-01-02\" | \"2025-01-05\" | \"4 days\" | \"None\" | \"Project Manager\" | \"Completed\" | \"Project Charter | Team Charter | Communication Plan\" | \"Stakeholder misalignment\" | \"Regular stakeholder meetings\"\n\"Phase 1: Foundation\" | \"P1.2 - Security Assessment\" | \"Comprehensive security posture and risk assessment\" | \"2025-01-06\" | \"2025-01-12\" | \"7 days\" | \"P1.1\" | \"Security Architect\" | \"Completed\".1 | \"Security Assessment Report | Risk Matrix\" | \"Incomplete assessment\" | \"Third-party validation\"\n\"Phase 1: Foundation\" | \"P1.3 - Network Architecture Review\" | \"Review current network architecture and design future state\" | \"2025-01-08\" | \"2025-01-15\" | \"8 days\" | \"P1.2\" | \"Network Engineer\" | \"Completed\".2 | \"Network Architecture Document | Migration Plan\" | \"Architecture complexity\" | \"Phased implementation approach\"\n\"Phase 1: Foundation\" | \"P1.4 - Identity Integration Design\" | \"Design Active Directory and identity provider integration\" | \"2025-01-13\" | \"2025-01-19\" | \"7 days\".1 | \"P1.3\" | \"Identity Engineer\" | \"Completed\".3 | \"Identity Integration Design | Authentication Flows\" | \"Integration complexity\" | \"Proof of concept validation\"\n\"Phase 1: Foundation\" | \"P1.5 - Policy Framework Development\" | \"Develop zero-trust access policies and governance framework\" | \"2025-01-16\" | \"2025-01-26\" | \"11 days\" | \"P1.4\" | \"Security Architect\".1 | \"Completed\".4 | \"Policy Framework | Governance Model\" | \"Policy conflicts\" | \"Stakeholder review and approval\"\n\"Phase 2: Core Implementation\" | \"P2.1 - Infrastructure Deployment\" | \"Deploy core Cisco security infrastructure components\" | \"2025-01-27\" | \"2025-02-07\" | \"12 days\" | \"P1.5\" | \"Platform Engineer\" | \"Completed\".5 | \"Infrastructure Deployment | Configuration Baseline\" | \"Hardware delivery delays\" | \"Alternative deployment options\"\n\"Phase 2: Core Implementation\" | \"P2.2 - Duo MFA Implementation\" | \"Deploy and configure Cisco Duo multi-factor authentication\" | \"2025-02-03\" | \"2025-02-14\" | \"12 days\".1 | \"P2.1\" | \"Security Engineer\" | \"Completed\".6 | \"MFA Platform | User Enrollment Process\" | \"User adoption resistance\" | \"Comprehensive training program\"\n\"Phase 2: Core Implementation\" | \"P2.3 - ISE Network Access Control\" | \"Implement Cisco ISE for network access control and policies\" | \"2025-02-10\" | \"2025-02-21\" | \"12 days\".2 | \"P2.2\" | \"Network Engineer\".1 | \"Completed\".7 | \"NAC Policies | Device Profiling\" | \"Network disruption\" | \"Phased rollout with testing\"\n\"Phase 2: Core Implementation\" | \"P2.4 - Umbrella DNS Security\" | \"Deploy Cisco Umbrella for DNS-layer security protection\" | \"2025-02-17\" | \"2025-02-28\" | \"12 days\".3 | \"P2.3\" | \"Security Engineer\".1 | \"Completed\".8 | \"DNS Security Policies | Threat Intelligence\" | \"DNS resolution issues\" | \"Gradual DNS transition\"\n\"Phase 2: Core Implementation\" | \"P2.5 - AnyConnect Deployment\" | \"Deploy Cisco AnyConnect for secure endpoint connectivity\" | \"2025-02-24\" | \"2025-03-07\" | \"12 days\".4 | \"P2.4\" | \"Platform Engineer\".1 | \"Completed\".9 | \"VPN Replacement | Endpoint Posture Assessment\" | \"Endpoint compatibility\" | \"Compatibility testing program\"\n\"Phase 3: Advanced Features\" | \"P3.1 - Application Integration\" | \"Integrate SSO with enterprise applications using SAML/OIDC\" | \"2025-03-03\" | \"2025-03-14\" | \"12 days\".5 | \"P2.5\" | \"Integration Engineer\" | \"Completed\".10 | \"Application SSO | API Integrations\" | \"Application compatibility\" | \"Application-specific testing\"\n\"Phase 3: Advanced Features\" | \"P3.2 - Adaptive Authentication\" | \"Implement risk-based and contextual authentication policies\" | \"2025-03-10\" | \"2025-03-21\" | \"12 days\".6 | \"P3.1\" | \"Security Architect\".2 | \"Completed\".11 | \"Adaptive Policies | Risk Assessment Engine\" | \"Policy accuracy\" | \"Extensive testing and tuning\"\n\"Phase 3: Advanced Features\" | \"P3.3 - Endpoint Security\" | \"Deploy advanced endpoint security and posture assessment\" | \"2025-03-17\" | \"2025-03-28\" | \"12 days\".7 | \"P3.2\" | \"Security Engineer\".2 | \"Completed\".12 | \"Endpoint Policies | Compliance Monitoring\" | \"Endpoint performance impact\" | \"Performance optimization\"\n\"Phase 3: Advanced Features\" | \"P3.4 - Cloud Security Integration\" | \"Integrate cloud application security and data protection\" | \"2025-03-24\" | \"2025-04-04\" | \"12 days\".8 | \"P3.3\" | \"Cloud Engineer\" | \"Completed\".13 | \"Cloud Security Policies | Data Protection\" | \"Cloud platform compatibility\" | \"Multi-cloud testing approach\"\n\"Phase 3: Advanced Features\" | \"P3.5 - Threat Intelligence\" | \"Implement advanced threat detection and response capabilities\" | \"2025-03-31\" | \"2025-04-11\" | \"12 days\".9 | \"P3.4\" | \"Threat Analyst\" | \"Completed\".14 | \"Threat Intelligence Feeds | Response Automation\" | \"False positive rates\" | \"Machine learning tuning\"\n\"Phase 4: Testing and Validation\" | \"P4.1 - Security Testing\" | \"Comprehensive penetration testing and vulnerability assessment\" | \"2025-04-07\" | \"2025-04-18\" | \"12 days\".10 | \"P3.5\" | \"Security Tester\" | \"Completed\".15 | \"Security Test Report | Vulnerability Assessment\" | \"Critical vulnerabilities\" | \"Immediate remediation process\"\n\"Phase 4: Testing and Validation\" | \"P4.2 - Performance Testing\" | \"Load testing and performance optimization validation\" | \"2025-04-14\" | \"2025-04-25\" | \"12 days\".11 | \"P4.1\" | \"Performance Engineer\" | \"Completed\".16 | \"Performance Test Results | Optimization Plan\" | \"Performance degradation\" | \"Infrastructure scaling options\"\n\"Phase 4: Testing and Validation\" | \"P4.3 - Integration Testing\" | \"End-to-end workflow and system integration validation\" | \"2025-04-21\" | \"2025-05-02\" | \"12 days\".12 | \"P4.2\" | \"QA Engineer\" | \"Completed\".17 | \"Integration Test Report | Workflow Validation\" | \"Integration failures\" | \"Rollback procedures\"\n\"Phase 4: Testing and Validation\" | \"P4.4 - User Acceptance Testing\" | \"Business stakeholder testing and approval process\" | \"2025-04-28\" | \"2025-05-09\" | \"12 days\".13 | \"P4.3\" | \"Business Analyst\" | \"Completed\".18 | \"UAT Results | Business Approval\" | \"User acceptance issues\" | \"User feedback integration\"\n\"Phase 4: Testing and Validation\" | \"P4.5 - Compliance Validation\" | \"Regulatory compliance testing and certification process\" | \"2025-05-05\" | \"2025-05-16\" | \"12 days\".14 | \"P4.4\" | \"Compliance Officer\" | \"Completed\".19 | \"Compliance Certification | Audit Reports\" | \"Compliance gaps\" | \"Immediate remediation\"\n\"Phase 5: Go-Live\" | \"P5.1 - Production Preparation\" | \"Final production environment preparation and validation\" | \"2025-05-12\" | \"2025-05-23\" | \"12 days\".15 | \"P4.5\" | \"Platform Engineer\".2 | \"Completed\".20 | \"Production Environment | Cutover Plan\" | \"Production issues\" | \"Comprehensive rollback plan\"\n\"Phase 5: Go-Live\" | \"P5.2 - Phased Rollout\" | \"Gradual production deployment with monitoring and validation\" | \"2025-05-19\" | \"2025-05-30\" | \"12 days\".16 | \"P5.1\" | \"Project Manager\".1 | \"Completed\".21 | \"Production Deployment | Monitoring Dashboard\" | \"Rollout issues\" | \"Phase-gate approvals\"\n\"Phase 5: Go-Live\" | \"P5.3 - User Training Delivery\" | \"Comprehensive security awareness and platform training\" | \"2025-05-26\" | \"2025-06-06\" | \"12 days\".17 | \"P5.2\" | \"Training Manager\" | \"Completed\".22 | \"Training Materials | Competency Assessments\" | \"Training effectiveness\" | \"Multiple delivery methods\"\n\"Phase 5: Go-Live\" | \"P5.4 - Performance Optimization\" | \"Policy optimization and performance tuning based on usage\" | \"2025-06-02\" | \"2025-06-13\" | \"12 days\".18 | \"P5.3\" | \"Performance Engineer\".1 | \"Completed\".23 | \"Optimized Policies | Performance Metrics\" | \"Performance issues\" | \"Real-time monitoring\"\n\"Phase 5: Go-Live\" | \"P5.5 - Documentation Completion\" | \"Finalize operational procedures and troubleshooting guides\" | \"2025-06-09\" | \"2025-06-20\" | \"12 days\".19 | \"P5.4\" | \"Technical Writer\" | \"Completed\".24 | \"Operations Manual | Troubleshooting Guides\" | \"Documentation gaps\" | \"Comprehensive review process\"\n\"Phase 6: Support Activation\" | \"P6.1 - Support Team Training\" | \"Train support teams on new platform and procedures\" | \"2025-06-16\" | \"2025-06-27\" | \"12 days\".20 | \"P5.5\" | \"Support Manager\" | \"Completed\".25 | \"Support Procedures | Escalation Matrix\" | \"Support readiness\" | \"Extensive hands-on training\"\n\"Phase 6: Support Activation\" | \"P6.2 - SOC Integration\" | \"Integrate platform with Security Operations Center\" | \"2025-06-23\" | \"2025-07-04\" | \"12 days\".21 | \"P6.1\" | \"SOC Manager\" | \"Completed\".26 | \"SOC Procedures | Monitoring Integration\" | \"SOC integration complexity\" | \"Gradual integration approach\"\n\"Phase 6: Support Activation\" | \"P6.3 - Hypercare Period\" | \"Intensive 24/7 support during initial production period\" | \"2025-06-30\" | \"2025-07-11\" | \"12 days\".22 | \"P6.2\" | \"Support Team\" | \"Completed\".27 | \"Hypercare Report | Issue Resolution\" | \"Critical production issues\" | \"Dedicated support resources\"\n\"Phase 6: Support Activation\" | \"P6.4 - Knowledge Transfer\" | \"Complete knowledge transfer to internal teams\" | \"2025-07-07\" | \"2025-07-18\" | \"12 days\".23 | \"P6.3\" | \"Technical Lead\" | \"Completed\".28 | \"Knowledge Base | Technical Documentation\" | \"Knowledge gaps\" | \"Structured transfer sessions\"\n\"Phase 6: Support Activation\" | \"P6.5 - Project Closure\" | \"Project closure activities and lessons learned documentation\" | \"2025-07-14\" | \"2025-07-25\" | \"12 days\".24 | \"P6.4\" | \"Project Manager\".2 | \"Completed\".29 | \"Project Closure Report | Lessons Learned\" | \"Incomplete closure\" | \"Comprehensive review process\"\n\"Ongoing Operations\" | \"O1 - Monthly Security Review\" | \"Monthly security posture and performance review\" | \"2025-08-01\" | \"Ongoing\" | \"Continuous\" | \"P6.5\" | \"Security Manager\" | \"Active\" | \"Monthly Security Reports\" | \"Performance degradation\".1 | \"Proactive monitoring\"\n\"Ongoing Operations\" | \"O2 - Quarterly Compliance Audit\" | \"Quarterly compliance assessment and certification\" | \"2025-08-01\".1 | \"Ongoing\".1 | \"Continuous\".1 | \"P6.5\".1 | \"Compliance Officer\".1 | \"Active\".1 | \"Compliance Reports\" | \"Compliance drift\" | \"Automated compliance monitoring\"\n\"Ongoing Operations\" | \"O3 - User Training Program\" | \"Continuous security awareness and training program\" | \"2025-08-01\".2 | \"Ongoing\".2 | \"Continuous\".2 | \"P6.5\".2 | \"Training Manager\".1 | \"Active\".2 | \"Training Effectiveness Reports\" | \"User knowledge gaps\" | \"Regular training assessments\"\n\"Ongoing Operations\" | \"O4 - Platform Enhancement\" | \"Ongoing platform optimization and feature enhancement\" | \"2025-08-01\".3 | \"Ongoing\".3 | \"Continuous\".3 | \"P6.5\".3 | \"Platform Engineer\".3 | \"Active\".3 | \"Enhancement Reports\" | \"Technology obsolescence\" | \"Regular technology reviews\"\n\"Ongoing Operations\" | \"O5 - Threat Intelligence Updates\" | \"Continuous threat intelligence and security updates\" | \"2025-08-01\".4 | \"Ongoing\".4 | \"Continuous\".4 | \"P6.5\".4 | \"Threat Analyst\".1 | \"Active\".4 | \"Threat Intelligence Reports\" | \"Emerging threats\" | \"Real-time threat monitoring\""}]