## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Sd Wan Enterprise
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive Network Status | Executive Sponsors | Network infrastructure project status and performance improvements | Weekly | Email Report | EO Project Manager | Email distribution list |  | Network performance metrics, deployment progress, key decisions needed | EO Quarterback and Network Director | Executive | Report delivered on time and strategic decisions made | Active | [DATE] | Include network performance dashboard and ROI tracking
COMM-002 | Network Steering Committee | Project Steering Committee | Strategic direction for network infrastructure and Cisco implementation | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | Network strategy, security policies, budget, timeline, scope changes | EO Quarterback and IT Leadership | Strategic | Meeting attendance >80% and critical decisions documented | Active | [DATE] | Decision authority for network architecture and budget
COMM-003 | Network Team Standup | Core Network Team | Daily coordination for Cisco deployment and configuration | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | Equipment deployment, configuration progress, network blockers | Network Team and Cisco Engineers | Operational | Daily attendance >90% and technical blockers resolved | Active | [DATE] | Focus on network implementation coordination and impediments
COMM-004 | Cisco Architecture Review | Technical and Network Teams | Cisco network architecture and performance optimization | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | Network design, security configuration, performance tuning | EO Sales Engineer (Solution Architecture) and Network Architects | Technical | Network decisions documented and performance targets achieved | Active | [DATE] | Include Cisco optimization results and performance metrics
COMM-010 | Testing Coordination | QA and Testing Teams | Testing progress and quality validation | Weekly | QA Meeting | EO Quarterback | Meeting invitation | 45 minutes | Test execution, quality metrics, defect resolution | QA Team and Test Engineers | Quality | Quality gates met and testing within tolerance | Active | [DATE] | Include testing metrics and quality validation results
COMM-011 | Deployment Planning | Deployment Teams | Production deployment planning and coordination | Weekly | Deployment Meeting | EO Project Manager | Meeting invitation | 60 minutes | Deployment readiness, rollback procedures, go-live coordination | Deployment Team and Operations | Deployment | Deployment readiness achieved and procedures validated | Active | [DATE] | Include deployment checklist and risk mitigation
COMM-012 | Stakeholder Updates | Business Stakeholders | Business impact and readiness updates | Bi-weekly | Business Meeting | EO Sales Engineer | Meeting invitation | 45 minutes | Business readiness, training status, change management | Business Leaders and Change Management | Business | Business stakeholder engagement and readiness achieved | Active | [DATE] | Include business impact assessment and training progress