## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Sd Wan Enterprise
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Description | Acceptance Criteria | Source | Owner | Status | Dependencies | Test Method | Compliance | Notes | Estimated Effort
REQ-001 | Network | Orchestration | Critical | Deploy vManage orchestrator for centralized SD-WAN management | vManage cluster with HA and policy management for 100+ sites | Network Architect | Cisco Team | Draft | Data center infrastructure | Management testing | Cisco certification | Centralized management requirement | 60 hours
REQ-002 | Network | Control Plane | Critical | Deploy vSmart controllers for overlay control plane | vSmart controllers with route reflection and policy distribution | Network Engineer | Cisco Team | Draft | REQ-001 | Control plane testing | SD-WAN architecture | Scalable control plane design | 48 hours
REQ-003 | Network | Authentication | High | Deploy vBond orchestrator for device authentication | vBond with certificate-based device onboarding | Security Team | Cisco Team | Draft | PKI infrastructure | Authentication testing | Security compliance | Zero-touch provisioning | 40 hours
REQ-004 | Network | Edge Deployment | Critical | Deploy cEdge routers at branch locations | ISR/ASR routers with SD-WAN software and dual uplinks | Field Engineers | Deployment Team | Draft | WAN circuits | Site testing | Branch connectivity | Redundant connectivity required | 120 hours
REQ-005 | Network | Policy Engine | High | Implement application-aware routing policies | Traffic steering based on application SLA requirements | Network Operations | Policy Team | Draft | REQ-002 | Policy testing | Application performance | Business application prioritization | 56 hours
REQ-006 | Security | Firewall | High | Configure distributed firewall policies | Zone-based firewall with application inspection | Security Team | Cisco Team | Draft | Security policies | Security testing | Security compliance | Enterprise security standards | 44 hours
REQ-007 | Security | Threat Protection | Medium | Enable integrated threat protection services | IPS and URL filtering with cloud-based updates | Security Operations | Security Team | Draft | REQ-006 | Threat testing | Threat intelligence | Advanced threat protection | 36 hours
REQ-008 | Cloud | Cloud Onramps | Medium | Configure direct cloud connectivity to AWS and Azure | Cloud onramps with optimized routing to cloud services | Cloud Team | Network Team | Draft | Cloud accounts | Cloud testing | Cloud optimization | Cloud-first architecture | 48 hours
REQ-009 | Operations | Monitoring | High | Deploy comprehensive network monitoring and analytics | Real-time visibility with performance and security analytics | Network Operations | Monitoring Team | Draft | REQ-001 | Monitoring validation | NOC integration | Proactive network operations | 40 hours
REQ-010 | Operations | Automation | Medium | Implement configuration templates and automation | Standardized device configurations with automated deployment | Automation Team | DevOps Team | Draft | Template validation | Automation testing | Configuration management | Operational efficiency | 52 hours