## Cover
Test Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Precision Ai Workstation
Customer Name: | Data table for test plan
Version: | 1.0

## Test Plan
Test_Phase | Test_Category | Test_ID | Test_Name | Description | Prerequisites | Expected_Result | Priority | Duration | Responsible_Team
Hardware Testing | Component Validation | HW001 | Hardware POST Test | Verify all hardware components pass Power-On Self Test | Hardware installed and connected | All components pass POST without errors | High | 30 minutes | Hardware Team
Hardware Testing | Performance Testing | HW002 | CPU Performance Validation | Validate CPU performance meets specifications | System fully operational | CPU benchmarks within 5% of specifications | High | 60 minutes | Performance Team
Hardware Testing | Memory Testing | HW003 | Memory Stress Test | Comprehensive memory testing under load | Hardware configuration complete | Memory passes all stress tests without errors | High | 120 minutes | QA Team
Network Testing | Connectivity Testing | NET001 | Network Interface Validation | Test all network interfaces and connectivity | Network configuration complete | All interfaces operational with expected throughput | High | 45 minutes | Network Team
Management Testing | Dell Integration | MGMT001 | iDRAC Functionality Test | Validate iDRAC management capabilities | iDRAC configured and accessible | All management functions operational | Medium | 60 minutes | Systems Team
Security Testing | Security Validation | SEC001 | TPM and Secure Boot Test | Verify security features are properly configured | Security policies applied | Security features operational and compliant | High | 30 minutes | Security Team