## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Vxrail Hci
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Description | Acceptance Criteria | Source | Owner | Status | Dependencies | Test Method | Compliance | Notes | Estimated Effort
REQ-001 | Infrastructure | Hardware | Critical | Deploy VxRail 4-node cluster with All-Flash storage | Cluster deployed with vSAN datastore and 99.9% availability | Business Stakeholder | Infrastructure Team | Draft | Dell hardware delivery | Hardware validation | VMware certification | Minimum cluster configuration | 80 hours
REQ-002 | Infrastructure | Virtualization | Critical | Configure VMware vCenter Server for cluster management | vCenter deployed with SSO and cluster management capabilities | IT Operations | VMware Team | Draft | REQ-001 | Management testing | VMware licensing | Centralized management required | 40 hours
REQ-003 | Infrastructure | Storage | High | Implement vSAN storage policies for data protection | Storage policies with RAID-1 mirroring and encryption at rest | Storage Administrator | Infrastructure Team | Draft | REQ-001 | Storage testing | Data protection compliance | Business critical data protection | 32 hours
REQ-004 | Infrastructure | Network | High | Configure VxRail networking with redundant uplinks | Dual 10GbE uplinks with LACP and VLAN segmentation | Network Administrator | Network Team | Draft | Network infrastructure | Network testing | Network security | Production network isolation | 24 hours
REQ-005 | Management | Lifecycle | High | Deploy VxRail Manager for automated lifecycle management | VxRail Manager with automated patching and health monitoring | System Administrator | Dell Team | Draft | REQ-002 | Lifecycle testing | Dell support | Automated operations capability | 48 hours
REQ-006 | Management | Monitoring | Medium | Integrate with existing monitoring systems via SNMP | Health metrics forwarded to enterprise monitoring system | Monitoring Team | Integration Team | Draft | REQ-005 | Monitoring validation | SNMP v3 | Enterprise monitoring integration | 24 hours
REQ-007 | Security | Access Control | High | Implement role-based access with Active Directory integration | User authentication via AD with appropriate role assignments | Security Team | Identity Team | Draft | Active Directory | Access testing | Security audit | Least privilege access | 32 hours
REQ-008 | Security | Encryption | Critical | Enable vSAN encryption with external key management | Data encrypted at rest with enterprise key management system | Security Team | Infrastructure Team | Draft | Key management system | Encryption validation | Compliance framework | Data protection mandate | 40 hours
REQ-009 | Operations | Backup | High | Integrate VxRail with existing backup infrastructure | VM backups with 4-hour RPO and 1-hour RTO targets | Backup Administrator | Backup Team | Draft | Backup infrastructure | Backup testing | Backup compliance | Business continuity requirement | 36 hours
REQ-010 | Operations | Performance | Medium | Establish performance baselines and capacity monitoring | Performance dashboards with capacity planning reports | Performance Team | Monitoring Team | Draft | REQ-006 | Performance testing | Capacity planning | Proactive capacity management | 28 hours