## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Poweredge Ci Infrastructure
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement_ID | Category | Requirement_Name | Description | Priority | Acceptance_Criteria | Stakeholder | Status | Effort_Estimate_Hours | Dependencies | Risk_Level | Compliance_Framework
REQ-001 | Security Operations | Real-time Threat Detection | Implement AI-powered threat detection with <5 minute MTTD for known attack patterns | Critical | MTTD <5 minutes for critical threats, 99.5% detection accuracy for known attack patterns | CISO | Approved | 120 | Data source integration | Medium | SOC 2 Type II
REQ-002 | Security Operations | Automated Incident Response | Deploy SOAR capabilities for automated response to common security scenarios | Critical | 80% automation rate for Tier 1 security alerts, <30 second response time for automated actions | SOC Manager | Approved | 160 | Analytics rules deployment | Medium | ISO 27001
REQ-003 | Data Integration | Azure AD Integration | Integrate Azure Active Directory logs for identity threat detection | Critical | Complete sign-in and audit log ingestion, real-time identity risk correlation | Identity Team | Approved | 40 | Azure AD Premium licensing | Low | GDPR
REQ-004 | Data Integration | Microsoft 365 Defender Integration | Integrate M365 Defender for endpoint and email security telemetry | Critical | Full endpoint telemetry ingestion, email security event correlation | Security Operations | Approved | 60 | M365 E5 licensing | Low | HIPAA
REQ-005 | Data Integration | Azure Security Center Integration | Integrate ASC for cloud security posture monitoring | Critical | Complete cloud resource monitoring, vulnerability correlation | Cloud Security | Approved | 32 | ASC Standard tier | Low | PCI DSS
REQ-006 | Data Integration | Network Security Integration | Integrate firewall and network security device logs | High | Network traffic analysis, lateral movement detection | Network Security | Approved | 80 | Firewall log forwarding | Medium | FISMA
REQ-007 | Data Integration | Endpoint Security Integration | Integrate EDR platform for endpoint threat detection | High | Endpoint behavioral analysis, process execution monitoring | Endpoint Security | Approved | 72 | EDR API access | Medium | NIST CSF
REQ-008 | Analytics | Custom Detection Rules | Develop organization-specific threat detection analytics | High | Industry-specific threat patterns, custom IoC matching | Threat Intelligence | Approved | 200 | Threat intelligence feeds | High | SOC 2 Type II
REQ-009 | Analytics | Machine Learning Analytics | Enable ML-powered behavioral analytics for anomaly detection | High | User behavior analysis, entity risk scoring | Security Analytics | Approved | 120 | ML models training | High | ISO 27001
REQ-010 | Analytics | Threat Hunting Capabilities | Implement advanced threat hunting platform with KQL | Medium | Interactive hunting queries, saved hunting sessions | Threat Hunters | Approved | 160 | Analyst KQL training | Medium | NIST CSF
REQ-011 | Automation | Incident Creation Automation | Automate security incident creation and assignment | Critical | Automatic incident generation, intelligent severity classification | SOC Manager | Approved | 80 | ITSM integration | Low | SOC 2 Type II
REQ-012 | Automation | Alert Enrichment | Implement automated alert enrichment with threat intelligence | High | Automatic IoC enrichment, geolocation and reputation scoring | Threat Intelligence | Approved | 120 | TI feed integration | Medium | ISO 27001
REQ-013 | Automation | User Account Response | Automate user account disable for compromise scenarios | High | Automatic account lockout, manager notification workflow | Identity Team | Approved | 100 | Identity management API | Medium | GDPR
REQ-014 | Automation | Email Security Response | Automate email security response actions | Medium | Automatic email quarantine, sender blocking | Email Security | Approved | 80 | Email security API | Medium | HIPAA
REQ-015 | Compliance | Audit Trail Generation | Generate comprehensive audit trails for all security activities | Critical | Complete activity logging, immutable audit records | Compliance Team | Approved | 60 | Log retention policies | Low | SOX
REQ-016 | Compliance | Regulatory Reporting | Automated compliance reporting for multiple frameworks | High | SOC 2 Type II, ISO 27001, PCI DSS reporting automation | Compliance Team | Approved | 140 | Compliance templates | Medium | Multiple
REQ-017 | Compliance | Data Retention Management | Implement automated data retention and lifecycle management | High | Policy-based retention, automated archival to cold storage | Data Protection | Approved | 80 | Storage tier configuration | Low | GDPR
REQ-018 | Performance | Query Performance | Ensure sub-30 second response for 90% of security queries | High | Query optimization, index management, caching implementation | Performance Team | Approved | 120 | Resource right-sizing | Medium | SLA Requirements
REQ-019 | Performance | Data Ingestion Scaling | Support 100TB+ daily data ingestion with auto-scaling | High | Horizontal scaling, ingestion rate optimization | Infrastructure Team | Approved | 100 | Infrastructure capacity | Medium | SLA Requirements
REQ-020 | Performance | Dashboard Performance | Ensure <5 second load times for security dashboards | Medium | Dashboard optimization, real-time data visualization | SOC Manager | Approved | 60 | Dashboard redesign | Low | SLA Requirements
REQ-021 | Integration | SIEM Tool Integration | Integrate existing security tools via APIs and connectors | High | Seamless data flow, unified security operations | Integration Team | Approved | 240 | Vendor API documentation | High | Operational Requirement
REQ-022 | Integration | ITSM Integration | Integrate with ServiceNow for incident management workflow | High | Automatic ticket creation, bi-directional status sync | ITSM Team | Approved | 80 | ServiceNow API access | Medium | Operational Requirement
REQ-023 | Integration | Collaboration Platform Integration | Integrate with Microsoft Teams for security notifications | Medium | Real-time security alerts, incident collaboration channels | Communications | Approved | 40 | Teams admin access | Low | Operational Requirement
REQ-024 | Security | Data Encryption | Implement end-to-end encryption for all security data | Critical | AES-256 encryption at rest, TLS 1.3 for transit | Security Architecture | Approved | 60 | Key vault configuration | Low | SOC 2 Type II
REQ-025 | Security | Access Controls | Implement role-based access control with MFA | Critical | Granular RBAC permissions, mandatory MFA for all users | Identity Security | Approved | 80 | Identity provider integration | Low | ISO 27001
REQ-026 | Security | Privileged Access Management | Implement PAM for administrative access to SIEM | High | Just-in-time access, privileged session monitoring | PAM Team | Approved | 100 | PAM tool integration | Medium | SOC 2 Type II
REQ-027 | Disaster Recovery | High Availability Configuration | Implement 99.99% availability with multi-region deployment | High | Active-passive failover, RTO <4 hours, RPO <1 hour | Infrastructure Team | Approved | 120 | Multi-region setup | Medium | Business Continuity
REQ-028 | Disaster Recovery | Backup and Recovery | Implement automated backup and point-in-time recovery | High | Daily automated backups, tested recovery procedures | Backup Team | Approved | 80 | Backup infrastructure | Low | Business Continuity
REQ-029 | Training | Security Analyst Training | Comprehensive training program for security analysts | High | KQL query training, Sentinel administration, incident response | Training Team | Approved | 200 | Training curriculum | Low | Operational Requirement
REQ-030 | Training | Administrator Training | Advanced training for SIEM administrators | High | Platform configuration, analytics rule development, automation | Training Team | Approved | 160 | Admin documentation | Low | Operational Requirement