## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Advanced Security
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Format | Success Metrics
Project Kickoff | All Stakeholders | One-time | Security Summit | Project Manager | GitHub security strategy, DevSecOps transformation, timeline, security objectives | Presentation and Q&A | 100% stakeholder attendance
Sprint Reviews | Development Teams | Bi-weekly | Agile Ceremonies | Security Scrum Master | Security sprint progress, vulnerability remediation, tool adoption, security metrics | Sprint demo and retrospective | 95% team engagement
Executive Security Dashboard | C-Level Executives | Weekly | Security Portal | Security Program Manager | Security posture, vulnerability trends, compliance status, risk metrics | Executive dashboard | Executive satisfaction >4.0
Security Architecture Reviews | Technical Leads | Weekly | Security Committee | Security Architect | Security designs, threat models, security controls, compliance validation | Technical documentation | Architecture approval <24 hours
GitHub Collaboration | GitHub Partners | Monthly | Partner Meetings | Technical Lead | Platform optimization, feature updates, support escalations, best practices | Partnership review | Partner satisfaction >95%
Developer Security Training | Engineering Teams | Monthly | Security Forums | Security Champion | Secure coding practices, tool usage, vulnerability patterns, security awareness | Interactive workshops | Knowledge retention >85%
Vulnerability Management | Security Team | Daily | Security Operations | Vulnerability Manager | Vulnerability status, remediation progress, threat intelligence, incident response | Security briefing | Vulnerability SLA compliance >95%
Compliance Updates | Compliance Team | Monthly | Compliance Reviews | Compliance Officer | Audit preparation, control testing, compliance status, regulatory updates | Compliance dashboard | Compliance score >98%
Security Champions Network | Security Champions | Bi-weekly | Champion Forums | Security Champion Lead | Security updates, tool training, best practices sharing, peer support | Champion community | Champion engagement >90%
DevSecOps Operations | Operations Team | Daily | Operations Channel | DevSecOps Engineer | Pipeline security, scanning results, automation status, tool performance | Operations dashboard | Security pipeline uptime >99%
Security Policy Updates | All Developers | As needed | Developer Notifications | Policy Manager | Policy changes, new security requirements, tool updates, compliance mandates | Policy notification system | Policy awareness >95%
Threat Intelligence | Security Team | Weekly | Threat Intelligence | Threat Analyst | Threat landscape, attack patterns, vulnerability intelligence, defensive measures | Threat briefing | Threat response readiness >95%
Security Metrics | Management Team | Monthly | Security Reviews | Security Metrics Analyst | Security KPIs, trend analysis, benchmark comparisons, improvement opportunities | Metrics dashboard | Target achievement >90%
Incident Communications | All Stakeholders | As needed | Incident Bridge | Incident Commander | Security incident status, impact assessment, containment progress, recovery plans | Incident portal | Response time <SLA
Tool Training | End Users | Ongoing | Learning Platform | Training Manager | GitHub security features, scanning tools, remediation techniques, best practices | Hands-on training | Tool proficiency >85%
Risk Management | Risk Committee | Monthly | Risk Reviews | Risk Manager | Security risk assessments, mitigation strategies, control effectiveness, risk trends | Risk dashboard | Risk score <Medium
Audit Communications | Audit Team | Quarterly | Audit Sessions | Audit Manager | Security control testing, evidence collection, compliance validation, findings | Audit documentation | Audit findings <3 per quarter
Vendor Security | Procurement Team | Quarterly | Security Reviews | Vendor Security Manager | Third-party security assessments, vendor compliance, security requirements | Security scorecard | Vendor security compliance >95%
Security Innovation | Innovation Teams | Monthly | Innovation Labs | Security Innovation Lead | Emerging security technologies, research projects, pilot programs, POCs | Innovation demos | Innovation adoption >70%
Customer Security | Customer Teams | Quarterly | Customer Reviews | Customer Security Manager | Security capabilities, compliance status, security roadmap, customer requirements | Customer briefing | Customer confidence >95%
Business Continuity | Business Teams | Quarterly | Continuity Reviews | Continuity Manager | Security resilience, recovery capabilities, business impact, continuity planning | Continuity dashboard | Recovery readiness >95%
Knowledge Management | Security Community | Monthly | Knowledge Base | Knowledge Manager | Security documentation, lessons learned, best practices, troubleshooting guides | Knowledge articles | Knowledge utilization >80%