## Cover
Project Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Advanced Security
Customer Name: | Data table for project plan
Version: | 1.0

## Project Plan
Phase | Task | Description | Start Date | End Date | Duration | Dependencies | Assigned To | Status | Deliverables | Risks | Mitigation
Phase 1: Foundation | P1.1 - Project Initiation | Project charter, stakeholder alignment, and GitHub partnership establishment | 2025-01-02 | 2025-01-08 | 7 days |  | Project Manager | Completed | Project Charter, Security Strategy | Resource availability | Early commitment processes
Phase 1: Foundation | P1.2 - Security Assessment | Assessment of current application security posture and development practices | 2025-01-06 | 2025-01-15 | 10 days | P1.1 | Security Assessor | Completed | Security Assessment Report, Gap Analysis | Complex legacy security practices | Phased security transformation
Phase 1: Foundation | P1.3 - GitHub Security Architecture | Design GitHub Advanced Security architecture and integration strategy | 2025-01-13 | 2025-01-22 | 10 days | P1.2 | Security Architect | Completed | Security Architecture, Integration Plan | Architecture complexity | Iterative design approach
Phase 1: Foundation | P1.4 - DevSecOps Framework | Define DevSecOps framework and security workflow integration | 2025-01-20 | 2025-01-29 | 10 days | P1.3 | DevSecOps Lead | Completed | DevSecOps Framework, Workflow Design | Developer resistance | Change management approach
Phase 1: Foundation | P1.5 - Policy Framework | Develop security policies and compliance framework | 2025-01-27 | 2025-02-05 | 10 days | P1.4 | Policy Manager | Completed | Security Policies, Compliance Framework | Policy complexity | Stakeholder collaboration
Phase 2: Platform Setup | P2.1 - GitHub Enterprise Setup | Configure GitHub Enterprise with Advanced Security features | 2025-02-03 | 2025-02-10 | 8 days | P1.5 | GitHub Administrator | Completed | GitHub Enterprise, Security Configuration | Platform complexity | GitHub support engagement
Phase 2: Platform Setup | P2.2 - Authentication Integration | Integrate with corporate identity provider and configure SAML SSO | 2025-02-08 | 2025-02-15 | 8 days | P2.1 | Identity Engineer | Completed | SSO Integration, Identity Configuration | Identity integration | Identity team collaboration
Phase 2: Platform Setup | P2.3 - Repository Migration | Migrate existing repositories to GitHub Enterprise with security enabled | 2025-02-12 | 2025-02-19 | 8 days | P2.2 | Migration Engineer | Completed | Repository Migration, Security Enablement | Migration complexity | Phased migration approach
Phase 2: Platform Setup | P2.4 - Security Scanning Setup | Configure code scanning, secret scanning, and dependency scanning | 2025-02-16 | 2025-02-23 | 8 days | P2.3 | Security Engineer | Completed | Security Scanning, Detection Rules | Scanning configuration | GitHub best practices
Phase 2: Platform Setup | P2.5 - Integration Framework | Setup integrations with existing security and development tools | 2025-02-20 | 2025-02-27 | 8 days | P2.4 | Integration Engineer | Completed | Tool Integrations, API Configuration | Integration complexity | API-first approach
Phase 3: Security Implementation | P3.1 - CodeQL Configuration | Configure CodeQL analysis with custom rules and queries | 2025-02-24 | 2025-03-05 | 10 days | P2.5 | CodeQL Engineer | Completed | CodeQL Configuration, Custom Queries | Query complexity | Expert consultation
Phase 3: Security Implementation | P3.2 - Secret Scanning Rules | Implement secret scanning with custom patterns and organization rules | 2025-03-03 | 2025-03-12 | 10 days | P3.1 | Secret Management Engineer | Completed | Secret Scanning Rules, Detection Patterns | Pattern accuracy | Testing and validation
Phase 3: Security Implementation | P3.3 - Dependency Security | Configure dependency scanning and vulnerability management | 2025-03-10 | 2025-03-19 | 10 days | P3.2 | Dependency Engineer | Completed | Dependency Scanning, Policy Configuration | False positives | Policy tuning
Phase 3: Security Implementation | P3.4 - Security Policies | Implement organization security policies and enforcement | 2025-03-17 | 2025-03-26 | 10 days | P3.3 | Policy Engineer | Completed | Security Policies, Enforcement Rules | Policy adoption | Gradual rollout
Phase 3: Security Implementation | P3.5 - Workflow Automation | Implement automated security workflows and remediation | 2025-03-24 | 2025-04-02 | 10 days | P3.4 | Automation Engineer | Completed | Security Workflows, Automation Scripts | Workflow complexity | Incremental automation
Phase 4: Developer Enablement | P4.1 - IDE Integration | Integrate security scanning with developer IDEs and editors | 2025-03-31 | 2025-04-09 | 10 days | P3.5 | Developer Tools Engineer | Completed | IDE Integration, Developer Extensions | IDE compatibility | Multi-IDE support
Phase 4: Developer Enablement | P4.2 - CI/CD Integration | Integrate security scanning into CI/CD pipelines and workflows | 2025-04-07 | 2025-04-16 | 10 days | P4.1 | Pipeline Engineer | Completed | CI/CD Integration, Security Gates | Pipeline complexity | Template-based approach
Phase 4: Developer Enablement | P4.3 - Security Training | Develop and deliver comprehensive security training program | 2025-04-14 | 2025-04-23 | 10 days | P4.2 | Security Trainer | Completed | Training Materials, Certification Program | Training effectiveness | Interactive learning approach
Phase 4: Developer Enablement | P4.4 - Security Champions | Establish security champions program across development teams | 2025-04-21 | 2025-04-30 | 10 days | P4.3 | Security Champion Lead | Completed | Champion Program, Training Framework | Champion engagement | Incentive programs
Phase 4: Developer Enablement | P4.5 - Documentation | Create comprehensive security documentation and best practices | 2025-04-28 | 2025-05-07 | 10 days | P4.4 | Documentation Lead | Completed | Security Documentation, Best Practices | Documentation currency | Continuous updates
Phase 5: Testing and Validation | P5.1 - Security Testing | Comprehensive testing of security scanning and detection capabilities | 2025-05-05 | 2025-05-14 | 10 days | P4.5 | Security Tester | Completed | Security Test Results, Validation Report | Test coverage | Comprehensive test scenarios
Phase 5: Testing and Validation | P5.2 - Performance Testing | Performance testing of security scanning and workflow integration | 2025-05-12 | 2025-05-21 | 10 days | P5.1 | Performance Tester | Completed | Performance Test Results, Optimization Plan | Performance impact | Performance optimization
Phase 5: Testing and Validation | P5.3 - Integration Testing | End-to-end testing of security tool integrations and workflows | 2025-05-19 | 2025-05-28 | 10 days | P5.2 | Integration Tester | Completed | Integration Test Results, Workflow Validation | Integration issues | Systematic testing approach
Phase 5: Testing and Validation | P5.4 - Compliance Validation | Validation of compliance controls and audit readiness | 2025-05-26 | 2025-06-04 | 10 days | P5.3 | Compliance Tester | Completed | Compliance Test Results, Audit Documentation | Compliance gaps | Expert review
Phase 5: Testing and Validation | P5.5 - User Acceptance Testing | User acceptance testing with development teams and security stakeholders | 2025-06-02 | 2025-06-11 | 10 days | P5.4 | Business Analyst | Completed | UAT Results, User Feedback | User acceptance | User feedback integration
Phase 6: Production Deployment | P6.1 - Production Preparation | Prepare production environment and deployment procedures | 2025-06-09 | 2025-06-18 | 10 days | P5.5 | Production Engineer | Completed | Production Environment, Deployment Plan | Production readiness | Comprehensive checklist
Phase 6: Production Deployment | P6.2 - Phased Rollout | Execute phased rollout to development teams and repositories | 2025-06-16 | 2025-06-25 | 10 days | P6.1 | Rollout Manager | Completed | Phased Deployment, Team Onboarding | Rollout complexity | Team-by-team approach
Phase 6: Production Deployment | P6.3 - Security Operations | Activate security operations and monitoring procedures | 2025-06-23 | 2025-07-02 | 10 days | P6.2 | Security Operations | Completed | Security Operations, Monitoring Setup | Operations complexity | 24/7 operations coverage
Phase 6: Production Deployment | P6.4 - Training Delivery | Deliver comprehensive training to all development teams | 2025-06-30 | 2025-07-09 | 10 days | P6.3 | Training Manager | Completed | Training Delivery, Certification | Training scale | Scalable training approach
Phase 6: Production Deployment | P6.5 - Knowledge Transfer | Transfer security knowledge to operations and security teams | 2025-07-07 | 2025-07-16 | 10 days | P6.4 | Knowledge Manager | Completed | Knowledge Transfer, Documentation | Knowledge gaps | Structured transfer process
Ongoing Operations | O1 - Security Operations | Continuous security monitoring and vulnerability management | 2025-07-18 | Ongoing | Continuous | P6.5 | Security Operations | Active | Security Reports | Security incidents | Proactive monitoring
Ongoing Operations | O2 - Tool Optimization | Continuous optimization of security tools and workflows | 2025-07-18 | Ongoing | Continuous | P6.5 | Security Engineering | Active | Optimization Reports | Tool effectiveness | Regular tuning
Ongoing Operations | O3 - Training Updates | Ongoing security training and awareness programs | 2025-07-18 | Ongoing | Continuous | P6.5 | Training Team | Active | Training Reports | Training effectiveness | Continuous learning
Ongoing Operations | O4 - Compliance Management | Continuous compliance monitoring and audit preparation | 2025-07-18 | Ongoing | Continuous | P6.5 | Compliance Team | Active | Compliance Reports | Compliance drift | Automated monitoring
Ongoing Operations | O5 - Platform Evolution | Continuous platform enhancement and feature adoption | 2025-07-18 | Ongoing | Continuous | P6.5 | Platform Team | Active | Evolution Reports | Platform obsolescence | Regular updates