## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Advanced Security
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Category | Requirement ID | Requirement Title | Description | Priority | Source | Business Justification | Acceptance Criteria | Test Method | Status | Owner | Dependencies
Platform Foundation | PLT-001 | GitHub Enterprise Setup | Deploy GitHub Enterprise with Advanced Security features enabled | High | Security Strategy | Enable comprehensive application security scanning and management | GitHub Enterprise deployed with 99.9% uptime and security features | Platform Testing | Implemented | GitHub Administrator | Infrastructure Setup
Platform Foundation | PLT-002 | Repository Management | Centralized repository management with security policy enforcement | High | Code Management | Ensure all code repositories are managed with consistent security controls | 450+ repositories managed with automated security scanning | Repository Testing | Implemented | Repository Manager | Platform Setup
Platform Foundation | PLT-003 | Organization Policies | Organization-wide security policies and enforcement mechanisms | High | Governance Requirements | Enforce consistent security policies across all development teams | Security policies implemented with 100% compliance enforcement | Policy Testing | Implemented | Policy Manager | Platform Configuration
Platform Foundation | PLT-004 | User Management | Comprehensive user management with role-based access controls | High | Access Management | Ensure appropriate access to repositories and security features | 250+ users managed with granular permissions and RBAC | Access Testing | Implemented | User Administrator | Authentication Setup
Platform Foundation | PLT-005 | Audit Logging | Comprehensive audit logging for all security and administrative activities | High | Compliance Requirements | Provide complete audit trail for security and compliance investigations | Audit logging with 100% activity coverage and retention | Audit Testing | Implemented | Audit Manager | Platform Setup
Authentication and Authorization | AUTH-001 | SAML SSO Integration | Single sign-on integration with corporate identity provider | High | Identity Management | Enable seamless authentication with corporate credentials | SAML SSO with 99% authentication success rate | Authentication Testing | Implemented | Identity Engineer | Platform Setup
Authentication and Authorization | AUTH-002 | Team-Based Access Control | Team-based repository access with hierarchical permissions | High | Access Control | Organize access based on team structure and responsibilities | Team-based access with principle of least privilege | Access Control Testing | Implemented | Access Manager | User Management
Authentication and Authorization | AUTH-003 | API Access Management | Secure API access with token-based authentication | High | API Security | Enable secure programmatic access to GitHub resources | API access with OAuth tokens and rate limiting | API Security Testing | Implemented | API Manager | Authentication Setup
Authentication and Authorization | AUTH-004 | Branch Protection | Branch protection rules with required reviews and status checks | High | Code Protection | Protect main branches from unauthorized changes | Branch protection with required reviews and automated checks | Branch Testing | Implemented | Branch Administrator | Repository Setup
Authentication and Authorization | AUTH-005 | Personal Access Tokens | Secure management of personal access tokens with expiration | Medium | Token Management | Ensure secure and controlled use of personal access tokens | Token management with automated expiration and rotation | Token Testing | Implemented | Token Manager | User Management
Code Scanning | SCAN-001 | CodeQL Analysis | Automated static code analysis with CodeQL semantic analysis | High | Security Requirements | Detect security vulnerabilities through static code analysis | CodeQL scanning with 95% vulnerability detection accuracy | CodeQL Testing | Implemented | CodeQL Engineer | Platform Setup
Code Scanning | SCAN-002 | Third-Party Integration | Integration with third-party SAST tools and analyzers | Medium | Tool Integration | Leverage existing security tools and enhance analysis coverage | Third-party tool integration with unified reporting | Integration Testing | Implemented | Integration Engineer | CodeQL Setup
Code Scanning | SCAN-003 | Custom Queries | Organization-specific CodeQL queries and security rules | High | Custom Security | Address organization-specific security patterns and vulnerabilities | Custom queries with 90% accuracy for organization patterns | Query Testing | Implemented | Security Engineer | CodeQL Platform
Code Scanning | SCAN-004 | Scan Automation | Automated scanning triggered by code changes and pull requests | High | Automation Requirements | Ensure all code changes are automatically scanned for vulnerabilities | Automated scanning with sub-5-minute response time | Automation Testing | Implemented | Automation Engineer | CI/CD Integration
Code Scanning | SCAN-005 | Result Management | Centralized management of scan results with triaging and tracking | High | Vulnerability Management | Effectively manage and track security findings and remediation | Result management with automated triaging and assignment | Result Testing | Implemented | Vulnerability Manager | Scanning Platform
Secret Scanning | SECRET-001 | Pattern Detection | Automated detection of secrets and credentials in code repositories | High | Credential Protection | Prevent exposure of sensitive credentials and API keys | Secret detection with 98% accuracy and minimal false positives | Secret Testing | Implemented | Secret Engineer | Platform Setup
Secret Scanning | SECRET-002 | Custom Patterns | Organization-specific secret patterns and detection rules | High | Custom Security | Detect organization-specific credentials and sensitive data | Custom patterns with 95% detection accuracy | Pattern Testing | Implemented | Pattern Engineer | Secret Platform
Secret Scanning | SECRET-003 | Historical Scanning | Retrospective scanning of repository history for exposed secrets | High | Historical Security | Identify and remediate historical credential exposures | Historical scanning with complete repository coverage | Historical Testing | Implemented | History Analyst | Secret Scanning
Secret Scanning | SECRET-004 | Alert Management | Real-time alerting and notification for detected secrets | High | Incident Response | Immediate notification of credential exposure incidents | Real-time alerts with sub-minute notification delivery | Alert Testing | Implemented | Alert Manager | Secret Detection
Secret Scanning | SECRET-005 | Remediation Workflows | Automated workflows for secret remediation and rotation | Medium | Automation Requirements | Streamline secret remediation and credential rotation processes | Automated remediation with 80% workflow automation | Remediation Testing | Implemented | Remediation Engineer | Alert System
Dependency Scanning | DEP-001 | Vulnerability Detection | Automated scanning of dependencies for known vulnerabilities | High | Supply Chain Security | Identify and manage vulnerabilities in third-party dependencies | Dependency scanning with comprehensive vulnerability database coverage | Dependency Testing | Implemented | Dependency Engineer | Platform Setup
Dependency Scanning | DEP-002 | License Compliance | Automated license compliance checking and reporting | Medium | Legal Compliance | Ensure compliance with open-source licensing requirements | License compliance with automated policy enforcement | License Testing | Implemented | License Manager | Dependency Platform
Dependency Scanning | DEP-003 | SBOM Generation | Software Bill of Materials generation for supply chain transparency | Medium | Supply Chain Transparency | Provide comprehensive visibility into software supply chain | SBOM generation with complete dependency mapping | SBOM Testing | Implemented | SBOM Generator | Dependency Scanning
Dependency Scanning | DEP-004 | Policy Enforcement | Automated blocking of vulnerable dependencies based on policies | High | Risk Management | Prevent introduction of high-risk dependencies | Policy enforcement with automated dependency blocking | Policy Testing | Implemented | Policy Enforcer | Dependency Detection
Dependency Scanning | DEP-005 | Update Automation | Automated dependency update suggestions and pull requests | Medium | Maintenance Automation | Streamline dependency maintenance and security updates | Automated updates with 70% successful auto-merge rate | Update Testing | Implemented | Update Automator | Dependency Management
CI/CD Integration | CICD-001 | GitHub Actions Security | Secure GitHub Actions workflows with security scanning integration | High | Pipeline Security | Ensure CI/CD pipelines include comprehensive security checks | GitHub Actions with security scanning in 95% of workflows | Pipeline Testing | Implemented | Pipeline Engineer | Platform Setup
CI/CD Integration | CICD-002 | Security Gates | Automated security gates preventing deployment of vulnerable code | High | Deployment Security | Prevent vulnerable code from reaching production environments | Security gates with 100% enforcement for critical vulnerabilities | Gate Testing | Implemented | Gate Engineer | Scanning Integration
CI/CD Integration | CICD-003 | Third-Party CI Integration | Integration with external CI/CD systems and tools | Medium | Tool Integration | Support teams using external CI/CD platforms | CI/CD integration with major platforms (Jenkins, Azure DevOps) | CI Integration Testing | Implemented | CI Engineer | API Platform
CI/CD Integration | CICD-004 | Artifact Scanning | Security scanning of build artifacts and container images | High | Artifact Security | Ensure build artifacts are free from vulnerabilities | Artifact scanning with comprehensive vulnerability detection | Artifact Testing | Implemented | Artifact Scanner | Pipeline Integration
CI/CD Integration | CICD-005 | Deployment Tracking | Tracking of deployments with security status and compliance | Medium | Deployment Visibility | Maintain visibility into deployment security status | Deployment tracking with security status dashboard | Deployment Testing | Implemented | Deployment Tracker | Security Gates
Developer Experience | DEV-001 | IDE Integration | Security scanning integration with popular IDEs and editors | High | Developer Productivity | Provide real-time security feedback during development | IDE integration with real-time vulnerability detection | IDE Testing | Implemented | IDE Engineer | Scanning Platform
Developer Experience | DEV-002 | Auto-Fix Suggestions | Automated fix suggestions for common vulnerability patterns | Medium | Remediation Assistance | Accelerate vulnerability remediation with automated suggestions | Auto-fix suggestions with 60% successful automatic remediation | Auto-Fix Testing | Implemented | Fix Engineer | Vulnerability Detection
Developer Experience | DEV-003 | Security Training | Integrated security training and best practices guidance | High | Developer Education | Educate developers on secure coding practices | Security training with 85% developer completion rate | Training Assessment | Implemented | Training Manager | Platform Setup
Developer Experience | DEV-004 | Contextual Help | Context-aware security help and documentation | Medium | User Experience | Provide relevant security guidance based on context | Contextual help with 90% user satisfaction | Help Testing | Implemented | UX Designer | Training Platform
Developer Experience | DEV-005 | Performance Optimization | Optimized scanning performance with minimal development impact | High | Performance Requirements | Ensure security scanning doesn't impede development velocity | Scanning performance with <30-second average scan time | Performance Testing | Implemented | Performance Engineer | Scanning Optimization
Compliance and Governance | COMP-001 | SOC 2 Controls | SOC 2 compliance controls for security and availability | High | Compliance Requirements | Meet SOC 2 requirements for customer trust and contracts | SOC 2 controls implemented with quarterly audits | Compliance Testing | Implemented | Compliance Officer | Security Framework
Compliance and Governance | COMP-002 | ISO 27001 Controls | ISO 27001 information security management controls | High | Security Standards | Implement international security management standards | ISO 27001 controls with annual certification | ISO Testing | Implemented | ISO Manager | Security Controls
Compliance and Governance | COMP-003 | Audit Trail | Comprehensive audit trail for all security activities | High | Audit Requirements | Provide complete audit trail for compliance and investigations | Audit trail with 100% activity coverage and integrity | Audit Trail Testing | Implemented | Audit Engineer | Logging Platform
Compliance and Governance | COMP-004 | Data Retention | Secure data retention policies for security and audit data | Medium | Data Governance | Ensure appropriate retention and disposal of security data | Data retention with automated policy enforcement | Retention Testing | Implemented | Data Manager | Audit System
Compliance and Governance | COMP-005 | Reporting Framework | Automated compliance reporting and dashboard generation | Medium | Reporting Requirements | Provide automated compliance reporting for audits | Reporting framework with automated report generation | Reporting Testing | Implemented | Report Engineer | Compliance Platform
Monitoring and Analytics | MON-001 | Security Dashboard | Centralized security dashboard with real-time metrics | High | Visibility Requirements | Provide comprehensive visibility into security posture | Security dashboard with real-time metrics and alerting | Dashboard Testing | Implemented | Dashboard Engineer | Platform Setup
MON-002 | Threat Intelligence | Integration with threat intelligence feeds and analysis | Medium | Threat Awareness | Enhance vulnerability detection with threat intelligence | Threat intelligence integration with automated analysis | Threat Testing | Implemented | Threat Analyst | Security Platform
Monitoring and Analytics | MON-003 | Performance Metrics | Performance monitoring and optimization metrics | Medium | Performance Management | Monitor and optimize security tool performance | Performance metrics with automated optimization | Metrics Testing | Implemented | Metrics Engineer | Monitoring Platform
Monitoring and Analytics | MON-004 | Trend Analysis | Security trend analysis and predictive insights | Medium | Strategic Planning | Provide insights for security strategy and planning | Trend analysis with predictive security insights | Analytics Testing | Implemented | Analytics Engineer | Data Platform
Monitoring and Analytics | MON-005 | Alerting Framework | Intelligent alerting with customizable rules and escalation | High | Incident Response | Ensure timely notification of security issues | Alerting framework with intelligent routing and escalation | Alert Testing | Implemented | Alert Engineer | Monitoring Setup