## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Actions Enterprise Cicd
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication ID | Communication Type | Audience | Purpose | Frequency | Format | Owner | Distribution Method | Meeting Duration | Agenda Topics | Key Stakeholders | Escalation Level | Success Metrics | Status | Next Scheduled | Notes
COMM-001 | Executive DevOps Status | Executive Sponsors | DevOps platform project status and automation improvements | Weekly | Email Report | EO Project Manager | Email distribution list |  | Automation metrics, deployment frequency, key decisions needed | EO Quarterback and Engineering Director | Executive | Report delivered on time and strategic decisions made | Active | [DATE] | Include DevOps metrics dashboard and productivity tracking
COMM-002 | DevOps Steering Committee | Project Steering Committee | Strategic direction for DevOps platform and CI/CD implementation | Bi-weekly | In-Person Meeting | EO Project Manager | Meeting invitation | 60 minutes | DevOps strategy, toolchain decisions, budget, timeline, scope changes | EO Quarterback and Engineering Leadership | Strategic | Meeting attendance >80% and critical decisions documented | Active | [DATE] | Decision authority for DevOps architecture and tooling
COMM-003 | DevOps Team Standup | Core DevOps Team | Daily coordination for CI/CD pipeline development | Daily | Virtual Meeting | EO Quarterback | Video conference | 15 minutes | Pipeline development, automation progress, DevOps blockers | DevOps Team and Platform Engineers | Operational | Daily attendance >90% and technical blockers resolved | Active | [DATE] | Focus on DevOps implementation coordination and impediments
COMM-004 | Platform Architecture Review | Technical and DevOps Teams | DevOps platform architecture and automation optimization | Weekly | Technical Meeting | EO Quarterback | Meeting invitation | 90 minutes | CI/CD design, automation workflows, platform integration | EO Sales Engineer (Solution Architecture) and DevOps Architects | Technical | Platform decisions documented and automation targets achieved | Active | [DATE] | Include DevOps optimization results and automation metrics
COMM-010 | Testing Coordination | QA and Testing Teams | Testing progress and quality validation | Weekly | QA Meeting | EO Quarterback | Meeting invitation | 45 minutes | Test execution, quality metrics, defect resolution | QA Team and Test Engineers | Quality | Quality gates met and testing within tolerance | Active | [DATE] | Include testing metrics and quality validation results
COMM-011 | Deployment Planning | Deployment Teams | Production deployment planning and coordination | Weekly | Deployment Meeting | EO Project Manager | Meeting invitation | 60 minutes | Deployment readiness, rollback procedures, go-live coordination | Deployment Team and Operations | Deployment | Deployment readiness achieved and procedures validated | Active | [DATE] | Include deployment checklist and risk mitigation
COMM-012 | Stakeholder Updates | Business Stakeholders | Business impact and readiness updates | Bi-weekly | Business Meeting | EO Sales Engineer | Meeting invitation | 45 minutes | Business readiness, training status, change management | Business Leaders and Change Management | Business | Business stakeholder engagement and readiness achieved | Active | [DATE] | Include business impact assessment and training progress