## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Landing Zone
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Format | Success Metrics
Project Kickoff | All Stakeholders | One-time | In-person/Virtual Meeting | Project Manager | Project overview, objectives, timeline, roles and responsibilities | Presentation and Q&A | 100% stakeholder attendance
Weekly Status Updates | Project Team | Weekly | Email/Slack | Project Manager | Progress updates, blockers, upcoming milestones, resource needs | Status report template | 95% team engagement
Executive Dashboard | C-Level Executives | Bi-weekly | Executive Dashboard | Program Manager | High-level progress, budget status, risk summary, key decisions needed | Visual dashboard | Executive satisfaction score >4.0
Technical Architecture Reviews | Technical Leads | Bi-weekly | Architecture Review Board | Solution Architect | Architecture decisions, design changes, technical risks, standards compliance | Technical documentation | Architecture approval within 3 days
Stakeholder Updates | Business Sponsors | Monthly | Formal Presentation | Project Manager | Milestone progress, business value delivery, budget updates, risk mitigation | Executive summary report | Stakeholder confidence >90%
Change Communications | All Affected Users | As needed | Email/Intranet | Change Manager | System changes, new procedures, training requirements, go-live dates | Change notification template | User awareness >95%
Risk and Issue Escalation | Executive Sponsors | As needed | Direct Communication | Project Manager | Critical risks, blockers requiring executive intervention, budget impacts | Escalation template | Resolution within 48 hours
Training Communications | End Users | Monthly | Training Portal | Training Manager | Training schedule, new courses, certification requirements, skill assessments | Learning management system | Training completion >90%
Technical Deep Dives | Engineering Teams | Weekly | Technical Sessions | Technical Leads | Implementation details, code reviews, integration patterns, best practices | Technical workshops | Knowledge transfer effectiveness >85%
Security Reviews | Security Team | Bi-weekly | Security Committee | Security Architect | Security assessments, compliance status, vulnerability reports, control implementation | Security dashboard | Security approval within 5 days
Vendor Communications | Technology Partners | Monthly | Vendor Meetings | Vendor Manager | Service delivery, support escalations, roadmap alignment, contract performance | Vendor scorecard | Vendor performance >95%
Quality Assurance | QA Team | Weekly | QA Reviews | QA Lead | Test results, defect status, quality metrics, release readiness | Quality dashboard | Defect resolution within SLA
Operations Handover | Operations Team | Bi-weekly | Operations Reviews | Technical Lead | Operational procedures, monitoring setup, support documentation, troubleshooting guides | Operations runbook | Operations readiness score >90%
Budget Reviews | Finance Team | Monthly | Financial Reviews | Program Manager | Budget utilization, forecast accuracy, cost optimization opportunities, financial risks | Financial dashboard | Budget variance <5%
Compliance Updates | Compliance Team | Monthly | Compliance Reviews | Compliance Officer | Audit preparation, control testing, compliance status, regulatory updates | Compliance scorecard | Compliance score >95%
Performance Reports | Infrastructure Team | Weekly | Performance Reviews | Infrastructure Lead | System performance, capacity utilization, optimization recommendations, SLA compliance | Performance dashboard | SLA compliance >99%
User Feedback | End Users | Ongoing | Feedback Portal | User Experience Lead | User satisfaction, feature requests, usability issues, improvement suggestions | Feedback management system | User satisfaction >4.0
Incident Communications | All Stakeholders | As needed | Incident Bridge | Incident Manager | Incident status, impact assessment, resolution progress, preventive measures | Incident status page | Resolution time within SLA
Go-Live Communications | All Stakeholders | Pre/During/Post Go-Live | Multiple Channels | Program Manager | Readiness status, go-live schedule, contingency plans, success metrics | Go-live playbook | Successful go-live execution
Lessons Learned | Project Team | Post-Implementation | Workshop | Project Manager | Project retrospective, best practices, improvement opportunities, knowledge capture | Lessons learned document | Action item completion >90%
Success Celebration | All Contributors | Post-Implementation | Team Event | Executive Sponsor | Achievement recognition, success metrics, team appreciation, future opportunities | Recognition event | Team satisfaction >4.5
Knowledge Transfer | Support Teams | Ongoing | Knowledge Base | Documentation Lead | Technical documentation, troubleshooting guides, best practices, lessons learned | Knowledge management system | Knowledge base completeness >95%