## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Landing Zone
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Category | Requirement ID | Requirement Title | Description | Priority | Source | Business Justification | Acceptance Criteria | Test Method | Status | Owner | Dependencies
Infrastructure Foundation | INF-001 | Google Cloud Organization Setup | Establish Google Cloud organization with proper hierarchy and resource management | High | Enterprise Architecture | Enable centralized governance and policy management | Organization created with 3-tier hierarchy (organization/folders/projects) | Configuration Validation | Implemented | Cloud Architect | Account Setup
Infrastructure Foundation | INF-002 | Multi-Project Architecture | Implement multi-project architecture for workload isolation | High | Security Requirements | Ensure proper workload isolation and security boundaries | 15 projects created with appropriate resource allocation | Project Validation | Implemented | Cloud Engineer | Organization Setup
Infrastructure Foundation | INF-003 | Regional Deployment | Deploy infrastructure across multiple Google Cloud regions | High | Availability Requirements | Ensure high availability and disaster recovery capabilities | Active deployment in 3 primary regions with DR capability | Regional Testing | Implemented | Infrastructure Engineer | Network Setup
Infrastructure Foundation | INF-004 | Resource Hierarchy | Implement standardized resource naming and tagging strategy | Medium | Governance Requirements | Enable effective resource management and cost allocation | All resources tagged with owner, environment, and cost center | Tag Validation | Implemented | Governance Engineer | Organization Setup
Infrastructure Foundation | INF-005 | Capacity Planning | Implement capacity planning and resource rightsizing | Medium | Cost Optimization | Optimize infrastructure costs through proper resource sizing | Automated rightsizing recommendations with 20% cost reduction | Capacity Testing | Implemented | FinOps Engineer | Monitoring Setup
Network Architecture | NET-001 | VPC Network Design | Design and implement VPC networks with proper segmentation | High | Network Security | Ensure secure network segmentation and traffic control | VPC networks deployed with micro-segmentation capabilities | Network Testing | Implemented | Network Architect
Network Architecture | NET-002 | Hybrid Connectivity | Establish Cloud Interconnect for hybrid connectivity | High | Connectivity Requirements | Enable secure connection to on-premises infrastructure | 10 Gbps dedicated interconnect with 99.9% uptime SLA | Connectivity Testing | Implemented | Network Engineer | VPC Setup
Network Architecture | NET-003 | Load Balancing | Implement global load balancing for high availability | High | Performance Requirements | Ensure optimal application performance and availability | Global load balancer with health checks and automatic failover | Load Testing | Implemented | Load Balancer Engineer | Network Setup
Network Architecture | NET-004 | DNS Management | Implement Cloud DNS for domain name resolution | Medium | Infrastructure Requirements | Provide reliable DNS services for applications | Cloud DNS zones configured with 99.9% availability | DNS Testing | Implemented | DNS Engineer | Network Setup
Network Architecture | NET-005 | Network Security | Implement network security controls and firewall rules | High | Security Requirements | Ensure network traffic is properly secured and controlled | Firewall rules implemented with default deny policy | Security Testing | Implemented | Security Engineer | VPC Setup
Identity and Access Management | IAM-001 | Identity Provider Integration | Integrate with corporate identity provider (Active Directory) | High | Identity Requirements | Enable single sign-on and centralized identity management | SSO integration with 99% authentication success rate | Identity Testing | Implemented | Identity Engineer
Identity and Access Management | IAM-002 | Role-Based Access Control | Implement granular RBAC with principle of least privilege | High | Security Requirements | Ensure users have minimum required access to resources | RBAC implemented with quarterly access reviews | Access Testing | Implemented | IAM Specialist | Identity Integration
Identity and Access Management | IAM-003 | Service Account Management | Implement service account governance and lifecycle management | High | Security Requirements | Ensure service accounts are properly managed and secured | Service accounts created with rotation and monitoring | Service Account Testing | Implemented | Security Engineer | IAM Setup
Identity and Access Management | IAM-004 | Privileged Access Management | Implement privileged access controls for administrative functions | High | Security Requirements | Control and monitor privileged access to infrastructure | Privileged access requires approval and is monitored | PAM Testing | Implemented | Security Architect | RBAC Setup
Identity and Access Management | IAM-005 | API Security | Implement API authentication and authorization controls | High | API Security | Secure API access with proper authentication mechanisms | APIs secured with OAuth 2.0 and rate limiting | API Security Testing | Implemented | API Security Engineer | IAM Setup
Security and Compliance | SEC-001 | Encryption Implementation | Implement encryption at rest and in transit for all data | High | Security Requirements | Protect sensitive data through comprehensive encryption | All data encrypted with customer-managed keys | Encryption Testing | Implemented | Security Engineer | KMS Setup
Security and Compliance | SEC-002 | Security Monitoring | Implement Security Command Center for threat detection | High | Security Operations | Enable real-time threat detection and incident response | Security monitoring with automated alerting and response | Security Testing | Implemented | Security Operations | Logging Setup
Security and Compliance | SEC-003 | Vulnerability Management | Implement automated vulnerability scanning and remediation | High | Security Requirements | Identify and remediate security vulnerabilities proactively | Vulnerability scans automated with 24-hour remediation SLA | Vulnerability Testing | Implemented | Vulnerability Engineer | Security Monitoring
Security and Compliance | SEC-004 | Compliance Controls | Implement SOC 2, ISO 27001, and PCI DSS compliance controls | High | Compliance Requirements | Meet regulatory and industry compliance standards | Compliance controls implemented with quarterly audits | Compliance Testing | Implemented | Compliance Officer | Security Framework
Security and Compliance | SEC-005 | Incident Response | Implement automated incident response and forensics capabilities | High | Security Operations | Enable rapid response to security incidents | Incident response procedures with 30-minute response time | Incident Testing | Implemented | Incident Response Team | Security Monitoring
Monitoring and Observability | MON-001 | Infrastructure Monitoring | Implement comprehensive infrastructure monitoring and alerting | High | Operations Requirements | Ensure infrastructure health and performance visibility | Infrastructure monitoring with 99.9% uptime alerting | Monitoring Testing | Implemented | Monitoring Engineer | Infrastructure Setup
Monitoring and Observability | MON-002 | Application Performance Monitoring | Implement APM for application performance visibility | High | Performance Requirements | Monitor application performance and user experience | APM implemented with response time and error rate monitoring | APM Testing | Implemented | APM Engineer | Application Deployment
Monitoring and Observability | MON-003 | Log Management | Implement centralized logging and log analysis | High | Operations Requirements | Centralize logs for troubleshooting and analysis | Centralized logging with search and alerting capabilities | Log Testing | Implemented | Log Engineer | Infrastructure Setup
Monitoring and Observability | MON-004 | Metrics and Dashboards | Create operational dashboards for infrastructure and applications | Medium | Operations Requirements | Provide visibility into system health and performance | Operational dashboards with real-time metrics | Dashboard Testing | Implemented | Dashboard Engineer | Monitoring Setup
Monitoring and Observability | MON-005 | Alerting Framework | Implement intelligent alerting with escalation procedures | High | Operations Requirements | Ensure timely notification of infrastructure issues | Alerting framework with automated escalation and on-call rotation | Alert Testing | Implemented | Alert Engineer | Monitoring Setup
Backup and Disaster Recovery | DR-001 | Backup Strategy | Implement automated backup for all critical systems and data | High | Data Protection | Protect against data loss through comprehensive backups | Automated backups with 99.9% success rate and 4-hour RPO | Backup Testing | Implemented | Backup Engineer | Storage Setup
Backup and Disaster Recovery | DR-002 | Disaster Recovery | Implement disaster recovery with cross-region replication | High | Business Continuity | Ensure business continuity during major outages | DR environment with 4-hour RTO and 1-hour RPO | DR Testing | Implemented | DR Engineer | Backup Setup
Backup and Disaster Recovery | DR-003 | Business Continuity | Develop business continuity plans and procedures | High | Risk Management | Ensure business operations continue during disasters | Business continuity plan with quarterly testing | BC Testing | Implemented | BC Manager | DR Setup
Backup and Disaster Recovery | DR-004 | Data Replication | Implement real-time data replication across regions | High | Data Protection | Ensure data availability during regional outages | Data replication with 99.9% consistency | Replication Testing | Implemented | Data Engineer | DR Infrastructure
Backup and Disaster Recovery | DR-005 | Recovery Testing | Implement regular disaster recovery testing procedures | High | Risk Management | Validate disaster recovery capabilities regularly | Quarterly DR tests with documented results | Recovery Testing | Implemented | DR Tester | DR Procedures
Cost Management | COST-001 | Cost Monitoring | Implement comprehensive cost monitoring and reporting | High | Financial Management | Provide visibility into cloud spending and utilization | Cost monitoring with project-level granularity | Cost Testing | Implemented | FinOps Engineer | Billing Setup
Cost Management | COST-002 | Budget Controls | Implement automated budget controls and alerting | High | Financial Management | Prevent cost overruns through automated controls | Budget alerts with automatic resource scaling controls | Budget Testing | Implemented | Budget Manager | Cost Monitoring
Cost Management | COST-003 | Resource Optimization | Implement automated resource rightsizing and optimization | Medium | Cost Optimization | Optimize costs through intelligent resource management | Rightsizing recommendations with 25% cost reduction | Optimization Testing | Implemented | Optimization Engineer | Cost Monitoring
Cost Management | COST-004 | Chargeback System | Implement cost allocation and chargeback to business units | Medium | Financial Management | Enable accurate cost attribution to business units | Chargeback system with monthly cost allocation reports | Chargeback Testing | Implemented | Chargeback Analyst | Cost Monitoring
Cost Management | COST-005 | Reserved Capacity | Implement strategic use of committed use discounts | Medium | Cost Optimization | Reduce costs through committed capacity planning | Reserved capacity strategy with 30% discount achievement | Capacity Testing | Implemented | Capacity Planner | Usage Analysis
Governance and Automation | GOV-001 | Organization Policies | Implement organization policies for resource governance | High | Governance Requirements | Ensure consistent policy enforcement across all projects | Organization policies implemented with 100% compliance | Policy Testing | Implemented | Policy Engineer | Organization Setup
Governance and Automation | GOV-002 | Infrastructure as Code | Implement Terraform for infrastructure automation | High | Automation Requirements | Enable repeatable and consistent infrastructure deployment | Terraform modules with 95% automated deployment success | IaC Testing | Implemented | IaC Engineer
Governance and Automation | GOV-003 | CI/CD Pipeline | Implement automated deployment pipelines | High | DevOps Requirements | Enable automated application and infrastructure deployment | CI/CD pipelines with automated testing and deployment | Pipeline Testing | Implemented | DevOps Engineer | IaC Setup
Governance and Automation | GOV-004 | Change Management | Implement automated change management and approval workflows | Medium | Operations Requirements | Ensure proper change control and approval processes | Change management with automated approval workflows | Change Testing | Implemented | Change Manager | CI/CD Setup
Governance and Automation | GOV-005 | Configuration Management | Implement configuration management and drift detection | Medium | Operations Requirements | Ensure configuration consistency and compliance | Configuration management with automated drift remediation | Config Testing | Implemented | Config Engineer | IaC Setup
Performance and Scalability | PERF-001 | Auto Scaling | Implement auto-scaling for compute resources | High | Performance Requirements | Ensure applications scale automatically based on demand | Auto-scaling configured with 300% traffic handling capability | Scale Testing | Implemented | Scale Engineer | Load Balancer Setup
Performance and Scalability | PERF-002 | Performance Optimization | Implement performance optimization and tuning | High | Performance Requirements | Ensure optimal application and infrastructure performance | Performance optimization achieving 40% improvement | Performance Testing | Implemented | Performance Engineer | Monitoring Setup
Performance and Scalability | PERF-003 | Capacity Planning | Implement predictive capacity planning and forecasting | Medium | Capacity Management | Plan capacity requirements based on growth projections | Capacity planning with 6-month accurate forecasting | Capacity Testing | Implemented | Capacity Engineer | Monitoring Setup
Performance and Scalability | PERF-004 | Load Testing | Implement automated load testing and performance validation | High | Quality Assurance | Validate system performance under expected loads | Load testing framework with automated performance validation | Load Testing | Implemented | Load Test Engineer | Performance Setup
Performance and Scalability | PERF-005 | Caching Strategy | Implement intelligent caching for performance optimization | Medium | Performance Requirements | Improve application performance through strategic caching | Caching implementation with 50% response time improvement | Cache Testing | Implemented | Cache Engineer | Application Setup
Training and Documentation | TRAIN-001 | Technical Documentation | Create comprehensive technical documentation and runbooks | High | Knowledge Management | Provide detailed documentation for operations and troubleshooting | Technical documentation with 95% coverage of procedures | Documentation Review | Implemented | Technical Writer | Implementation Completion
Training and Documentation | TRAIN-002 | User Training | Provide comprehensive training for end users and administrators | High | User Enablement | Ensure users can effectively utilize the platform | Training program with 90% user certification rate | Training Assessment | Implemented | Training Manager | Documentation Completion
Training and Documentation | TRAIN-003 | Operations Training | Provide specialized training for operations and support teams | High | Operations Enablement | Ensure operations teams can effectively manage the platform | Operations training with 95% competency achievement | Operations Assessment | Implemented | Operations Trainer | User Training
Training and Documentation | TRAIN-004 | Knowledge Transfer | Implement knowledge transfer and best practices sharing | Medium | Knowledge Management | Share knowledge and best practices across teams | Knowledge transfer with documented best practices | Knowledge Assessment | Implemented | Knowledge Manager | Training Completion
Training and Documentation | TRAIN-005 | Continuous Learning | Establish continuous learning and certification programs | Medium | Skill Development | Maintain current skills and certifications for team members | Certification program with 80% team participation | Certification Tracking | Implemented | Learning Manager | Training Infrastructure