## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Workspace
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Format | Success Metrics
Project Kickoff | All Stakeholders | One-time | All-Hands Meeting | Project Manager | Google Workspace strategy, collaboration transformation, migration timeline, user benefits | Presentation and Q&A | 100% stakeholder attendance
Migration Updates | All Employees | Weekly | Email/Intranet | Migration Manager | Migration progress, upcoming changes, training schedules, support resources | Newsletter format | 95% employee awareness
Executive Dashboard | Leadership Team | Bi-weekly | Executive Portal | Program Manager | Migration progress, user adoption, cost savings, ROI metrics | Executive dashboard | Leadership satisfaction >4.0
IT Coordination | IT Teams | Daily | IT Channels | Technical Lead | Technical progress, system integrations, issue resolution, infrastructure updates | Technical briefing | IT team alignment >95%
Google Partnership | Google Teams | Monthly | Partner Meetings | Partnership Manager | Platform optimization, feature updates, support escalations, roadmap alignment | Partnership review | Partner satisfaction >95%
Department Liaisons | Department Heads | Weekly | Department Meetings | Change Manager | Department-specific updates, training coordination, adoption metrics, feedback collection | Department briefing | Department engagement >90%
User Training | End Users | Ongoing | Training Platform | Training Manager | Google Workspace features, collaboration best practices, productivity tips, support resources | Interactive training | Training completion >90%
Champion Network | Power Users | Bi-weekly | Champion Forums | Champion Coordinator | Advanced features, peer support strategies, feedback sharing, success stories | Champion community | Champion engagement >95%
Help Desk | Support Team | Daily | Support Channels | Support Manager | Issue trends, resolution procedures, escalation processes, knowledge updates | Support briefing | Ticket resolution >95%
Security Updates | Security Team | Weekly | Security Committee | Security Officer | Security policies, compliance status, threat monitoring, access controls | Security briefing | Security compliance >98%
Change Management | Change Agents | Weekly | Change Network | Change Manager | Adoption strategies, resistance management, success measurement, best practices | Change workshop | Change effectiveness >85%
Vendor Management | Procurement Team | Monthly | Vendor Reviews | Vendor Manager | License optimization, cost management, contract performance, renewal planning | Vendor scorecard | Cost optimization >target
Compliance Updates | Compliance Team | Monthly | Compliance Reviews | Compliance Officer | Regulatory compliance, audit preparation, policy updates, control testing | Compliance dashboard | Compliance score >95%
User Feedback | All Users | Ongoing | Feedback Portal | User Experience Manager | User satisfaction, feature requests, usability feedback, improvement suggestions | Feedback system | User satisfaction >4.5
Business Impact | Business Leaders | Monthly | Business Reviews | Business Analyst | Productivity metrics, collaboration improvements, business value, ROI analysis | Business dashboard | Business value achievement >target
Performance Reports | Operations Team | Weekly | Operations Reviews | Operations Manager | System performance, availability metrics, optimization opportunities, capacity planning | Performance dashboard | SLA compliance >99%
Training Effectiveness | Learning Team | Monthly | Learning Reviews | Learning Manager | Training completion rates, skill assessments, competency development, knowledge retention | Learning analytics | Learning objectives >85%
Integration Updates | Integration Team | Bi-weekly | Integration Reviews | Integration Manager | System integrations, API performance, data flows, compatibility updates | Integration briefing | Integration success >95%
Mobile Enablement | Mobile Users | Monthly | Mobile Forums | Mobile Coordinator | Mobile features, device management, security policies, productivity tips | Mobile guidance | Mobile adoption >target
Global Coordination | Global Teams | Weekly | Global Forums | Global Manager | Regional updates, localization status, cultural considerations, global standards | Global briefing | Global alignment >90%
Innovation Showcase | Innovation Teams | Quarterly | Innovation Sessions | Innovation Lead | New features, productivity innovations, automation opportunities, future roadmap | Innovation demos | Innovation adoption >70%
Emergency Communications | All Stakeholders | As needed | Emergency Channels | Emergency Coordinator | Service outages, security incidents, critical updates, recovery procedures | Emergency alerts | Response time <30 minutes