## Cover
Project Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Workspace
Customer Name: | Data table for project plan
Version: | 1.0

## Project Plan
Phase | Task | Description | Start Date | End Date | Duration | Dependencies | Assigned To | Status | Deliverables | Risks | Mitigation
Phase 1: Planning | P1.1 - Project Initiation | Project charter, stakeholder alignment, and Google partnership establishment | 2025-01-02 | 2025-01-08 | 7 days |  | Project Manager | Completed | Project Charter, Stakeholder Matrix | Stakeholder alignment | Executive sponsorship
Phase 1: Planning | P1.2 - Current State Assessment | Assessment of existing collaboration tools and user requirements | 2025-01-06 | 2025-01-15 | 10 days | P1.1 | Business Analyst | Completed | Current State Report, Requirements Analysis | Complex requirements | User interview process
Phase 1: Planning | P1.3 - Migration Strategy | Design migration strategy and timeline for Google Workspace | 2025-01-13 | 2025-01-22 | 10 days | P1.2 | Migration Architect | Completed | Migration Strategy, Timeline Plan | Migration complexity | Phased migration approach
Phase 1: Planning | P1.4 - Security Framework | Design security architecture and compliance framework | 2025-01-20 | 2025-01-29 | 10 days | P1.3 | Security Architect | Completed | Security Architecture, Compliance Plan | Security requirements | Google security consultation
Phase 1: Planning | P1.5 - Change Management Strategy | Develop comprehensive change management and training strategy | 2025-01-27 | 2025-02-05 | 10 days | P1.4 | Change Manager | Completed | Change Strategy, Training Plan | User resistance | User-centric approach
Phase 2: Infrastructure Setup | P2.1 - Google Workspace Setup | Configure Google Workspace tenant and administrative controls | 2025-02-03 | 2025-02-10 | 8 days | P1.5 | Google Administrator | Completed | Workspace Tenant, Admin Configuration | Configuration complexity | Google expert support
Phase 2: Infrastructure Setup | P2.2 - Identity Integration | Integrate with Active Directory and configure single sign-on | 2025-02-08 | 2025-02-15 | 8 days | P2.1 | Identity Engineer | Completed | SSO Integration, Directory Sync | Identity complexity | Identity team collaboration
Phase 2: Infrastructure Setup | P2.3 - Security Configuration | Configure security policies, DLP, and compliance controls | 2025-02-12 | 2025-02-19 | 8 days | P2.2 | Security Engineer | Completed | Security Policies, DLP Configuration | Policy complexity | Gradual policy rollout
Phase 2: Infrastructure Setup | P2.4 - Mobile Device Management | Configure mobile device management and security policies | 2025-02-16 | 2025-02-23 | 8 days | P2.3 | MDM Administrator | Completed | MDM Configuration, Mobile Policies | Device compatibility | Multi-platform testing
Phase 2: Infrastructure Setup | P2.5 - Integration Framework | Setup integrations with existing enterprise applications | 2025-02-20 | 2025-02-27 | 8 days | P2.4 | Integration Engineer | Completed | Application Integrations, API Configuration | Integration challenges | API-first approach
Phase 3: Pilot Deployment | P3.1 - Pilot Group Selection | Select and prepare pilot user groups for initial deployment | 2025-02-24 | 2025-03-03 | 8 days | P2.5 | Pilot Coordinator | Completed | Pilot Group, User Selection | Pilot representation | Diverse user group selection
Phase 3: Pilot Deployment | P3.2 - Pilot Migration | Migrate pilot users to Google Workspace with full support | 2025-03-01 | 2025-03-10 | 10 days | P3.1 | Migration Engineer | Completed | Pilot Migration, User Accounts | Migration issues | Comprehensive testing
Phase 3: Pilot Deployment | P3.3 - Pilot Training | Deliver intensive training to pilot users and collect feedback | 2025-03-08 | 2025-03-17 | 10 days | P3.2 | Training Manager | Completed | Pilot Training, User Feedback | Training effectiveness | Interactive training approach
Phase 3: Pilot Deployment | P3.4 - Pilot Optimization | Optimize configuration based on pilot feedback and performance | 2025-03-15 | 2025-03-24 | 10 days | P3.3 | Optimization Engineer | Completed | Configuration Optimization, Performance Tuning | Optimization complexity | Data-driven optimization
Phase 3: Pilot Deployment | P3.5 - Pilot Validation | Validate pilot success and prepare for full deployment | 2025-03-22 | 2025-03-31 | 10 days | P3.4 | Validation Manager | Completed | Pilot Success Report, Deployment Plan | Validation criteria | Clear success metrics
Phase 4: Training and Preparation | P4.1 - Training Content Development | Develop comprehensive training materials and resources | 2025-03-29 | 2025-04-07 | 10 days | P3.5 | Content Developer | Completed | Training Materials, E-Learning Content | Content quality | Subject matter expert review
Phase 4: Training and Preparation | P4.2 - Trainer Preparation | Train internal trainers and establish champion network | 2025-04-05 | 2025-04-14 | 10 days | P4.1 | Training Coordinator | Completed | Trainer Certification, Champion Network | Trainer readiness | Train-the-trainer program
Phase 4: Training and Preparation | P4.3 - Support Infrastructure | Establish help desk and support procedures for deployment | 2025-04-12 | 2025-04-21 | 10 days | P4.2 | Support Manager | Completed | Support Infrastructure, Help Desk Setup | Support capacity | Scaled support model
Phase 4: Training and Preparation | P4.4 - Communication Campaign | Launch comprehensive communication campaign for deployment | 2025-04-19 | 2025-04-28 | 10 days | P4.3 | Communications Manager | Completed | Communication Campaign, Awareness Materials | Message clarity | Multi-channel communication
Phase 4: Training and Preparation | P4.5 - Final Preparations | Complete final preparations and readiness validation | 2025-04-26 | 2025-05-05 | 10 days | P4.4 | Deployment Manager | Completed | Deployment Readiness, Final Checklist | Readiness gaps | Comprehensive readiness review
Phase 5: Migration Execution | P5.1 - Wave 1 Migration | Migrate first wave of users (early adopters and champions) | 2025-05-03 | 2025-05-12 | 10 days | P4.5 | Migration Team | Completed | Wave 1 Migration, User Accounts | Migration complexity | Experienced user support
Phase 5: Migration Execution | P5.2 - Wave 2 Migration | Migrate second wave of users (department by department) | 2025-05-10 | 2025-05-19 | 10 days | P5.1 | Migration Team | Completed | Wave 2 Migration, Department Rollout | Scale challenges | Parallel migration streams
Phase 5: Migration Execution | P5.3 - Wave 3 Migration | Migrate remaining users with intensive support | 2025-05-17 | 2025-05-26 | 10 days | P5.2 | Migration Team | Completed | Wave 3 Migration, Full User Base | Support capacity | Enhanced support coverage
Phase 5: Migration Execution | P5.4 - Data Migration | Complete data migration and validation for all users | 2025-05-24 | 2025-06-02 | 10 days | P5.3 | Data Engineer | Completed | Data Migration, Validation Report | Data integrity | Comprehensive validation
Phase 5: Migration Execution | P5.5 - Legacy Decommission | Decommission legacy collaboration systems | 2025-05-31 | 2025-06-09 | 10 days | P5.4 | Decommission Manager | Completed | Legacy System Shutdown, Archive Procedures | System dependencies | Thorough dependency analysis
Phase 6: Optimization and Support | P6.1 - User Adoption Support | Intensive user adoption support and troubleshooting | 2025-06-07 | 2025-06-16 | 10 days | P5.5 | Adoption Manager | Completed | Adoption Support, User Success | Adoption challenges | Proactive user support
Phase 6: Optimization and Support | P6.2 - Performance Optimization | Optimize system performance and user experience | 2025-06-14 | 2025-06-23 | 10 days | P6.1 | Performance Engineer | Completed | Performance Optimization, Tuning Report | Performance issues | Continuous monitoring
Phase 6: Optimization and Support | P6.3 - Advanced Training | Deliver advanced training for power users and administrators | 2025-06-21 | 2025-06-30 | 10 days | P6.2 | Advanced Trainer | Completed | Advanced Training, Power User Certification | Training complexity | Hands-on training labs
Phase 6: Optimization and Support | P6.4 - Integration Enhancement | Enhance and optimize enterprise application integrations | 2025-06-28 | 2025-07-07 | 10 days | P6.3 | Integration Specialist | Completed | Integration Enhancements, API Optimization | Integration stability | Thorough testing protocols
Phase 6: Optimization and Support | P6.5 - Success Measurement | Measure project success and document lessons learned | 2025-07-05 | 2025-07-14 | 10 days | P6.4 | Success Manager | Completed | Success Report, Lessons Learned | Metric accuracy | Comprehensive measurement framework
Ongoing Operations | O1 - User Support | Ongoing user support and help desk operations | 2025-07-16 | Ongoing | Continuous | P6.5 | Support Team | Active | Support Reports | Support quality | Continuous improvement
Ongoing Operations | O2 - System Administration | Ongoing Google Workspace administration and maintenance | 2025-07-16 | Ongoing | Continuous | P6.5 | Admin Team | Active | Admin Reports | System stability | Proactive monitoring
Ongoing Operations | O3 - Security Monitoring | Continuous security monitoring and compliance management | 2025-07-16 | Ongoing | Continuous | P6.5 | Security Team | Active | Security Reports | Security threats | 24/7 monitoring
Ongoing Operations | O4 - Training Programs | Ongoing training and skill development programs | 2025-07-16 | Ongoing | Continuous | P6.5 | Training Team | Active | Training Reports | Skill gaps | Continuous learning
Ongoing Operations | O5 - Platform Evolution | Continuous platform enhancement and feature adoption | 2025-07-16 | Ongoing | Continuous | P6.5 | Platform Team | Active | Evolution Reports | Technology changes | Regular roadmap reviews