## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Workspace
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Category | Requirement ID | Requirement Title | Description | Priority | Source | Business Justification | Acceptance Criteria | Test Method | Status | Owner | Dependencies
Platform Foundation | PLT-001 | Google Workspace Tenant Setup | Configure Google Workspace enterprise tenant with administrative controls | High | Platform Requirements | Establish foundation for enterprise collaboration and productivity | Workspace tenant configured with 2500+ user capacity | Platform Testing | Implemented | Workspace Administrator | Google Partnership
Platform Foundation | PLT-002 | Domain Verification | Configure and verify corporate domain for Google Workspace | High | Identity Requirements | Enable corporate email addresses and maintain brand consistency | Corporate domain verified with email routing configured | Domain Testing | Implemented | DNS Administrator | Domain Management
Platform Foundation | PLT-003 | Organizational Units | Configure organizational units for department and role-based management | High | User Management | Enable structured user management and policy application | Organizational units configured matching corporate structure | OU Testing | Implemented | User Administrator | Corporate Structure
Platform Foundation | PLT-004 | Administrative Roles | Configure administrative roles and delegated administration | High | Access Management | Enable appropriate administrative access and responsibility delegation | Admin roles configured with principle of least privilege | Admin Testing | Implemented | Access Manager | Role Definition
Platform Foundation | PLT-005 | Licensing Management | Configure user licensing and automatic license assignment | Medium | Cost Management | Optimize licensing costs and ensure appropriate feature access | License management with automatic assignment and optimization | License Testing | Implemented | License Manager | User Provisioning
Identity and Authentication | AUTH-001 | Single Sign-On Integration | Integrate Google Workspace with corporate Active Directory via SAML SSO | High | Identity Management | Enable seamless authentication with corporate credentials | SSO integration with 99% authentication success rate | SSO Testing | Implemented | Identity Engineer | Active Directory
Identity and Authentication | AUTH-002 | Directory Synchronization | Configure Google Cloud Directory Sync with Active Directory | High | User Provisioning | Automate user provisioning and maintain identity consistency | Directory sync with automated user provisioning and updates | Sync Testing | Implemented | Directory Engineer | SSO Integration
Identity and Authentication | AUTH-003 | Multi-Factor Authentication | Implement mandatory multi-factor authentication for all users | High | Security Requirements | Enhance account security and prevent unauthorized access | MFA implemented with 100% user enrollment | MFA Testing | Implemented | Security Administrator | Identity Platform
Identity and Authentication | AUTH-004 | Password Policies | Configure corporate password policies and complexity requirements | Medium | Security Governance | Ensure password security aligns with corporate standards | Password policies enforced with complexity requirements | Policy Testing | Implemented | Policy Manager | Identity Management
Identity and Authentication | AUTH-005 | Session Management | Configure session timeout and concurrent session controls | Medium | Security Controls | Manage user sessions and prevent unauthorized access | Session management with appropriate timeout and controls | Session Testing | Implemented | Session Manager | Authentication Platform
Email and Communication | EMAIL-001 | Gmail Enterprise Configuration | Configure Gmail with enterprise features and security controls | High | Email Requirements | Provide secure and feature-rich email platform | Gmail configured with advanced security and compliance features | Email Testing | Implemented | Email Administrator | Platform Setup
Email and Communication | EMAIL-002 | Email Security Controls | Implement advanced email security including DLP and ATP | High | Email Security | Protect against email threats and data leakage | Email security with 99.8% threat detection accuracy | Security Testing | Implemented | Email Security Engineer | Security Framework
Email and Communication | EMAIL-003 | Email Migration | Migrate existing email data and archives to Gmail | High | Data Migration | Preserve email history and ensure business continuity | Email migration with zero data loss and minimal downtime | Migration Testing | Implemented | Migration Engineer | Email Platform
Email and Communication | EMAIL-004 | Distribution Lists | Configure distribution lists and group management | Medium | Communication Management | Enable efficient group communication and management | Distribution lists configured with automated management | List Testing | Implemented | Communication Manager | User Management
Email and Communication | EMAIL-005 | Email Archiving | Configure email archiving and retention policies | High | Compliance Requirements | Meet regulatory requirements for email retention | Email archiving with automated retention and eDiscovery | Archive Testing | Implemented | Compliance Officer | Legal Requirements
Collaboration Tools | COLLAB-001 | Google Drive Enterprise | Configure Google Drive with enterprise storage and sharing controls | High | File Storage | Provide secure cloud storage with collaboration capabilities | Google Drive configured with unlimited storage and security controls | Drive Testing | Implemented | Storage Administrator | Security Policies
Collaboration Tools | COLLAB-002 | Real-Time Document Editing | Enable real-time collaborative editing for documents, sheets, and slides | High | Collaboration Requirements | Enable simultaneous collaboration and reduce version conflicts | Real-time editing with conflict resolution and version history | Collaboration Testing | Implemented | Collaboration Engineer | Document Platform
Collaboration Tools | COLLAB-003 | Sharing and Permissions | Configure granular sharing permissions and external sharing controls | High | Data Governance | Control data access and prevent unauthorized sharing | Sharing controls with granular permissions and audit trails | Sharing Testing | Implemented | Data Governance Officer | Security Framework
Collaboration Tools | COLLAB-004 | Team Drives | Configure shared drives for team collaboration and project management | Medium | Team Collaboration | Enable structured team collaboration and file organization | Team drives configured with appropriate access controls | Team Drive Testing | Implemented | Team Coordinator | Drive Platform
Collaboration Tools | COLLAB-005 | Offline Access | Configure offline access and synchronization capabilities | Medium | Mobile Productivity | Enable productivity during connectivity issues | Offline access with automatic synchronization upon reconnection | Offline Testing | Implemented | Mobile Engineer | Sync Platform
Video Conferencing | VIDEO-001 | Google Meet Enterprise | Configure Google Meet with enterprise features and controls | High | Video Communication | Provide secure and scalable video conferencing platform | Google Meet configured with advanced features and security | Video Testing | Implemented | Video Administrator | Communication Platform
Video Conferencing | VIDEO-002 | Meeting Recording | Configure automatic meeting recording and transcription | Medium | Knowledge Management | Capture meeting content for future reference and compliance | Meeting recording with automatic transcription and storage | Recording Testing | Implemented | Recording Manager | Storage Integration
Video Conferencing | VIDEO-003 | Calendar Integration | Integrate video conferencing with Google Calendar | High | Scheduling Integration | Enable seamless meeting scheduling and joining | Calendar integration with one-click meeting join | Calendar Testing | Implemented | Calendar Administrator | Meeting Platform
Video Conferencing | VIDEO-004 | External Guest Access | Configure secure external guest access for meetings | Medium | External Collaboration | Enable collaboration with external partners and customers | External access with security controls and guest management | Guest Testing | Implemented | Guest Manager | Security Controls
Video Conferencing | VIDEO-005 | Room Systems Integration | Integrate conference room systems with Google Meet | Medium | Room Technology | Enable seamless room-based video conferencing | Room systems integrated with Google Meet platform | Room Testing | Implemented | Room Engineer | AV Systems
Mobile Device Management | MDM-001 | Mobile Device Policies | Configure mobile device management policies and controls | High | Mobile Security | Secure corporate data on mobile devices | MDM policies configured with device compliance requirements | MDM Testing | Implemented | Mobile Administrator | Security Policies
Mobile Device Management | MDM-002 | App Management | Configure mobile app management and distribution | High | App Security | Control app access and prevent data leakage | App management with controlled distribution and security | App Testing | Implemented | App Manager | Mobile Platform
Mobile Device Management | MDM-003 | Device Compliance | Implement device compliance checking and enforcement | High | Compliance Requirements | Ensure mobile devices meet security standards | Device compliance with automated enforcement | Compliance Testing | Implemented | Compliance Engineer | Security Framework
Mobile Device Management | MDM-004 | Remote Wipe Capability | Configure remote wipe capabilities for lost or stolen devices | High | Data Protection | Protect corporate data on compromised devices | Remote wipe capability with immediate execution | Wipe Testing | Implemented | Security Engineer | Device Management
Mobile Device Management | MDM-005 | BYOD Support | Configure bring-your-own-device support and policies | Medium | Device Strategy | Enable personal device usage while maintaining security | BYOD support with appropriate security controls | BYOD Testing | Implemented | BYOD Manager | Device Policies
Security and Compliance | SEC-001 | Data Loss Prevention | Implement comprehensive data loss prevention policies | High | Data Protection | Prevent unauthorized data disclosure and maintain compliance | DLP policies with automated detection and prevention | DLP Testing | Implemented | DLP Administrator | Security Platform
Security and Compliance | SEC-002 | Advanced Threat Protection | Configure advanced threat protection for email and files | High | Threat Protection | Protect against advanced threats and malware | ATP with 99.9% threat detection and blocking | ATP Testing | Implemented | Threat Engineer | Security Infrastructure
Security and Compliance | SEC-003 | Security Monitoring | Implement security monitoring and alerting | High | Security Operations | Monitor security events and respond to incidents | Security monitoring with real-time alerting and response | Monitoring Testing | Implemented | Security Analyst | Monitoring Platform
Security and Compliance | SEC-004 | Audit Logging | Configure comprehensive audit logging and retention | High | Audit Requirements | Provide audit trails for compliance and investigation | Audit logging with comprehensive coverage and retention | Audit Testing | Implemented | Audit Engineer | Compliance Framework
Security and Compliance | SEC-005 | Encryption Controls | Implement encryption for data at rest and in transit | High | Data Encryption | Protect sensitive data through comprehensive encryption | Encryption implemented with appropriate key management | Encryption Testing | Implemented | Encryption Engineer | Security Infrastructure
Integration and APIs | INT-001 | Enterprise Application Integration | Integrate Google Workspace with existing enterprise applications | High | System Integration | Enable seamless workflow between Google Workspace and enterprise systems | Enterprise integration with SSO and data synchronization | Integration Testing | Implemented | Integration Engineer | API Framework
Integration and APIs | INT-002 | CRM Integration | Integrate with customer relationship management systems | Medium | Business Process | Enable CRM data access within collaboration workflows | CRM integration with data synchronization and workflow | CRM Testing | Implemented | CRM Engineer | API Platform
Integration and APIs | INT-003 | ERP Integration | Integrate with enterprise resource planning systems | Medium | Business Systems | Enable ERP data access and workflow integration | ERP integration with appropriate data access and security | ERP Testing | Implemented | ERP Engineer | Integration Platform
Integration and APIs | INT-004 | Business Intelligence Integration | Integrate with business intelligence and analytics platforms | Medium | Data Analytics | Enable data-driven insights within collaboration platform | BI integration with dashboard and reporting capabilities | BI Testing | Implemented | BI Engineer | Analytics Platform
Integration and APIs | INT-005 | Workflow Automation | Implement workflow automation using Google Apps Script | Medium | Process Automation | Automate repetitive business processes and workflows | Workflow automation with 80% process automation coverage | Automation Testing | Implemented | Automation Engineer | Scripting Platform
Training and Adoption | TRAIN-001 | User Training Program | Develop comprehensive user training program for Google Workspace | High | User Enablement | Ensure users can effectively utilize Google Workspace features | Training program with 90% user completion rate | Training Assessment | Implemented | Training Manager | Content Development
Training and Adoption | TRAIN-002 | Administrator Training | Provide specialized training for Google Workspace administrators | High | Admin Enablement | Ensure administrators can effectively manage the platform | Administrator training with certification completion | Admin Assessment | Implemented | Admin Trainer | Platform Knowledge
Training and Adoption | TRAIN-003 | Change Management | Implement comprehensive change management program | High | Adoption Success | Ensure successful user adoption and minimize resistance | Change management with 85% successful adoption rate | Adoption Measurement | Implemented | Change Manager | User Psychology
Training and Adoption | TRAIN-004 | Support Documentation | Create comprehensive support documentation and resources | Medium | User Support | Provide self-service support resources for users | Support documentation with 90% user issue resolution | Documentation Testing | Implemented | Documentation Manager | Knowledge Base
Training and Adoption | TRAIN-005 | Champion Network | Establish power user champion network for peer support | Medium | Peer Support | Enable peer-to-peer support and knowledge sharing | Champion network with active participation and support | Champion Effectiveness | Implemented | Champion Coordinator | User Community