## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Multi Cloud Platform
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Description | Acceptance Criteria | Source | Owner | Status | Dependencies | Test Method | Compliance | Notes | Estimated Effort
REQ-001 | Platform | Terraform Enterprise | Critical | Deploy Terraform Enterprise with workspace management | TFE cluster with 500+ workspace capacity and state management | Platform Team | HashiCorp Team | Draft | Infrastructure provisioning | Platform testing | HashiCorp licensing | Infrastructure as Code at scale | 64 hours
REQ-002 | Security | Vault Enterprise | Critical | Deploy Vault Enterprise for secrets management | HA Vault cluster with auto-unsealing and encryption | Security Team | HashiCorp Team | Draft | Security infrastructure | Security testing | Security compliance | Centralized secrets management | 72 hours
REQ-003 | Network | Consul Enterprise | High | Deploy Consul for service mesh and discovery | Multi-datacenter Consul with service mesh and Connect | Network Team | Platform Team | Draft | Network infrastructure | Service testing | Service mesh | Microservices connectivity | 56 hours
REQ-004 | Platform | Nomad Enterprise | Medium | Deploy Nomad for container orchestration | Nomad cluster with multi-region federation and ACLs | Platform Team | DevOps Team | Draft | REQ-003 | Orchestration testing | Container management | Alternative to Kubernetes | 48 hours
REQ-005 | Multi-Cloud | Cloud Integration | High | Configure multi-cloud providers (AWS Azure GCP) | Terraform providers with cross-cloud networking and policies | Cloud Team | Platform Team | Draft | Cloud accounts | Multi-cloud testing | Cloud portability | Avoid vendor lock-in | 80 hours
REQ-006 | Security | Policy as Code | High | Implement Sentinel policies for governance | Policy enforcement for security compliance and cost control | Governance Team | Security Team | Draft | REQ-002 | Policy testing | Governance compliance | Automated policy enforcement | 52 hours
REQ-007 | CI/CD | Pipeline Integration | Medium | Integrate with existing CI/CD pipelines | Automated infrastructure deployment via GitOps workflows | DevOps Team | Platform Team | Draft | CI/CD systems | Pipeline testing | Automation workflow | Infrastructure automation | 44 hours
REQ-008 | Operations | Monitoring and Logging | Medium | Deploy comprehensive platform monitoring | Centralized logging and metrics for all HashiCorp tools | Operations Team | Monitoring Team | Draft | Monitoring infrastructure | Monitoring validation | Operational visibility | Platform observability | 40 hours
REQ-009 | Compliance | Audit and Compliance | High | Implement audit logging and compliance reporting | Comprehensive audit trails with regulatory compliance | Compliance Team | Security Team | Draft | REQ-006 | Compliance validation | Regulatory audit | SOC2 and compliance frameworks | 36 hours
REQ-010 | Training | Platform Training | Medium | Provide HashiCorp platform training for teams | Training programs for 100+ engineers on HashiCorp stack | Training Team | Platform Team | Draft | Training materials | Training assessment | Knowledge transfer | Platform adoption enablement | 56 hours