## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Terraform Enterprise
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Format | Success Metrics
Project Kickoff | All Stakeholders | One-time | Town Hall Meeting | Project Manager | Project overview, HashiCorp strategy, timeline, team roles | Presentation and Q&A | 100% stakeholder attendance
Weekly Sprint Updates | Development Teams | Weekly | Slack/Email | Scrum Master | Sprint progress, module development, blockers, upcoming deliverables | Agile status update | 95% team engagement
Executive Dashboard | C-Level Executives | Bi-weekly | Executive Portal | Program Manager | Platform adoption, cost savings, risk status, milestone progress | Executive dashboard | Executive satisfaction >4.0
Architecture Reviews | Technical Leads | Weekly | Architecture Committee | Solution Architect | Module designs, policy frameworks, integration patterns, security reviews | Technical documentation | Architecture approval <48 hours
HashiCorp Collaboration | HashiCorp Partners | Monthly | Partner Meetings | Technical Lead | Platform optimization, roadmap alignment, support escalations, best practices | Partnership review | Partner satisfaction >95%
Infrastructure Teams | Engineering Teams | Bi-weekly | Engineering Forums | Platform Engineer | Platform capabilities, new modules, training opportunities, best practices | Technical workshops | Knowledge transfer >85%
Policy and Governance | Compliance Team | Monthly | Governance Committee | Compliance Officer | Policy updates, compliance status, audit preparations, control effectiveness | Governance dashboard | Compliance score >98%
Cost Management | Finance Team | Monthly | Financial Reviews | FinOps Manager | Cost analysis, budget performance, optimization opportunities, ROI metrics | Financial dashboard | Budget variance <3%
User Training | End Users | Ongoing | Learning Platform | Training Manager | Terraform skills, platform features, certification paths, hands-on labs | Training portal | Certification rate >80%
Platform Operations | Operations Team | Daily | Operations Channel | Platform Administrator | Platform health, performance metrics, incidents, maintenance activities | Operations dashboard | SLA compliance >99.5%
Change Communications | All Users | As needed | Platform Notifications | Change Manager | Platform updates, new features, maintenance windows, policy changes | Notification system | User awareness >95%
Security Updates | Security Team | Weekly | Security Committee | Security Engineer | Security assessments, vulnerability reports, policy compliance, threat intelligence | Security briefing | Security posture >95%
Module Development | Module Authors | Weekly | Developer Community | Module Lead | Module standards, code reviews, testing requirements, publication guidelines | Developer portal | Module quality >90%
Vendor Management | Procurement Team | Quarterly | Vendor Reviews | Vendor Manager | License management, contract performance, renewal planning, cost optimization | Vendor scorecard | Vendor performance >95%
Risk Management | Risk Committee | Monthly | Risk Reviews | Risk Manager | Risk assessments, mitigation strategies, incident analysis, control effectiveness | Risk dashboard | Risk score <Medium
Business Value | Business Sponsors | Quarterly | Business Reviews | Business Analyst | Value realization, productivity metrics, cost savings, strategic alignment | Business value report | Value target achievement >90%
Technical Deep Dives | Engineering Community | Bi-weekly | Tech Talks | Subject Matter Expert | Advanced patterns, troubleshooting, optimization techniques, emerging practices | Technical sessions | Knowledge sharing >85%
Compliance Audits | Audit Team | Quarterly | Audit Sessions | Compliance Manager | Control testing, evidence collection, compliance validation, remediation plans | Audit documentation | Audit findings <5 per quarter
Innovation Showcase | Innovation Teams | Monthly | Innovation Labs | Innovation Lead | New capabilities, experimental features, proof of concepts, technology trends | Innovation demos | Innovation adoption >70%
Customer Success | Business Users | Quarterly | Success Reviews | Customer Success Manager | Usage analytics, success metrics, improvement opportunities, expansion plans | Success scorecard | Customer satisfaction >4.5
Incident Management | All Stakeholders | As needed | Incident Bridge | Incident Commander | Incident status, impact assessment, resolution progress, preventive measures | Incident portal | Resolution time <SLA
Knowledge Sharing | Technical Community | Monthly | Knowledge Base | Knowledge Manager | Best practices, lessons learned, troubleshooting guides, FAQs | Knowledge articles | Knowledge base usage >80%