## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Terraform Enterprise
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Category | Requirement ID | Requirement Title | Description | Priority | Source | Business Justification | Acceptance Criteria | Test Method | Status | Owner | Dependencies
Platform Foundation | PLT-001 | Terraform Enterprise Installation | Deploy Terraform Enterprise platform with high availability configuration | High | Infrastructure Strategy | Enable centralized infrastructure automation and collaboration | TFE installed with 99.9% uptime and disaster recovery | Platform Testing | Implemented | Platform Engineer | Infrastructure Setup
Platform Foundation | PLT-002 | Multi-Cloud Provider Support | Support AWS, Azure, GCP, and VMware vSphere providers | High | Multi-Cloud Strategy | Enable consistent automation across all cloud platforms | All major cloud providers configured and tested | Provider Testing | Implemented | Cloud Engineer | Platform Installation
Platform Foundation | PLT-003 | Workspace Management | Implement organized workspace structure for teams and environments | High | Team Collaboration | Enable team-based infrastructure management with proper isolation | 180+ workspaces organized by team and environment | Workspace Testing | Implemented | Workspace Manager | Access Controls
Platform Foundation | PLT-004 | State Management | Centralized state management with encryption and backup | High | Security Requirements | Ensure infrastructure state is secure and recoverable | Centralized state with encryption and automated backup | State Testing | Implemented | State Engineer | Security Framework
Platform Foundation | PLT-005 | Private Module Registry | Private registry for reusable infrastructure modules | High | Code Reusability | Enable module sharing and standardization across teams | 85+ modules published with versioning and documentation | Registry Testing | Implemented | Registry Engineer | Module Development
Authentication and Authorization | AUTH-001 | SSO Integration | Integration with corporate Active Directory for single sign-on | High | Identity Management | Enable seamless user authentication with corporate credentials | SSO integration with 99% authentication success rate | Authentication Testing | Implemented | Identity Engineer | Platform Setup
Authentication and Authorization | AUTH-002 | Role-Based Access Control | Granular RBAC with team and workspace-level permissions | High | Security Governance | Ensure users have appropriate access based on roles | RBAC implemented with principle of least privilege | Access Testing | Implemented | Security Engineer | SSO Integration
Authentication and Authorization | AUTH-003 | Service Account Management | Service accounts for automated integrations and CI/CD | High | Automation Security | Enable secure automation without user credentials | Service accounts with rotation and audit capabilities | Service Account Testing | Implemented | Automation Engineer | RBAC Setup
Authentication and Authorization | AUTH-004 | API Access Control | API authentication and authorization for programmatic access | High | API Security | Secure API access for external integrations | API access with OAuth 2.0 and rate limiting | API Security Testing | Implemented | API Engineer | Service Accounts
Authentication and Authorization | AUTH-005 | Audit Logging | Comprehensive audit logging for all platform activities | High | Compliance Requirements | Provide audit trail for compliance and security investigations | Complete audit trail with user and API activity logging | Audit Testing | Implemented | Audit Engineer | Platform Setup
Version Control Integration | VCS-001 | GitLab Integration | Integration with GitLab for infrastructure code management | High | Code Management | Enable Git-based workflow for infrastructure changes | GitLab integration with automated plan and apply | Integration Testing | Implemented | VCS Engineer | Platform Setup
Version Control Integration | VCS-002 | GitHub Integration | Support for GitHub repositories and workflows | Medium | Developer Preference | Support teams using GitHub for version control | GitHub integration with webhook automation | GitHub Testing | Implemented | Integration Engineer | VCS Framework
Version Control Integration | VCS-003 | Bitbucket Integration | Integration with Atlassian Bitbucket for enterprise teams | Medium | Enterprise Tools | Support existing Bitbucket infrastructure | Bitbucket integration with automated triggers | Bitbucket Testing | Implemented | Integration Specialist | VCS Framework
Version Control Integration | VCS-004 | Branch Protection | Implement branch protection and approval workflows | High | Code Quality | Ensure infrastructure changes go through proper review | Branch protection with required reviews and status checks | Branch Testing | Implemented | Workflow Engineer | VCS Integration
Version Control Integration | VCS-005 | Webhook Automation | Automated triggers for plan and apply operations | High | Automation Requirements | Enable automated infrastructure deployment workflows | Webhooks triggering plans within 30 seconds | Webhook Testing | Implemented | Automation Engineer | VCS Integration
Policy and Governance | POL-001 | Sentinel Policy Engine | Implement Sentinel policies for governance and compliance | High | Governance Requirements | Automate policy enforcement for infrastructure compliance | 45+ Sentinel policies with 100% enforcement | Policy Testing | Implemented | Policy Engineer | Platform Setup
Policy and Governance | POL-002 | Security Policies | Security policies for infrastructure hardening and compliance | High | Security Requirements | Enforce security best practices across all infrastructure | Security policies with automated enforcement | Security Testing | Implemented | Security Policy Engineer | Sentinel Setup
Policy and Governance | POL-003 | Cost Control Policies | Policies for cost optimization and budget enforcement | High | Cost Management | Prevent cost overruns through automated policy enforcement | Cost policies with budget alerts and controls | Cost Testing | Implemented | FinOps Engineer | Policy Framework
Policy and Governance | POL-004 | Compliance Policies | Regulatory compliance policies for SOC 2, ISO 27001 | High | Compliance Requirements | Ensure infrastructure meets regulatory requirements | Compliance policies with automated validation | Compliance Testing | Implemented | Compliance Engineer | Security Policies
Policy and Governance | POL-005 | Custom Policy Development | Framework for developing organization-specific policies | Medium | Custom Governance | Enable custom policy development for unique requirements | Custom policy framework with testing and deployment | Custom Policy Testing | Implemented | Custom Policy Developer | Sentinel Framework
Module Development | MOD-001 | AWS Module Library | Comprehensive library of AWS infrastructure modules | High | AWS Strategy | Accelerate AWS infrastructure deployment with reusable modules | 85+ AWS modules covering all common use cases | Module Testing | Implemented | AWS Module Developer | Registry Setup
Module Development | MOD-002 | Azure Module Library | Comprehensive library of Azure infrastructure modules | High | Azure Strategy | Accelerate Azure infrastructure deployment with standardized modules | 75+ Azure modules with complete documentation | Azure Testing | Implemented | Azure Module Developer | Registry Platform
Module Development | MOD-003 | GCP Module Library | Google Cloud Platform infrastructure modules | High | GCP Strategy | Enable rapid GCP deployment with tested modules | 60+ GCP modules with version management | GCP Testing | Implemented | GCP Module Developer | Registry Platform
Module Development | MOD-004 | Module Testing Framework | Automated testing framework for infrastructure modules | High | Quality Assurance | Ensure all modules are tested and validated before publication | Automated testing with 95% code coverage | Testing Framework Validation | Implemented | Test Engineer | Module Development
Module Development | MOD-005 | Module Documentation | Comprehensive documentation for all infrastructure modules | High | User Experience | Enable easy adoption and usage of infrastructure modules | Complete documentation with examples and best practices | Documentation Review | Implemented | Documentation Engineer | Module Development
Workflow Automation | WF-001 | Automated Planning | Automated Terraform plan generation and review workflows | High | Automation Requirements | Streamline infrastructure change review and approval process | Automated plans with approval workflows | Workflow Testing | Implemented | Workflow Engineer | VCS Integration
Workflow Automation | WF-002 | Approval Workflows | Multi-stage approval workflows for infrastructure changes | High | Change Management | Ensure appropriate approval for infrastructure modifications | Approval workflows with configurable rules | Approval Testing | Implemented | Approval Engineer | Policy Framework
Workflow Automation | WF-003 | Automated Apply | Automated infrastructure deployment after approvals | High | Deployment Automation | Enable rapid deployment of approved infrastructure changes | Automated apply with rollback capabilities | Apply Testing | Implemented | Deploy Engineer | Approval Workflows
Workflow Automation | WF-004 | Notification System | Automated notifications for workflow events and status | Medium | Communication Requirements | Keep stakeholders informed of infrastructure change status | Notification system with configurable rules | Notification Testing | Implemented | Notification Engineer | Workflow Setup
Workflow Automation | WF-005 | Rollback Capabilities | Automated rollback for failed deployments | High | Risk Management | Quickly recover from failed infrastructure deployments | Rollback procedures with 15-minute recovery time | Rollback Testing | Implemented | Rollback Engineer | Workflow Framework
Integration and APIs | API-001 | RESTful API Access | Comprehensive REST API for platform integration | High | Integration Requirements | Enable programmatic access for external tools and automation | REST API with complete coverage of platform capabilities | API Testing | Implemented | API Developer | Platform Setup
Integration and APIs | API-002 | CI/CD Integration | Integration with Jenkins, GitLab CI, and Azure DevOps | High | DevOps Integration | Enable infrastructure automation within existing CI/CD pipelines | CI/CD integration with automated deployment pipelines | Pipeline Testing | Implemented | Pipeline Engineer | API Framework
Integration and APIs | API-003 | Monitoring Integration | Integration with monitoring and alerting systems | High | Operations Requirements | Enable monitoring of infrastructure automation activities | Monitoring integration with alerting and dashboards | Monitoring Testing | Implemented | Monitoring Engineer | API Platform
Integration and APIs | API-004 | ITSM Integration | Integration with IT Service Management tools | Medium | Process Integration | Integrate infrastructure changes with ITIL processes | ITSM integration with change management workflows | ITSM Testing | Implemented | ITSM Engineer | API Framework
Integration and APIs | API-005 | Webhook Framework | Webhook framework for event-driven integrations | Medium | Event Integration | Enable event-driven automation and notifications | Webhook framework with configurable event triggers | Webhook Testing | Implemented | Webhook Engineer | API Platform
Cost Management | COST-001 | Cost Estimation | Automated cost estimation for infrastructure changes | High | Financial Management | Provide cost visibility before infrastructure deployment | Cost estimation with 90% accuracy | Cost Testing | Implemented | Cost Engineer | Platform Setup
Cost Management | COST-002 | Budget Controls | Budget controls and alerts for workspace spending | High | Budget Management | Prevent cost overruns through automated budget enforcement | Budget controls with automated alerts | Budget Testing | Implemented | Budget Manager | Cost Framework
Cost Management | COST-003 | Cost Allocation | Cost allocation and chargeback to teams and projects | Medium | Financial Governance | Enable accurate cost attribution and chargeback | Cost allocation with team-level granularity | Allocation Testing | Implemented | Allocation Analyst | Cost Monitoring
Cost Management | COST-004 | Optimization Recommendations | Automated recommendations for cost optimization | Medium | Cost Optimization | Identify opportunities for infrastructure cost reduction | Optimization recommendations with 25% potential savings | Optimization Testing | Implemented | Optimization Engineer | Cost Analysis
Cost Management | COST-005 | Financial Reporting | Comprehensive financial reporting and dashboards | Medium | Financial Visibility | Provide executive visibility into infrastructure spending | Financial dashboards with real-time cost metrics | Reporting Testing | Implemented | Reporting Analyst | Cost Framework
Security and Compliance | SEC-001 | Encryption Implementation | Encryption at rest and in transit for all platform data | High | Security Requirements | Protect sensitive infrastructure data and credentials | End-to-end encryption with key management | Encryption Testing | Implemented | Security Engineer | Platform Setup
Security and Compliance | SEC-002 | Secret Management | Integration with HashiCorp Vault for credential management | High | Credential Security | Secure management of infrastructure credentials | Vault integration with automated credential rotation | Secret Testing | Implemented | Vault Engineer | Security Framework
Security and Compliance | SEC-003 | Network Security | Network segmentation and firewall controls | High | Network Security | Ensure secure network communication for platform | Network security with private connectivity | Network Testing | Implemented | Network Security Engineer | Platform Infrastructure
Security and Compliance | SEC-004 | Vulnerability Scanning | Automated vulnerability scanning and remediation | High | Security Operations | Identify and remediate security vulnerabilities proactively | Vulnerability scanning with automated reporting | Vulnerability Testing | Implemented | Vulnerability Engineer | Security Monitoring
Security and Compliance | SEC-005 | Compliance Monitoring | Continuous compliance monitoring and reporting | High | Compliance Requirements | Ensure ongoing compliance with regulatory standards | Compliance monitoring with automated reporting | Compliance Testing | Implemented | Compliance Monitor | Security Framework
Monitoring and Observability | MON-001 | Platform Monitoring | Comprehensive monitoring of platform health and performance | High | Operations Requirements | Ensure platform reliability and performance | Platform monitoring with 99.9% uptime alerting | Monitoring Testing | Implemented | Platform Monitor | Platform Setup
Monitoring and Observability | MON-002 | Infrastructure Drift Detection | Automated detection of infrastructure configuration drift | High | Configuration Management | Identify and alert on infrastructure configuration changes | Drift detection with automated alerting | Drift Testing | Implemented | Drift Engineer | Monitoring Platform
Monitoring and Observability | MON-003 | Audit Trail Monitoring | Monitoring and alerting for audit trail activities | High | Security Monitoring | Monitor and alert on suspicious platform activities | Audit monitoring with real-time alerting | Audit Monitoring Testing | Implemented | Audit Monitor | Logging Framework
Monitoring and Observability | MON-004 | Performance Analytics | Analytics for platform performance and usage patterns | Medium | Performance Optimization | Optimize platform performance based on usage analytics | Performance analytics with optimization recommendations | Analytics Testing | Implemented | Analytics Engineer | Monitoring Data
Monitoring and Observability | MON-005 | Custom Dashboards | Customizable dashboards for teams and stakeholders | Medium | User Experience | Provide customized views for different user roles | Custom dashboards with role-based access | Dashboard Testing | Implemented | Dashboard Engineer | Monitoring Platform
Training and Documentation | TRAIN-001 | Technical Documentation | Comprehensive technical documentation and runbooks | High | Knowledge Management | Provide detailed documentation for platform operations | Technical documentation with 95% coverage | Documentation Review | Implemented | Technical Writer | Platform Implementation
Training and Documentation | TRAIN-002 | User Training Program | Comprehensive training program for platform users | High | User Enablement | Ensure users can effectively use the platform | Training program with 85% certification rate | Training Assessment | Implemented | Training Manager | Documentation
Training and Documentation | TRAIN-003 | Administrator Training | Specialized training for platform administrators | High | Admin Enablement | Ensure administrators can effectively manage the platform | Admin training with 95% competency achievement | Admin Assessment | Implemented | Admin Trainer | User Training
Training and Documentation | TRAIN-004 | Best Practices Guide | Best practices guide for infrastructure as code | Medium | Knowledge Sharing | Share IaC best practices across the organization | Best practices guide with regular updates | Best Practices Review | Implemented | Best Practices Author | Training Materials
Training and Documentation | TRAIN-005 | Community Portal | Internal community portal for knowledge sharing | Medium | Collaboration | Enable knowledge sharing and collaboration among users | Community portal with active user participation | Community Metrics | Implemented | Community Manager | Training Platform