## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Openshift Container Platform
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Format | Success Metrics
Project Kickoff | All Stakeholders | One-time | Enterprise Forum | Project Manager | OpenShift strategy, container transformation roadmap, timeline, team roles | Presentation and Q&A | 100% stakeholder attendance
Sprint Reviews | Development Teams | Bi-weekly | Agile Ceremonies | Scrum Master | Sprint progress, application migrations, container development, blockers | Sprint demo and retrospective | 95% team engagement
Executive Dashboard | C-Level Executives | Weekly | Executive Portal | Program Manager | Platform adoption, migration progress, cost savings, risk status | Executive dashboard | Executive satisfaction >4.0
Architecture Reviews | Technical Leads | Weekly | Architecture Committee | Solution Architect | Container designs, microservices patterns, integration architecture, security | Technical documentation | Architecture approval <24 hours
Red Hat Collaboration | Red Hat Partners | Monthly | Partner Meetings | Technical Lead | Platform optimization, roadmap alignment, support escalations, best practices | Partnership review | Partner satisfaction >95%
Development Teams | Engineering Teams | Daily | DevOps Channels | Platform Engineer | Platform capabilities, CI/CD pipelines, deployment automation, troubleshooting | Technical standups | Knowledge transfer >90%
Security Reviews | Security Team | Weekly | Security Committee | Security Architect | Container security, policy enforcement, vulnerability assessments, compliance | Security briefing | Security posture >98%
Application Migration | Product Teams | Bi-weekly | Migration Reviews | Migration Lead | Migration progress, containerization status, testing results, go-live planning | Migration dashboard | Migration success rate >95%
User Training | End Users | Ongoing | Learning Platform | Training Manager | OpenShift skills, container development, CI/CD practices, troubleshooting | Hands-on training | Certification rate >85%
Platform Operations | Operations Team | Daily | Operations Channel | Platform Administrator | Cluster health, performance metrics, incidents, maintenance activities | Operations dashboard | SLA compliance >99.9%
Change Communications | All Users | As needed | Platform Notifications | Change Manager | Platform updates, new features, maintenance windows, policy changes | Notification system | User awareness >95%
Cost Management | Finance Team | Monthly | Financial Reviews | FinOps Manager | Cost analysis, resource utilization, optimization opportunities, ROI metrics | Financial dashboard | Budget variance <5%
Container Development | Developer Community | Weekly | Developer Forums | Developer Advocate | Best practices, troubleshooting, new features, community contributions | Developer portal | Community engagement >80%
Vendor Management | Procurement Team | Quarterly | Vendor Reviews | Vendor Manager | License management, support performance, renewal planning, cost optimization | Vendor scorecard | Vendor performance >95%
Risk Management | Risk Committee | Monthly | Risk Reviews | Risk Manager | Risk assessments, mitigation strategies, incident analysis, control effectiveness | Risk dashboard | Risk score <Medium
Business Value | Business Sponsors | Quarterly | Business Reviews | Business Analyst | Value realization, productivity metrics, cost savings, strategic alignment | Business value report | Value target achievement >90%
Technical Deep Dives | Engineering Community | Bi-weekly | Tech Talks | Subject Matter Expert | Advanced patterns, troubleshooting, optimization techniques, emerging practices | Technical sessions | Knowledge sharing >85%
Compliance Audits | Audit Team | Quarterly | Audit Sessions | Compliance Manager | Control testing, evidence collection, compliance validation, remediation plans | Audit documentation | Audit findings <3 per quarter
Innovation Showcase | Innovation Teams | Monthly | Innovation Labs | Innovation Lead | New capabilities, experimental features, proof of concepts, technology trends | Innovation demos | Innovation adoption >70%
Customer Success | Business Users | Quarterly | Success Reviews | Customer Success Manager | Usage analytics, success metrics, improvement opportunities, expansion plans | Success scorecard | Customer satisfaction >4.5
Incident Management | All Stakeholders | As needed | Incident Bridge | Incident Commander | Incident status, impact assessment, resolution progress, preventive measures | Incident portal | Resolution time <SLA
Knowledge Sharing | Technical Community | Monthly | Knowledge Base | Knowledge Manager | Best practices, lessons learned, troubleshooting guides, container patterns | Knowledge articles | Knowledge base usage >85%