## Cover
Project Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Openshift Container Platform
Customer Name: | Data table for project plan
Version: | 1.0

## Project Plan
Phase | Task | Description | Start Date | End Date | Duration | Dependencies | Assigned To | Status | Deliverables | Risks | Mitigation
Phase 1: Foundation | P1.1 - Project Initiation | Project charter, stakeholder alignment, and Red Hat partnership establishment | 2025-01-02 | 2025-01-08 | 7 days |  | Project Manager | Completed | Project Charter, Partnership Agreement | Resource availability | Early commitment processes
Phase 1: Foundation | P1.2 - Current State Assessment | Assessment of existing application architecture and containerization readiness | 2025-01-06 | 2025-01-15 | 10 days | P1.1 | Application Architect | Completed | Current State Report, Application Inventory | Complex legacy applications | Phased migration strategy
Phase 1: Foundation | P1.3 - Platform Architecture Design | Design OpenShift platform architecture and deployment strategy | 2025-01-13 | 2025-01-22 | 10 days | P1.2 | Solution Architect | Completed | Architecture Design, Deployment Plan | Architecture complexity | Iterative design approach
Phase 1: Foundation | P1.4 - Security Framework Design | Design container security controls and compliance framework | 2025-01-20 | 2025-01-29 | 10 days | P1.3 | Security Architect | Completed | Security Architecture, Policy Framework | Container security complexity | Red Hat security consultation
Phase 1: Foundation | P1.5 - Migration Strategy | Define application migration strategy and containerization approach | 2025-01-27 | 2025-02-05 | 10 days | P1.4 | Migration Lead | Completed | Migration Framework, Containerization Plan | Migration complexity | Pilot application approach
Phase 2: Platform Setup | P2.1 - Infrastructure Provisioning | Provision underlying infrastructure for OpenShift clusters | 2025-02-03 | 2025-02-10 | 8 days | P1.5 | Cloud Engineer | Completed | Cluster Infrastructure, Network Setup | Infrastructure dependencies | Multi-zone deployment
Phase 2: Platform Setup | P2.2 - OpenShift Installation | Install and configure OpenShift Container Platform | 2025-02-08 | 2025-02-15 | 8 days | P2.1 | Platform Engineer | Completed | OCP Installation, Base Configuration | Installation complexity | Red Hat support engagement
Phase 2: Platform Setup | P2.3 - Authentication Integration | Integrate with corporate identity provider and configure RBAC | 2025-02-12 | 2025-02-19 | 8 days | P2.2 | Identity Engineer | Completed | SSO Integration, RBAC Configuration | Identity integration | Identity team collaboration
Phase 2: Platform Setup | P2.4 - Container Registry Setup | Configure integrated container registry and image management | 2025-02-16 | 2025-02-23 | 8 days | P2.3 | Registry Engineer | Completed | Container Registry, Image Policies | Registry complexity | Automated image scanning
Phase 2: Platform Setup | P2.5 - Monitoring and Logging | Deploy monitoring, logging, and alerting stack | 2025-02-20 | 2025-02-27 | 8 days | P2.4 | Monitoring Engineer | Completed | Monitoring Stack, Alert Configuration | Observability coverage | Comprehensive monitoring strategy
Phase 3: DevOps Platform | P3.1 - CI/CD Pipeline Setup | Configure OpenShift Pipelines (Tekton) for automated deployments | 2025-02-24 | 2025-03-05 | 10 days | P2.5 | DevOps Engineer | Completed | CI/CD Pipelines, Automation Framework | Pipeline complexity | Template-based approach
Phase 3: DevOps Platform | P3.2 - GitOps Implementation | Implement GitOps workflows with ArgoCD | 2025-03-03 | 2025-03-12 | 10 days | P3.1 | GitOps Engineer | Completed | GitOps Workflows, ArgoCD Configuration | GitOps adoption | Training and documentation
Phase 3: DevOps Platform | P3.3 - Source Control Integration | Integrate with Git repositories and automated triggers | 2025-03-10 | 2025-03-19 | 10 days | P3.2 | Integration Engineer | Completed | Git Integration, Webhook Configuration | Integration complexity | Multiple repository support
Phase 3: DevOps Platform | P3.4 - Quality Gates | Implement automated testing and quality gates in pipelines | 2025-03-17 | 2025-03-26 | 10 days | P3.3 | QA Engineer | Completed | Testing Framework, Quality Gates | Test automation | Comprehensive test strategy
Phase 3: DevOps Platform | P3.5 - Security Scanning | Integrate container and application security scanning | 2025-03-24 | 2025-04-02 | 10 days | P3.4 | Security Engineer | Completed | Security Scanning, Policy Enforcement | Security integration | Red Hat ACS integration
Phase 4: Application Migration | P4.1 - Pilot Application Selection | Select and prepare pilot applications for containerization | 2025-03-31 | 2025-04-09 | 10 days | P3.5 | Application Lead | Completed | Pilot Application List, Migration Plan | Application complexity | Simple applications first
Phase 4: Application Migration | P4.2 - Containerization Framework | Develop containerization standards and templates | 2025-04-07 | 2025-04-16 | 10 days | P4.1 | Container Engineer | Completed | Container Standards, Base Images | Standardization challenges | Reference architecture approach
Phase 4: Application Migration | P4.3 - Pilot Migration Execution | Execute pilot application migrations to OpenShift | 2025-04-14 | 2025-04-23 | 10 days | P4.2 | Migration Engineer | Completed | Pilot Migrations, Lessons Learned | Migration issues | Comprehensive testing
Phase 4: Application Migration | P4.4 - Production Migration Planning | Plan production application migration waves | 2025-04-21 | 2025-04-30 | 10 days | P4.3 | Migration Planner | Completed | Migration Waves, Risk Assessment | Migration planning | Risk-based prioritization
Phase 4: Application Migration | P4.5 - Migration Automation | Develop automation tools for application migration | 2025-04-28 | 2025-05-07 | 10 days | P4.4 | Automation Engineer | Completed | Migration Tools, Automation Scripts | Automation complexity | Modular automation approach
Phase 5: Production Deployment | P5.1 - Production Environment Preparation | Prepare production OpenShift environment | 2025-05-05 | 2025-05-14 | 10 days | P4.5 | Production Engineer | Completed | Production Environment, Security Hardening | Production readiness | Comprehensive readiness checklist
Phase 5: Production Deployment | P5.2 - Application Migration Waves | Execute production application migration in planned waves | 2025-05-12 | 2025-05-28 | 17 days | P5.1 | Migration Team | Completed | Migrated Applications, Performance Validation | Migration risks | Staged migration approach
Phase 5: Production Deployment | P5.3 - Performance Testing | Comprehensive performance testing of migrated applications | 2025-05-26 | 2025-06-04 | 10 days | P5.2 | Performance Tester | Completed | Performance Test Results, Optimization Plan | Performance issues | Performance baseline validation
Phase 5: Production Deployment | P5.4 - Security Validation | Security testing and compliance validation | 2025-06-02 | 2025-06-11 | 10 days | P5.3 | Security Tester | Completed | Security Test Results, Compliance Report | Security vulnerabilities | Immediate remediation
Phase 5: Production Deployment | P5.5 - User Acceptance Testing | End-user acceptance testing and workflow validation | 2025-06-09 | 2025-06-18 | 10 days | P5.4 | Business Analyst | Completed | UAT Results, User Sign-off | User acceptance | User training enhancement
Phase 6: Go-Live and Support | P6.1 - Go-Live Preparation | Final preparations for production go-live | 2025-06-16 | 2025-06-25 | 10 days | P5.5 | Go-Live Manager | Completed | Go-Live Plan, Rollback Procedures | Go-live risks | Comprehensive contingency planning
Phase 6: Go-Live and Support | P6.2 - Production Go-Live | Execute production go-live with cutover procedures | 2025-06-23 | 2025-07-02 | 10 days | P6.1 | Cutover Manager | Completed | Production Cutover, Success Validation | Cutover complexity | Phased cutover approach
Phase 6: Go-Live and Support | P6.3 - Hypercare Support | Provide intensive support during initial production period | 2025-06-30 | 2025-07-09 | 10 days | P6.2 | Support Team | Completed | Support Documentation, Issue Resolution | Support complexity | 24/7 support coverage
Phase 6: Go-Live and Support | P6.4 - Training Delivery | Deliver comprehensive training for development and operations teams | 2025-07-07 | 2025-07-16 | 10 days | P6.3 | Training Manager | Completed | Training Materials, Certification Program | Training effectiveness | Hands-on training approach
Phase 6: Go-Live and Support | P6.5 - Knowledge Transfer | Transfer platform knowledge to operations and support teams | 2025-07-14 | 2025-07-23 | 10 days | P6.4 | Knowledge Manager | Completed | Knowledge Transfer, Documentation | Knowledge gaps | Structured knowledge transfer
Ongoing Operations | O1 - Platform Operations | Continuous platform monitoring and operational support | 2025-07-25 | Ongoing | Continuous | P6.5 | Operations Team | Active | Operations Reports | Platform issues | Proactive monitoring
Ongoing Operations | O2 - Application Lifecycle | Ongoing application development and deployment support | 2025-07-25 | Ongoing | Continuous | P6.5 | Development Team | Active | Application Updates | Development issues | DevOps automation
Ongoing Operations | O3 - Security Operations | Continuous security monitoring and compliance management | 2025-07-25 | Ongoing | Continuous | P6.5 | Security Operations | Active | Security Reports | Security threats | 24/7 security monitoring
Ongoing Operations | O4 - Platform Evolution | Continuous platform enhancement and technology updates | 2025-07-25 | Ongoing | Continuous | P6.5 | Platform Team | Active | Evolution Reports | Technology obsolescence | Regular technology refresh
Ongoing Operations | O5 - Cost Optimization | Continuous cost monitoring and optimization activities | 2025-07-25 | Ongoing | Continuous | P6.5 | FinOps Team | Active | Cost Reports | Cost overruns | Automated cost controls