## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Ansible Automation Platform
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Format | Success Metrics
Project Kickoff | All Stakeholders | One-time | Operations Forum | Project Manager | Ansible automation strategy, infrastructure transformation, operational efficiency goals | Presentation and Q&A | 100% stakeholder attendance
Automation Updates | Operations Teams | Weekly | Operations Meetings | Automation Lead | Automation progress, playbook development, infrastructure coverage, performance metrics | Operations briefing | 95% team engagement
Executive Dashboard | Leadership Team | Bi-weekly | Executive Portal | Program Manager | Automation adoption, cost savings, efficiency gains, risk reduction | Executive dashboard | Leadership satisfaction >4.0
Technical Reviews | Infrastructure Engineers | Weekly | Technical Committee | Technical Architect | Playbook reviews, automation patterns, integration status, best practices | Technical documentation | Technical approval <24 hours
Red Hat Partnership | Red Hat Teams | Monthly | Partner Meetings | Partnership Manager | Platform optimization, feature updates, support escalations, roadmap alignment | Partnership review | Partner satisfaction >95%
Training Programs | Engineering Teams | Monthly | Training Center | Training Manager | Ansible skills, automation development, best practices, certification programs | Hands-on workshops | Certification rate >80%
Compliance Reviews | Compliance Team | Weekly | Compliance Committee | Compliance Officer | Automated compliance, audit trails, policy enforcement, regulatory alignment | Compliance briefing | Compliance score >98%
Change Management | Change Advisory Board | Bi-weekly | CAB Meetings | Change Manager | Automation changes, risk assessments, approval workflows, impact analysis | Change documentation | Change approval rate >95%
Operations Excellence | Operations Management | Daily | Operations Center | Operations Manager | Automation execution, job status, performance monitoring, incident response | Operations dashboard | SLA compliance >99%
Security Integration | Security Team | Weekly | Security Reviews | Security Engineer | Security automation, credential management, access controls, threat response | Security briefing | Security posture >95%
Performance Analytics | Performance Team | Monthly | Analytics Reviews | Performance Analyst | Automation metrics, efficiency gains, optimization opportunities, trend analysis | Analytics dashboard | Performance target achievement >90%
Vendor Coordination | Vendor Management | Quarterly | Vendor Reviews | Vendor Manager | Platform performance, support quality, contract optimization, strategic alignment | Vendor scorecard | Vendor performance >95%
Knowledge Sharing | Automation Community | Bi-weekly | Community Forums | Community Manager | Best practices, lessons learned, innovation sharing, peer support | Community sessions | Community engagement >85%
Business Value | Business Sponsors | Monthly | Business Reviews | Business Analyst | ROI achievement, business impact, process improvements, strategic alignment | Business dashboard | Value target achievement >90%
Risk Management | Risk Committee | Monthly | Risk Reviews | Risk Manager | Automation risks, mitigation strategies, control effectiveness, incident analysis | Risk dashboard | Risk score <Medium
Incident Communications | All Stakeholders | As needed | Incident Bridge | Incident Commander | Automation incidents, impact assessment, resolution progress, preventive measures | Incident portal | Resolution time <SLA
Training Effectiveness | Learning Team | Quarterly | Learning Reviews | Learning Manager | Training outcomes, skill development, certification progress, knowledge retention | Learning analytics | Learning objectives >85%
Innovation Showcase | Innovation Teams | Quarterly | Innovation Labs | Innovation Lead | Automation innovations, emerging technologies, pilot programs, research projects | Innovation demos | Innovation adoption >70%
Customer Impact | Service Teams | Monthly | Service Reviews | Service Manager | Service improvements, automation benefits, customer satisfaction, service quality | Service metrics | Customer satisfaction >4.5
Audit Preparations | Audit Team | Quarterly | Audit Sessions | Audit Manager | Audit readiness, evidence collection, compliance validation, control testing | Audit documentation | Audit findings <3 per quarter
Capacity Planning | Capacity Team | Monthly | Capacity Reviews | Capacity Manager | Resource utilization, capacity forecasting, scaling requirements, optimization opportunities | Capacity dashboard | Capacity efficiency >85%
Continuous Improvement | Process Team | Monthly | Process Reviews | Process Manager | Process optimization, automation enhancements, efficiency improvements, best practices | Process metrics | Process improvement >10% per quarter