## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Ansible Automation Platform
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Category | Requirement ID | Requirement Title | Description | Priority | Source | Business Justification | Acceptance Criteria | Test Method | Status | Owner | Dependencies
Platform Foundation | PLT-001 | Ansible Automation Platform Installation | Deploy Ansible Automation Platform with high availability configuration | High | Automation Strategy | Enable centralized automation execution and management | AAP installed with 99.9% uptime and clustering | Platform Testing | Implemented | Platform Engineer | Infrastructure Setup
Platform Foundation | PLT-002 | Automation Controller | Configure automation controller with execution environments | High | Execution Requirements | Provide scalable automation execution capabilities | Controller configured with containerized execution environments | Controller Testing | Implemented | Controller Administrator | Platform Installation
Platform Foundation | PLT-003 | Automation Hub | Private automation hub with certified collections | High | Content Management | Centralized automation content repository and distribution | Hub configured with private collections and content sync | Hub Testing | Implemented | Hub Administrator | Platform Setup
Platform Foundation | PLT-004 | Event-Driven Ansible | Event-driven automation for reactive infrastructure management | Medium | Event Automation | Enable automated response to infrastructure events | Event-driven automation with rulebook configuration | Event Testing | Implemented | Event Engineer | Platform Configuration
Platform Foundation | PLT-005 | Automation Mesh | Distributed execution mesh for scalable automation | High | Scalability Requirements | Enable automation across distributed infrastructure | Mesh configured with execution nodes and hop nodes | Mesh Testing | Implemented | Mesh Engineer | Network Infrastructure
Authentication and Authorization | AUTH-001 | LDAP Integration | Integration with corporate LDAP for user authentication | High | Identity Management | Enable corporate authentication and user management | LDAP integration with 99% authentication success rate | Authentication Testing | Implemented | Identity Engineer | LDAP Infrastructure
Authentication and Authorization | AUTH-002 | Role-Based Access Control | Team-based RBAC with granular permissions | High | Access Control | Control access to automation resources based on roles | RBAC implemented with team-based permissions | Access Testing | Implemented | Access Manager | Authentication Setup
Authentication and Authorization | AUTH-003 | API Authentication | Secure API access with token-based authentication | High | API Security | Enable secure programmatic access to platform | API authentication with token management | API Testing | Implemented | API Manager | Platform Setup
Authentication and Authorization | AUTH-004 | Credential Management | Secure credential storage and management | High | Security Requirements | Protect sensitive credentials used in automation | Credential vault with encryption and rotation | Credential Testing | Implemented | Credential Manager | Security Framework
Authentication and Authorization | AUTH-005 | Audit Logging | Comprehensive audit logging for all platform activities | High | Compliance Requirements | Provide audit trail for automation activities | Audit logging with complete activity coverage | Audit Testing | Implemented | Audit Engineer | Platform Setup
Automation Development | AUTO-001 | Playbook Library | Comprehensive library of automation playbooks | High | Automation Content | Provide reusable automation content for common tasks | 450+ playbooks covering infrastructure automation | Playbook Testing | Implemented | Automation Developer | Content Framework
Automation Development | AUTO-002 | Role Collections | Reusable Ansible roles and collections | High | Code Reusability | Enable modular automation development | Role collections with version management | Role Testing | Implemented | Role Developer | Playbook Framework
Automation Development | AUTO-003 | Job Templates | Standardized job templates with survey integration | High | Automation Execution | Provide standardized automation execution templates | Job templates with survey-based input collection | Template Testing | Implemented | Template Engineer | Playbook Library
Automation Development | AUTO-004 | Workflow Templates | Complex workflow orchestration templates | High | Workflow Automation | Enable complex multi-step automation workflows | Workflow templates with conditional logic | Workflow Testing | Implemented | Workflow Engineer | Job Templates
Automation Development | AUTO-005 | Testing Framework | Automated testing framework for infrastructure code | Medium | Quality Assurance | Ensure automation code quality and reliability | Testing framework with Molecule integration | Testing Validation | Implemented | Test Engineer | Development Framework
Infrastructure Automation | INFRA-001 | Server Configuration | Automated server configuration and hardening | High | Infrastructure Management | Standardize server configuration across environments | Server automation with 95% configuration compliance | Configuration Testing | Implemented | Config Engineer | Playbook Library
Infrastructure Automation | INFRA-002 | Application Deployment | Automated application deployment and lifecycle management | High | Application Management | Automate application deployment across environments | Application automation with zero-downtime deployment | Deployment Testing | Implemented | Deployment Engineer | Infrastructure Framework
Infrastructure Automation | INFRA-003 | Database Management | Automated database provisioning and configuration | High | Database Operations | Automate database operations and management | Database automation with automated backup and recovery | Database Testing | Implemented | Database Engineer | Application Framework
Infrastructure Automation | INFRA-004 | Network Configuration | Automated network device configuration | Medium | Network Management | Automate network device configuration and management | Network automation with configuration compliance | Network Testing | Implemented | Network Engineer | Infrastructure Setup
Infrastructure Automation | INFRA-005 | Storage Management | Automated storage provisioning and management | Medium | Storage Operations | Automate storage operations and lifecycle management | Storage automation with capacity management | Storage Testing | Implemented | Storage Engineer | Infrastructure Platform
Cloud Automation | CLOUD-001 | Multi-Cloud Support | Automation across AWS, Azure, and Google Cloud | High | Cloud Strategy | Enable consistent automation across cloud platforms | Multi-cloud automation with provider-specific modules | Cloud Testing | Implemented | Cloud Engineer | Cloud Integration
Cloud Automation | CLOUD-002 | Infrastructure Provisioning | Automated cloud infrastructure provisioning | High | Cloud Operations | Automate cloud resource provisioning and management | Infrastructure automation with Terraform integration | Provisioning Testing | Implemented | Provisioning Engineer | Cloud Platform
Cloud Automation | CLOUD-003 | Auto Scaling | Automated scaling and capacity management | Medium | Resource Optimization | Optimize cloud resource utilization and costs | Auto-scaling automation with cost optimization | Scaling Testing | Implemented | Scaling Engineer | Cloud Infrastructure
Cloud Automation | CLOUD-004 | Backup and Recovery | Automated backup and disaster recovery | High | Data Protection | Ensure data protection and disaster recovery capabilities | Backup automation with automated recovery testing | Backup Testing | Implemented | Backup Engineer | Storage Framework
Cloud Automation | CLOUD-005 | Cost Management | Automated cloud cost monitoring and optimization | Medium | Cost Control | Monitor and optimize cloud infrastructure costs | Cost automation with automated reporting | Cost Testing | Implemented | Cost Engineer | Cloud Management
Security Automation | SEC-001 | Security Hardening | Automated security hardening and compliance | High | Security Requirements | Ensure consistent security configuration across infrastructure | Security automation with 98% compliance achievement | Security Testing | Implemented | Security Engineer | Compliance Framework
Security Automation | SEC-002 | Vulnerability Management | Automated vulnerability scanning and remediation | High | Vulnerability Management | Identify and remediate security vulnerabilities | Vulnerability automation with automated patching | Vulnerability Testing | Implemented | Vulnerability Engineer | Security Platform
Security Automation | SEC-003 | Patch Management | Automated patch deployment and validation | High | System Maintenance | Ensure systems are updated with latest security patches | Patch automation with rollback capabilities | Patch Testing | Implemented | Patch Engineer | Vulnerability Management
Security Automation | SEC-004 | Certificate Management | Automated SSL certificate management | Medium | Certificate Operations | Automate certificate lifecycle management | Certificate automation with automated renewal | Certificate Testing | Implemented | Certificate Engineer | Security Infrastructure
Security Automation | SEC-005 | Access Review | Automated access review and compliance | High | Access Governance | Ensure access permissions are regularly reviewed | Access automation with compliance reporting | Access Testing | Implemented | Access Reviewer | Security Governance
Compliance and Governance | COMP-001 | Change Management Integration | Integration with ServiceNow for change management | High | Change Control | Integrate automation with formal change processes | Change integration with automated change tracking | Change Testing | Implemented | Change Engineer | ITSM Integration
Compliance and Governance | COMP-002 | Compliance Reporting | Automated compliance reporting and documentation | High | Regulatory Compliance | Provide automated compliance reporting capabilities | Compliance automation with regulatory report generation | Compliance Testing | Implemented | Compliance Officer | Audit Framework
Compliance and Governance | COMP-003 | Policy Enforcement | Automated policy enforcement and validation | High | Policy Management | Enforce organizational policies through automation | Policy automation with automated validation | Policy Testing | Implemented | Policy Engineer | Governance Framework
Compliance and Governance | COMP-004 | Evidence Collection | Automated evidence collection for audits | Medium | Audit Support | Automate evidence collection for compliance audits | Evidence automation with audit trail generation | Evidence Testing | Implemented | Evidence Collector | Compliance Platform
Compliance and Governance | COMP-005 | Risk Assessment | Automated risk assessment and reporting | Medium | Risk Management | Automate risk assessment for infrastructure changes | Risk automation with automated risk scoring | Risk Testing | Implemented | Risk Engineer | Governance Platform
Performance and Scalability | PERF-001 | Execution Performance | Optimized automation execution performance | High | Performance Requirements | Ensure automation executes efficiently at scale | Performance optimization with sub-5-minute execution | Performance Testing | Implemented | Performance Engineer | Platform Optimization
Performance and Scalability | PERF-002 | Parallel Execution | Parallel automation execution across multiple targets | High | Scalability Requirements | Enable efficient automation across large infrastructure | Parallel execution with linear scaling performance | Scalability Testing | Implemented | Scalability Engineer | Performance Platform
Performance and Scalability | PERF-003 | Resource Optimization | Automated resource optimization and rightsizing | Medium | Resource Management | Optimize infrastructure resource utilization | Resource automation with optimization recommendations | Resource Testing | Implemented | Resource Engineer | Performance Framework
Performance and Scalability | PERF-004 | Capacity Planning | Automated capacity planning and forecasting | Medium | Capacity Management | Plan infrastructure capacity based on automation data | Capacity automation with predictive analytics | Capacity Testing | Implemented | Capacity Planner | Analytics Platform
Performance and Scalability | PERF-005 | Load Balancing | Automated load balancing and distribution | Medium | Load Management | Distribute automation load across execution nodes | Load balancing with automated failover | Load Testing | Implemented | Load Engineer | Mesh Platform
Monitoring and Analytics | MON-001 | Platform Monitoring | Comprehensive platform monitoring and alerting | High | Operational Requirements | Monitor platform health and performance | Monitoring with real-time dashboards and alerting | Monitoring Testing | Implemented | Monitoring Engineer | Platform Setup
Monitoring and Analytics | MON-002 | Job Analytics | Automation job analytics and performance tracking | Medium | Performance Analytics | Track automation job performance and trends | Analytics with automated performance reporting | Analytics Testing | Implemented | Analytics Engineer | Monitoring Platform
Monitoring and Analytics | MON-003 | Infrastructure Metrics | Infrastructure metrics collection and analysis | Medium | Infrastructure Visibility | Provide visibility into infrastructure performance | Metrics collection with automated analysis | Metrics Testing | Implemented | Metrics Engineer | Monitoring Framework
Monitoring and Analytics | MON-004 | Alerting Framework | Intelligent alerting and escalation procedures | High | Incident Management | Ensure timely response to automation issues | Alerting with intelligent routing and escalation | Alert Testing | Implemented | Alert Engineer | Monitoring Setup
Monitoring and Analytics | MON-005 | Reporting Dashboard | Executive and operational reporting dashboards | Medium | Management Reporting | Provide visibility into automation value and performance | Dashboards with automated report generation | Dashboard Testing | Implemented | Dashboard Engineer | Analytics Platform