## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Srx Firewall Platform
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Category | Requirement ID | Requirement Title | Description | Priority | Source | Business Justification | Acceptance Criteria | Test Method | Status | Owner | Dependencies
Firewall Platform | FW-001 | SRX Series Deployment | Deploy Juniper SRX series next-generation firewalls | High | Security Strategy | Provide advanced threat protection and network security | SRX firewalls deployed with 50Gbps throughput capacity | Platform Testing | Implemented | Firewall Engineer | Infrastructure Setup
Firewall Platform | FW-002 | High Availability Clustering | Implement active-active clustering for high availability | High | Business Continuity | Ensure 99.99% uptime for critical security services | HA clustering with sub-second failover capability | HA Testing | Implemented | Clustering Engineer | Platform Deployment
Firewall Platform | FW-003 | Junos OS Configuration | Configure Junos OS with security-optimized settings | High | Platform Requirements | Provide secure and optimized operating system foundation | Junos OS configured with security hardening and optimization | OS Testing | Implemented | OS Administrator | Platform Setup
Firewall Platform | FW-004 | Performance Optimization | Optimize firewall performance for high-throughput environments | High | Performance Requirements | Meet network performance requirements with security enabled | Performance optimization achieving 50Gbps with security services | Performance Testing | Implemented | Performance Engineer | Platform Configuration
Firewall Platform | FW-005 | Management Interface | Configure centralized management and monitoring interfaces | Medium | Management Requirements | Enable efficient firewall management and monitoring | Management interface with centralized policy and monitoring | Management Testing | Implemented | Management Engineer | Platform Setup
Threat Protection | THREAT-001 | Advanced Threat Prevention | Implement Sky ATP for advanced threat prevention | High | Security Requirements | Protect against advanced persistent threats and zero-day attacks | ATP with 99.7% threat detection and prevention rate | Threat Testing | Implemented | Threat Engineer | Security Platform
Threat Protection | THREAT-002 | Intrusion Prevention | Deploy IPS with custom signatures and threat intelligence | High | Network Security | Detect and prevent network-based attacks and intrusions | IPS with real-time threat detection and automated blocking | IPS Testing | Implemented | IPS Engineer | Threat Platform
Threat Protection | THREAT-003 | Anti-Malware Protection | Implement comprehensive anti-malware and anti-virus protection | High | Malware Protection | Protect against malware, viruses, and malicious content | Anti-malware with 99.5% malware detection rate | Malware Testing | Implemented | Malware Engineer | Security Services
Threat Protection | THREAT-004 | Web Filtering | Deploy web filtering and content control capabilities | Medium | Content Security | Control web access and prevent access to malicious sites | Web filtering with URL categorization and policy enforcement | Web Filter Testing | Implemented | Web Filter Engineer | Content Platform
Threat Protection | THREAT-005 | SSL Inspection | Implement SSL/TLS inspection and decryption capabilities | High | Encrypted Traffic Security | Inspect encrypted traffic for hidden threats | SSL inspection with certificate management and policy control | SSL Testing | Implemented | SSL Engineer | Certificate Management
Network Security | NET-001 | Micro-Segmentation | Implement network micro-segmentation with application control | High | Zero Trust Architecture | Enable zero-trust network security with granular controls | Micro-segmentation with application-based security policies | Segmentation Testing | Implemented | Segmentation Engineer | Policy Framework
Network Security | NET-002 | VPN Services | Deploy secure VPN services for remote access | High | Remote Access Security | Provide secure remote access for mobile workforce | VPN services with multi-factor authentication and encryption | VPN Testing | Implemented | VPN Engineer | Authentication Platform
Network Security | NET-003 | Network Access Control | Implement dynamic network access control | Medium | Access Management | Control network access based on device compliance and user identity | NAC with automated device compliance and access control | NAC Testing | Implemented | NAC Engineer | Identity Integration
Network Security | NET-004 | DDoS Protection | Deploy DDoS protection and mitigation capabilities | High | Availability Protection | Protect against distributed denial of service attacks | DDoS protection with automated detection and mitigation | DDoS Testing | Implemented | DDoS Engineer | Network Platform
Network Security | NET-005 | Network Analytics | Implement network security analytics and monitoring | Medium | Security Visibility | Provide visibility into network traffic and security events | Analytics with real-time monitoring and threat correlation | Analytics Testing | Implemented | Analytics Engineer | Monitoring Platform
Policy Management | POL-001 | Security Policy Framework | Implement comprehensive security policy framework | High | Policy Governance | Provide structured approach to security policy management | Policy framework with automated enforcement and compliance | Policy Testing | Implemented | Policy Manager | Governance Framework
Policy Management | POL-002 | Automated Policy Deployment | Deploy automated security policy deployment and management | High | Policy Automation | Enable efficient and consistent policy deployment | Automated policy deployment with version control and rollback | Automation Testing | Implemented | Automation Engineer | Policy Platform
Policy Management | POL-003 | Application Control | Implement application-based security policies | High | Application Security | Control application access and usage based on security policies | Application control with traffic shaping and security enforcement | Application Testing | Implemented | Application Engineer | Policy Framework
Policy Management | POL-004 | User-Based Policies | Deploy identity-aware security policies | High | Identity Security | Enable security policies based on user identity and role | User-based policies with Active Directory integration | Identity Testing | Implemented | Identity Engineer | Authentication Platform
Policy Management | POL-005 | Policy Compliance | Implement automated policy compliance monitoring | High | Compliance Requirements | Ensure continuous compliance with security policies | Compliance monitoring with automated reporting and alerting | Compliance Testing | Implemented | Compliance Engineer | Policy Platform
Integration and APIs | INT-001 | SIEM Integration | Integrate with enterprise SIEM platforms | High | Security Operations | Enable centralized security event monitoring and correlation | SIEM integration with real-time event forwarding | SIEM Testing | Implemented | SIEM Engineer | Security Platform
Integration and APIs | INT-002 | SOAR Integration | Integrate with security orchestration and response platforms | Medium | Incident Response | Enable automated incident response and workflow orchestration | SOAR integration with automated response workflows | SOAR Testing | Implemented | SOAR Engineer | Integration Platform
Integration and APIs | INT-003 | Threat Intelligence | Integrate with threat intelligence feeds and platforms | High | Threat Detection | Enhance threat detection with real-time threat intelligence | Threat intelligence integration with automated IOC updates | Threat Intel Testing | Implemented | Threat Intel Engineer | Security Platform
Integration and APIs | INT-004 | Network Management | Integrate with network management and monitoring tools | Medium | Network Operations | Enable comprehensive network monitoring and management | Network integration with monitoring and alerting platforms | Network Testing | Implemented | Network Engineer | Management Platform
Integration and APIs | INT-005 | API Framework | Implement RESTful API framework for custom integrations | Medium | Integration Requirements | Enable custom integrations and automation workflows | API framework with comprehensive documentation and SDKs | API Testing | Implemented | API Engineer | Platform Integration
Monitoring and Analytics | MON-001 | Security Monitoring | Implement comprehensive security monitoring and alerting | High | Security Operations | Provide real-time security monitoring and threat detection | Security monitoring with 24/7 alerting and response | Monitoring Testing | Implemented | Security Analyst | Security Platform
Monitoring and Analytics | MON-002 | Performance Monitoring | Deploy performance monitoring and capacity management | High | Performance Management | Monitor firewall performance and capacity utilization | Performance monitoring with real-time dashboards and alerting | Performance Testing | Implemented | Performance Analyst | Monitoring Platform
Monitoring and Analytics | MON-003 | Traffic Analytics | Implement network traffic analytics and reporting | Medium | Network Visibility | Provide visibility into network traffic patterns and usage | Traffic analytics with automated reporting and insights | Traffic Testing | Implemented | Traffic Analyst | Analytics Platform
Monitoring and Analytics | MON-004 | Log Management | Deploy centralized log management and analysis | High | Log Analytics | Enable centralized logging and security event analysis | Log management with retention policies and search capabilities | Log Testing | Implemented | Log Engineer | Monitoring Platform
Monitoring and Analytics | MON-005 | Reporting Framework | Implement automated reporting and dashboard framework | Medium | Management Reporting | Provide executive and operational reporting capabilities | Reporting framework with automated report generation | Reporting Testing | Implemented | Report Engineer | Analytics Platform
Compliance and Governance | COMP-001 | Regulatory Compliance | Implement controls for SOC 2, PCI DSS, and FISMA compliance | High | Regulatory Requirements | Meet regulatory compliance requirements for security controls | Compliance controls with automated monitoring and reporting | Compliance Testing | Implemented | Compliance Officer | Security Framework
Compliance and Governance | COMP-002 | Audit Trail | Implement comprehensive audit trail and logging | High | Audit Requirements | Provide complete audit trail for security and compliance | Audit trail with tamper-proof logging and retention | Audit Testing | Implemented | Audit Engineer | Logging Platform
Compliance and Governance | COMP-003 | Change Management | Implement formal change management for security policies | High | Change Control | Ensure proper change control for security policy modifications | Change management with approval workflows and tracking | Change Testing | Implemented | Change Manager | Policy Platform
Compliance and Governance | COMP-004 | Risk Assessment | Implement automated risk assessment and reporting | Medium | Risk Management | Provide continuous risk assessment and mitigation | Risk assessment with automated scoring and reporting | Risk Testing | Implemented | Risk Engineer | Compliance Platform
Compliance and Governance | COMP-005 | Evidence Collection | Implement automated evidence collection for audits | Medium | Audit Support | Automate evidence collection for compliance audits | Evidence collection with automated documentation and storage | Evidence Testing | Implemented | Evidence Manager | Audit Platform
Business Continuity | BC-001 | Disaster Recovery | Implement disaster recovery procedures and capabilities | High | Business Continuity | Ensure business continuity during security infrastructure failures | DR procedures with 4-hour RTO and 1-hour RPO | DR Testing | Implemented | DR Manager | HA Platform
Business Continuity | BC-002 | Backup and Recovery | Implement automated backup and recovery procedures | High | Data Protection | Protect security configuration and policy data | Backup procedures with automated recovery validation | Backup Testing | Implemented | Backup Engineer | Configuration Management
Business Continuity | BC-003 | Failover Testing | Implement regular failover testing and validation | High | Continuity Validation | Validate business continuity capabilities through testing | Failover testing with documented procedures and results | Failover Testing | Implemented | Continuity Tester | BC Procedures
Business Continuity | BC-004 | Recovery Procedures | Develop comprehensive recovery procedures and runbooks | Medium | Operational Continuity | Provide detailed recovery procedures for various scenarios | Recovery procedures with step-by-step documentation | Procedure Testing | Implemented | Procedure Manager | DR Framework
Business Continuity | BC-005 | Communication Plans | Implement incident communication and notification plans | Medium | Incident Management | Ensure proper communication during security incidents | Communication plans with automated notification workflows | Communication Testing | Implemented | Communication Manager | Incident Response
Training and Documentation | TRAIN-001 | Technical Documentation | Create comprehensive technical documentation and runbooks | High | Knowledge Management | Provide detailed documentation for operations and troubleshooting | Technical documentation with 95% coverage of procedures | Documentation Review | Implemented | Technical Writer | Platform Implementation
Training and Documentation | TRAIN-002 | Security Training | Provide comprehensive security training for operations teams | High | Team Enablement | Ensure teams can effectively operate and manage security platform | Security training with 85% certification completion rate | Training Assessment | Implemented | Security Trainer | Documentation
Training and Documentation | TRAIN-003 | Operations Training | Provide specialized training for network operations teams | High | Operations Enablement | Ensure operations teams can effectively manage the platform | Operations training with 90% competency achievement | Operations Assessment | Implemented | Operations Trainer | Security Training
Training and Documentation | TRAIN-004 | Incident Response Training | Provide incident response training and procedures | High | Response Readiness | Ensure teams can effectively respond to security incidents | Incident response training with scenario-based exercises | Response Assessment | Implemented | Response Trainer | Security Training
Training and Documentation | TRAIN-005 | Continuous Learning | Establish ongoing training and certification programs | Medium | Skill Development | Maintain current skills and certifications for security teams | Learning program with 80% annual certification rate | Learning Assessment | Implemented | Learning Manager | Training Infrastructure