## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Cmmc Enclave
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Purpose | Success Metrics
Executive Security Briefings | C-Level Leadership | Weekly | Secure Executive Dashboard | CISO, Project Manager | CMMC compliance status and security KPIs | Strategic oversight and risk management | 90% executive engagement and decision support
CMMC Steering Committee | Project Steering Committee | Bi-weekly | Secure Conference Room + Encrypted Virtual | Project Manager | Compliance progress and regulatory updates | Governance and regulatory alignment | 100% attendance for compliance decisions
DoD Liaison Updates | Defense Contract Officers | Monthly | Secure Communication Channel | Contracts Director | CMMC certification status and contract eligibility | Contract maintenance and renewal | 100% DoD requirement compliance
Security Operations Center (SOC) Briefings | SOC Team and Security Analysts | Daily | SOC Command Center | SOC Manager | Threat landscape and incident status | 24/7 security monitoring and response | <15 minute threat detection time
Compliance Audit Updates | Internal Audit and Compliance Teams | Weekly | Compliance Management Portal | Compliance Officer | Audit readiness and evidence collection | Regulatory preparedness and documentation | 100% audit requirement coverage
User Security Training | All Enclave Users | Monthly | Security Training Platform | Security Training Coordinator | CMMC awareness and secure practices | User education and policy adherence | 100% training completion and certification
Incident Response Communications | Incident Response Team | As needed (real-time) | Secure Emergency Channel | IR Team Lead | Security incident status and response actions | Rapid incident containment and resolution | <30 minute notification for critical incidents
Vendor Security Reviews | Third-party Vendors and Suppliers | Quarterly | Vendor Security Portal | Vendor Management Lead | Supply chain security and CMMC alignment | Vendor compliance and risk mitigation | 100% vendor security assessment completion
Risk Management Reports | Enterprise Risk Committee | Monthly | Risk Management Dashboard | Risk Manager | CMMC risk register and mitigation status | Enterprise risk oversight and management | 95% risk mitigation target achievement
Privacy and Data Protection Updates | Data Privacy Office | Bi-weekly | Privacy Management System | Data Protection Officer | CUI data handling and privacy compliance | Data protection and regulatory adherence | Zero data privacy incidents
IT Security Architecture Reviews | Enterprise Architecture Team | Weekly | Architecture Review Board | Security Architect | Security control implementation and effectiveness | Technical security oversight and optimization | 100% security control validation
Legal and Regulatory Updates | Legal Counsel and Regulatory Affairs | Monthly | Legal Advisory Channel | General Counsel | Regulatory changes and legal compliance | Legal risk management and compliance | 100% regulatory requirement tracking
User Access Reviews | Identity and Access Management Team | Weekly | IAM Management Console | IAM Administrator | User access rights and privilege validation | Access control and least privilege enforcement | 100% access review completion
Penetration Testing Reports | External Security Assessors | Quarterly | Secure Assessment Portal | Security Assessment Lead | Security testing results and vulnerability status | Independent security validation and improvement | Zero critical vulnerabilities in production
Business Continuity Updates | Business Continuity Team | Monthly | BC Management Platform | BC Manager | Disaster recovery and continuity readiness | Business resilience and operational continuity | 100% BC requirement coverage
Technology Refresh Communications | IT Operations Team | Quarterly | IT Operations Dashboard | IT Operations Manager | Security technology updates and improvements | Technology currency and security effectiveness | Quarterly technology assessment completion
Employee Security Awareness | All Company Personnel | Quarterly | Company-wide Communications | Security Awareness Lead | Security culture and awareness initiatives | Security mindset and behavioral change | 80% security awareness assessment scores
Contractor Security Briefings | External Contractors and Consultants | Monthly | Contractor Security Portal | Contractor Security Officer | Security requirements and compliance obligations | Contractor security compliance and oversight | 100% contractor security training completion
Supply Chain Security Updates | Supply Chain Management | Monthly | Supply Chain Security Platform | Supply Chain Security Lead | Vendor security assessments and compliance | Supply chain risk management and security | 100% critical vendor security assessment
Board Security Reporting | Board of Directors | Quarterly | Board Reporting Package | CISO | Enterprise cybersecurity posture and CMMC status | Board oversight and strategic security direction | Quarterly board security presentation
Customer Security Communications | Defense Contractor Customers | As needed | Customer Security Portal | Customer Success Manager | Security capabilities and compliance certification | Customer confidence and relationship management | Customer security requirement validation
Threat Intelligence Briefings | Security Leadership Team | Weekly | Threat Intelligence Platform | Threat Intelligence Analyst | Emerging threats and threat landscape analysis | Proactive threat awareness and preparation | Weekly threat assessment delivery
Security Metrics and KPI Reports | Security Management Team | Weekly | Security Dashboard | Security Metrics Analyst | Security performance indicators and trending | Performance monitoring and continuous improvement | Weekly KPI target achievement
Emergency Notification System | All Critical Personnel | Real-time | Mass Notification System | Emergency Coordinator | Critical security incidents and emergency procedures | Rapid emergency response and coordination | <5 minute emergency notification delivery
Security Tool Administration | Security Tool Administrators | Daily | Security Tool Management Console | Security Tool Administrator | Security tool health and operational status | Security infrastructure reliability and effectiveness | 99.9% security tool uptime target
Vulnerability Management Updates | Vulnerability Management Team | Weekly | Vulnerability Management Platform | Vulnerability Manager | Vulnerability scan results and remediation status | Proactive vulnerability identification and remediation | 95% vulnerability remediation within SLA
Privilege Access Management Reviews | PAM Administrators | Daily | PAM Management Console | PAM Administrator | Privileged account activity and access reviews | Privileged access oversight and control | 100% privileged access session monitoring
Security Policy Updates | All Enclave Personnel | As needed | Policy Management System | Policy Manager | Security policy changes and requirement updates | Policy compliance and awareness | 100% policy acknowledgment and compliance
Third-party Security Assessments | External Security Partners | Quarterly | Assessment Coordination Platform | Assessment Coordinator | Independent security assessments and validation | Objective security posture evaluation and improvement | Quarterly assessment completion and remediation
Data Loss Prevention Alerts | Data Security Team | Real-time | DLP Management Console | DLP Administrator | Data movement and potential loss incidents | Data protection and loss prevention | <10 minute DLP incident response time
Backup and Recovery Testing | Backup Operations Team | Monthly | Backup Management Platform | Backup Manager | Backup integrity and recovery capability validation | Data protection and business continuity assurance | 100% backup test success rate
Security Configuration Management | Configuration Management Team | Weekly | Configuration Management Database | Configuration Manager | Security baseline compliance and configuration drift | Security configuration consistency and control | 100% security baseline compliance
Insider Threat Monitoring | Insider Threat Team | Weekly | Insider Threat Platform | Insider Threat Analyst | Behavioral analysis and potential insider risk indicators | Insider threat detection and prevention | Weekly insider threat assessment completion
Digital Forensics Communications | Digital Forensics Team | As needed | Forensics Case Management | Forensics Lead | Investigation status and forensic analysis results | Incident investigation and evidence preservation | Complete forensic analysis for all incidents
Security Training Effectiveness | Training Assessment Team | Quarterly | Training Analytics Platform | Training Effectiveness Analyst | Training impact and behavioral change assessment | Training program optimization and effectiveness | Quarterly training effectiveness measurement
Regulatory Compliance Reporting | Regulatory Compliance Team | Monthly | Compliance Reporting System | Regulatory Compliance Manager | Regulatory requirement status and compliance evidence | Regulatory adherence and audit readiness | 100% regulatory compliance maintenance
Crisis Communication Planning | Crisis Management Team | Quarterly | Crisis Management Platform | Crisis Communications Lead | Crisis response procedures and communication protocols | Crisis preparedness and stakeholder communication | Quarterly crisis communication exercise completion
Security Investment Reporting | Finance and Security Leadership | Quarterly | Financial Management System | Security Finance Analyst | Security investment ROI and budget performance | Financial accountability and investment optimization | Quarterly security investment review completion
International Security Coordination | Global Security Teams | Monthly | Global Security Platform | Global Security Coordinator | Multi-regional security coordination and alignment | Global security consistency and collaboration | Monthly global security coordination completion