## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | M365 Deployment
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Stakeholder Group | Communication Type | Frequency | Channel | Key Messages | Responsible Party | Timing | Audience Size | Feedback Mechanism | Success Metrics | Escalation Path | Templates Available | Status | Notes
Executive Leadership | Strategic Updates | Weekly | Executive Dashboard | Project status ROI metrics business impact | EO Project Manager | Fridays 2PM | 8 |  | Decision speed stakeholder satisfaction | CEO | Yes | Focus on business value and ROI
IT Leadership | Technical Status | Daily | Slack #m365-project | Technical progress issues risks mitigation | EO Delivery Engineer (Technical Leadership) | Daily standup | 12 |  | Issue resolution time technical decisions | CTO | Yes | Technical implementation focus
Project Sponsors | Governance Updates | Bi-weekly | Steering Committee Meeting | Milestone progress budget status change requests | EO Project Manager | Every other Tuesday | 6 |  | Milestone achievement budget adherence | Executive Sponsor | Yes | Governance and oversight focus
Department Managers | Operational Impact | Weekly | Manager Newsletter | Deployment schedule user impact training requirements | EO Sales Engineer (Business Analysis) | Wednesdays | 25 |  | Manager engagement user readiness | Department VPs | Yes | Operational readiness and change management
End Users | Training and Adoption | Bi-weekly | Company Newsletter | Feature highlights training schedule success stories | EO Engineer (Training) | Every other Monday | 1500 |  | Training participation user satisfaction | HR Leadership | Yes | User adoption and success focus
IT Administrators | Technical Implementation | Daily | Teams Channel | Configuration changes deployment status technical issues | EO Delivery Engineer (Technical Leadership) | Morning updates | 15 |  | Response time issue resolution | IT Director | Yes | Technical implementation and support
Security Team | Security and Compliance | Weekly | Security Review Meeting | Security configurations compliance status risk mitigation | EO Engineer (Security) | Thursdays 1PM | 8 |  | Compliance metrics security incidents | CISO | Yes | Security posture and compliance
Help Desk Team | Support Readiness | Daily | Support Portal | Known issues training updates user guides | EO Engineer (Support) | Updates as needed | 20 |  | Ticket resolution time user satisfaction | IT Support Manager | Yes | Support effectiveness and user experience
Change Management Committee | Change Coordination | Weekly | Change Review Board | Change requests impact assessments approval status | EO Sales Engineer (Business Analysis) | Tuesdays 3PM | 10 |  | Change success rate impact assessment | Change Manager | Yes | Change control and risk management
External Vendors | Vendor Coordination | Bi-weekly | Vendor Portal | Integration requirements timeline coordination | EO Delivery Engineer (Platform Implementation) | Vendor coordination meetings | 5 |  | Delivery timeline integration success | Procurement Manager | Yes | Vendor management and coordination
Training Champions | User Adoption | Weekly | Champions Network | Training materials feedback adoption metrics support escalation | EO Engineer (Training) | Champion meetings | 30 |  | User adoption rates champion effectiveness | Training Manager | Yes | User adoption and support network
Compliance Team | Regulatory Updates | Monthly | Compliance Review | Regulatory compliance audit readiness policy updates | EO Engineer (Security) | First Monday monthly | 6 |  | Audit readiness compliance metrics | Legal Counsel | Yes | Regulatory compliance and audit
Business Unit Leaders | Business Impact | Bi-weekly | BU Leadership Meeting | Business process impact productivity gains ROI metrics | EO Sales Engineer (Business Analysis) | Every other Friday | 15 |  | Productivity metrics business satisfaction | Division Presidents | Yes | Business value and operational impact
Quality Assurance | Testing and Validation | Daily | QA Status Reports | Test results defect status quality metrics validation | EO Engineer (QA) | Daily test reports | 8 |  | Test coverage defect resolution | QA Manager | Yes | Quality assurance and testing
Regional Offices | Deployment Coordination | Weekly | Regional Coordination Call | Regional deployment schedule local support coordination | EO Project Manager | Regional meetings | 20 |  | Regional readiness deployment success | Regional Directors | Yes | Geographic coordination and support
Partner Organizations | External Coordination | Monthly | Partner Review Meeting | Integration status data sharing coordination | EO Delivery Engineer (Platform Implementation) | Monthly partner review | 8 |  | Integration success data quality | Partnership Manager | Yes | External integration and collaboration
Audit Team | Audit Readiness | Quarterly | Audit Preparation Meeting | Audit trail compliance documentation control framework | EO Engineer (Security) | Quarterly audit prep | 4 |  | Audit findings compliance rating | Audit Director | Yes | Audit readiness and compliance
Board of Directors | Strategic Oversight | Quarterly | Board Presentation | Strategic alignment business value risk management | Executive Sponsor | Quarterly board meeting | 12 |  | Strategic alignment risk mitigation | Board Chair | Yes | Strategic oversight and governance
Union Representatives | Employee Relations | Monthly | Union Liaison Meeting | Employee impact training opportunities change management | HR Leadership | Monthly union meeting | 6 |  | Employee satisfaction change acceptance | Union President | Yes | Employee relations and change acceptance
Regulatory Bodies | Compliance Reporting | As Required | Regulatory Submissions | Compliance status audit results regulatory changes | EO Engineer (Security) | Regulatory deadlines | 3 |  | Compliance rating regulatory approval | Legal Counsel | Yes | Regulatory compliance and reporting
Customer Support | Customer Impact | Weekly | Customer Impact Review | Service availability customer communication impact mitigation | EO Engineer (Support) | Customer impact meetings | 12 |  | Customer satisfaction service availability | Customer Success Manager | Yes | Customer experience and service delivery
Finance Team | Budget and ROI | Monthly | Financial Review Meeting | Budget status cost savings ROI metrics financial impact | EO Project Manager | Monthly financial review | 8 |  | Budget adherence ROI achievement | CFO | Yes | Financial management and ROI tracking
Legal Team | Legal and Risk | Monthly | Legal Review Meeting | Contractual obligations risk assessment compliance requirements | EO Engineer (Security) | Monthly legal review | 5 |  | Legal compliance risk mitigation | General Counsel | Yes | Legal compliance and risk management
Facilities Team | Infrastructure Coordination | Bi-weekly | Facilities Coordination | Network infrastructure space requirements equipment needs | EO Delivery Engineer (Infrastructure) | Facilities meetings | 6 |  | Infrastructure readiness facility compliance | Facilities Manager | Yes | Infrastructure and facilities coordination
Marketing Team | Internal Communications | Weekly | Marketing Review Meeting | Communication strategy internal branding success story development | EO Engineer (Training) | Marketing coordination | 8 |  | Communication effectiveness brand alignment | Marketing Director | Yes | Internal communication and branding