## Cover
Project Plan
Delivery Document
Generated: | November 15, 2025
Solution: | M365 Deployment
Customer Name: | Data table for project plan
Version: | 1.0

## Project Plan
Task ID | Phase | Task Name | Description | Owner | Start Date | End Date | Duration | Dependencies | Resource Allocation | Priority | Status | Completion % | Deliverables | Success Criteria | Risks | Notes
M365-001 | Planning | Project Initiation | Project charter stakeholder identification and kickoff meeting | EO Project Manager | Week 1 Day 1 | Week 1 Day 3 | 3 days |  | Project Manager 100% | Critical | Completed | 100% | Project charter stakeholder matrix | Executive approval and stakeholder commitment | Scope creep stakeholder misalignment | Foundation for project success
M365-002 | Planning | Requirements Gathering | Business requirements technical requirements and user needs assessment | EO Sales Engineer (Business Analysis) | Week 1 Day 2 | Week 1 Day 5 | 4 days | M365-001 | Business Analyst 100% | Critical | Completed | 100% | Requirements document business case | Complete and validated requirements | Changing requirements incomplete discovery | Critical for solution design
M365-003 | Planning | Current State Assessment | Existing infrastructure applications and user environment analysis | EO Delivery Engineer (Technical Leadership) | Week 1 Day 4 | Week 2 Day 2 | 3 days | M365-002 | Technical Lead 100% | High | Completed | 100% | Current state documentation gap analysis | Comprehensive environment understanding | Hidden dependencies security issues | Baseline for migration planning
M365-004 | Planning | Solution Architecture Design | M365 architecture design integration planning and technical specifications | EO Sales Engineer (Solution Architecture) | Week 2 Day 1 | Week 2 Day 5 | 5 days | M365-003 | Solution Architect 100% | Critical | Completed | 100% | Architecture document technical design | Technical validation and approval | Design flaws integration challenges | Blueprint for implementation
M365-005 | Planning | Migration Strategy Planning | Migration approach timeline and risk mitigation strategy | EO Delivery Engineer (Technical Leadership) | Week 2 Day 3 | Week 3 Day 2 | 4 days | M365-004 | Technical Lead 80% | Critical | Completed | 100% | Migration strategy document cutover plan | Risk-managed migration approach | Data loss service disruption | Critical for migration success
M365-006 | Planning | Security and Compliance Design | Security architecture compliance framework and governance design | EO Engineer (Security) | Week 2 Day 4 | Week 3 Day 3 | 4 days | M365-004 | Security Engineer 100% | Critical | Completed | 100% | Security design compliance framework | Security validation and approval | Security gaps compliance violations | Essential for enterprise deployment
M365-007 | Planning | Change Management Planning | User communication training strategy and adoption planning | EO Sales Engineer (Business Analysis) | Week 3 Day 1 | Week 3 Day 5 | 5 days | M365-002 | Change Manager 100% | High | Completed | 100% | Change management plan communication strategy | Stakeholder buy-in and readiness | User resistance low adoption | Critical for user acceptance
M365-008 | Setup | Azure AD Tenant Setup | Azure AD tenant configuration domain verification and initial setup | EO Engineer (Identity) | Week 3 Day 3 | Week 4 Day 1 | 3 days | M365-005 | Identity Engineer 100% | Critical | Completed | 100% | Configured Azure AD tenant domain verification | Tenant ready for service deployment | Configuration errors domain issues | Foundation for all M365 services
M365-009 | Setup | Licensing and Subscriptions | M365 licensing procurement user assignment and quota management | EO Delivery Engineer (Platform Implementation) | Week 4 Day 1 | Week 4 Day 3 | 3 days | M365-008 | Platform Engineer 80% | Critical | Completed | 100% | License allocation user assignments | All users properly licensed | Licensing errors cost overruns | Required for service access
M365-010 | Setup | Azure AD Connect Setup | Hybrid identity configuration directory synchronization and authentication | EO Engineer (Identity) | Week 4 Day 2 | Week 4 Day 5 | 4 days | M365-008 | Identity Engineer 100% | Critical | Completed | 100% | Azure AD Connect configuration identity sync | Seamless identity integration | Sync failures authentication issues | Critical for hybrid environment
M365-011 | Implementation | Exchange Online Configuration | Exchange Online setup mailbox provisioning and mail flow configuration | EO Delivery Engineer (Technical Leadership) | Week 4 Day 4 | Week 5 Day 3 | 4 days | M365-010 | Email Specialist 100% | Critical | Completed | 100% | Exchange Online configuration mail flow setup | Email services operational | Mail flow issues configuration errors | Core productivity service
M365-012 | Implementation | SharePoint Online Setup | SharePoint Online configuration site collections and permission structure | EO Engineer (Collaboration) | Week 5 Day 1 | Week 5 Day 5 | 5 days | M365-009 | SharePoint Specialist 100% | High | Completed | 100% | SharePoint configuration site structure | SharePoint services ready | Permission issues site failures | Collaboration foundation
M365-013 | Implementation | Microsoft Teams Deployment | Teams deployment voice integration and meeting room setup | EO Engineer (Collaboration) | Week 5 Day 3 | Week 6 Day 2 | 4 days | M365-011 | Teams Specialist 100% | High | Completed | 100% | Teams configuration voice setup | Teams platform operational | Call quality network issues | Unified communications platform
M365-014 | Implementation | OneDrive for Business Setup | OneDrive deployment file sync configuration and storage policies | EO Engineer (Collaboration) | Week 6 Day 1 | Week 6 Day 3 | 3 days | M365-012 | OneDrive Specialist 80% | High | Completed | 100% | OneDrive configuration sync policies | OneDrive services operational | Sync issues storage problems | File collaboration and storage
M365-015 | Implementation | Security Configuration | Conditional Access MFA configuration and security policies | EO Engineer (Security) | Week 6 Day 2 | Week 7 Day 1 | 4 days | M365-010 | Security Engineer 100% | Critical | Completed | 100% | Security policies MFA configuration | Security controls operational | Security gaps policy conflicts | Essential security foundation
M365-016 | Implementation | Data Loss Prevention Setup | DLP policies configuration sensitive data protection and monitoring | EO Engineer (Security) | Week 7 Day 1 | Week 7 Day 4 | 4 days | M365-015 | Security Engineer 80% | High | Completed | 100% | DLP policies data classification | Data protection operational | False positives policy gaps | Data protection and compliance
M365-017 | Implementation | Power Platform Deployment | Power Apps Power Automate and Power BI configuration for business processes | EO Engineer (Automation) | Week 7 Day 3 | Week 8 Day 2 | 4 days | M365-012 | Automation Specialist 100% | Medium | Completed | 100% | Power Platform configuration workflow automation | Power Platform operational | Workflow failures licensing issues | Business process automation
M365-018 | Migration | Pilot User Migration | Pilot group migration testing validation and feedback collection | EO Delivery Engineer (Technical Leadership) | Week 8 Day 1 | Week 8 Day 5 | 5 days | M365-017 | Migration Specialist 100% | Critical | Completed | 100% | Pilot migration results feedback report | Successful pilot with user validation | Migration issues user problems | Validation of migration approach
M365-019 | Migration | Email Migration Phase 1 | First wave email migration including executives and IT staff | EO Delivery Engineer (Technical Leadership) | Week 9 Day 1 | Week 9 Day 3 | 3 days | M365-018 | Migration Team 100% | Critical | Completed | 100% | Migrated mailboxes cutover validation | Email migration success with minimal downtime | Data loss email disruption | Critical business communication
M365-020 | Migration | Email Migration Phase 2 | Second wave email migration for remaining departments and users | EO Delivery Engineer (Technical Leadership) | Week 9 Day 4 | Week 10 Day 2 | 3 days | M365-019 | Migration Team 100% | Critical | Completed | 100% | Complete email migration user validation | All email successfully migrated | Migration delays user disruption | Complete email platform migration
M365-021 | Migration | File Migration | SharePoint and OneDrive file migration including legacy file servers | EO Engineer (Collaboration) | Week 10 Day 1 | Week 10 Day 5 | 5 days | M365-020 | Migration Team 80% | High | Completed | 100% | File migration completion permission validation | Files accessible with proper permissions | File corruption permission issues | Document and file collaboration
M365-022 | Testing | User Acceptance Testing | Comprehensive UAT with business users for all M365 services | EO Engineer (QA) | Week 11 Day 1 | Week 11 Day 4 | 4 days | M365-021 | QA Team 100% | Critical | Completed | 100% | UAT results defect reports | User acceptance and system validation | User rejection system defects | User validation of solution
M365-023 | Testing | Performance Testing | System performance testing load testing and optimization | EO Engineer (Performance) | Week 11 Day 3 | Week 11 Day 5 | 3 days | M365-022 | Performance Engineer 100% | High | Completed | 100% | Performance test results optimization recommendations | System meets performance requirements | Performance issues scalability problems | System performance validation
M365-024 | Testing | Security Testing | Security validation penetration testing and compliance verification | EO Engineer (Security) | Week 11 Day 4 | Week 12 Day 2 | 3 days | M365-023 | Security Team 100% | Critical | Completed | 100% | Security test results vulnerability assessment | Security requirements validated | Security vulnerabilities compliance gaps | Security posture validation
M365-025 | Training | IT Administrator Training | Comprehensive training for IT staff on M365 administration | EO Engineer (Training) | Week 12 Day 1 | Week 12 Day 3 | 3 days | M365-024 | Training Specialist 100% | High | Completed | 100% | Training completion certificates knowledge validation | IT team competency in M365 administration | Knowledge gaps training deficiencies | Administrative capability building
M365-026 | Training | End User Training Phase 1 | Initial end user training for core M365 services | EO Engineer (Training) | Week 12 Day 2 | Week 12 Day 5 | 4 days | M365-025 | Training Team 100% | High | Completed | 100% | Training materials user completion | User competency in M365 basics | Low participation training effectiveness | User adoption foundation
M365-027 | Training | Champion Network Training | Train-the-trainer program for internal champions and super users | EO Engineer (Training) | Week 12 Day 4 | Week 13 Day 1 | 2 days | M365-026 | Training Specialist 80% | Medium | Completed | 100% | Champion certification ongoing support model | Internal support network established | Champion effectiveness ongoing support | Sustainable user support
M365-028 | Deployment | Production Go-Live | Final production deployment system monitoring and user support | EO Project Manager | Week 13 Day 1 | Week 13 Day 3 | 3 days | M365-027 | Full Team 100% | Critical | Completed | 100% | Production system user access validation | Successful go-live with user access | System failures user access issues | Production deployment success
M365-029 | Support | Hypercare Support | Intensive support period monitoring and issue resolution | EO Engineer (Support) | Week 13 Day 1 | Week 14 Day 5 | 10 days | M365-028 | Support Team 100% | Critical | Completed | 100% | Support metrics issue resolution | Smooth transition with minimal issues | User issues system problems | Post-deployment stability
M365-030 | Optimization | Performance Optimization | System tuning performance optimization and capacity planning | EO Engineer (Performance) | Week 14 Day 1 | Week 14 Day 5 | 5 days | M365-029 | Performance Engineer 80% | Medium | Completed | 100% | Optimization report performance improvements | Optimized system performance | Performance degradation capacity issues | System performance enhancement
M365-031 | Documentation | Knowledge Transfer | Documentation creation knowledge transfer and handover preparation | EO Engineer (Support) | Week 14 Day 3 | Week 15 Day 2 | 4 days | M365-030 | Documentation Team 100% | High | Completed | 100% | Complete documentation knowledge base | Comprehensive documentation for ongoing support | Documentation gaps knowledge transfer issues | Sustainable support capability
M365-032 | Closeout | Project Review | Project retrospective lessons learned and success measurement | EO Project Manager | Week 15 Day 1 | Week 15 Day 3 | 3 days | M365-031 | Project Team 80% | Medium | Completed | 100% | Project review report lessons learned | Project success validation and learning | Limited insights missed opportunities | Project completion and learning
M365-033 | Closeout | Stakeholder Satisfaction | Stakeholder feedback collection satisfaction measurement and reporting | EO Sales Engineer (Business Analysis) | Week 15 Day 2 | Week 15 Day 4 | 3 days | M365-032 | Business Analyst 60% | Medium | Completed | 100% | Satisfaction survey results stakeholder feedback | High stakeholder satisfaction | Stakeholder dissatisfaction feedback gaps | Stakeholder relationship management
M365-034 | Closeout | Financial Closeout | Budget reconciliation cost analysis and financial reporting | EO Project Manager | Week 15 Day 3 | Week 15 Day 5 | 3 days | M365-033 | Finance Team 100% | High | Completed | 100% | Financial closeout report budget analysis | Budget compliance and cost optimization | Budget overruns cost escalation | Financial accountability
M365-035 | Closeout | Project Handover | Final handover to operations team ongoing support transition | EO Project Manager | Week 15 Day 4 | Week 15 Day 5 | 2 days | M365-034 | Operations Team 100% | Critical | Completed | 100% | Handover documentation support transition | Smooth transition to operations | Support gaps transition issues | Operational readiness