## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | M365 Deployment
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Title | Description | Acceptance Criteria | Source | Owner | Status | Validation Method | Dependencies | Risk Level | Compliance Impact | Business Impact | Technical Complexity | Effort Estimate | Notes
REQ-001 | Functional | Core Service | Critical | Exchange Online Email Service | Deploy Exchange Online for all users with mailbox migration from on-premises | All 1500 users have functional Exchange Online mailboxes with complete email history | Business Stakeholders | EO Delivery Engineer (Technical Leadership) | Completed | User testing and migration validation | Azure AD tenant licensing | Low | High | High | Medium | 40 hours | Core email communication platform
REQ-002 | Functional | Core Service | Critical | Microsoft Teams Unified Communications | Implement Microsoft Teams for chat calling and meetings with phone system integration | Teams deployed for all users with voice calling and meeting capabilities | IT Leadership | EO Engineer (Collaboration) | Completed | Functionality testing and user acceptance | Exchange Online deployment | Medium | Medium | High | High | 60 hours | Unified communication and collaboration
REQ-003 | Functional | Core Service | Critical | SharePoint Online Collaboration | Deploy SharePoint Online with modern sites and document collaboration | SharePoint sites accessible with proper permissions and collaboration features | Department Managers | EO Engineer (Collaboration) | Completed | Site functionality and permission testing | Azure AD and OneDrive integration | Low | Medium | High | Medium | 35 hours | Document collaboration and intranet
REQ-004 | Functional | Core Service | Critical | OneDrive for Business File Storage | Implement OneDrive for Business with file sync and sharing capabilities | All users have OneDrive access with file sync working across devices | End Users | EO Engineer (Collaboration) | Completed | File sync testing and user validation | SharePoint Online deployment | Low | Medium | High | Low | 25 hours | Personal file storage and sync
REQ-005 | Security | Authentication | Critical | Multi-Factor Authentication | Implement MFA for all user accounts with multiple authentication methods | 100% of users enrolled in MFA with choice of authentication methods | Security Team | EO Engineer (Security) | Completed | MFA enrollment and testing | Azure AD configuration | Low | High | Medium | Medium | 30 hours | Enhanced security for user authentication
REQ-006 | Security | Access Control | Critical | Conditional Access Policies | Deploy conditional access policies for risk-based authentication and device compliance | Conditional access policies active with risk-based authentication | Security Team | EO Engineer (Security) | Completed | Policy testing and compliance validation | Azure AD Premium licensing | Medium | High | Medium | High | 45 hours | Risk-based access control
REQ-007 | Security | Data Protection | Critical | Data Loss Prevention | Implement DLP policies to protect sensitive data across M365 services | DLP policies deployed with sensitive data detection and protection | Compliance Team | EO Engineer (Security) | Completed | Data classification and policy testing | Information protection configuration | Medium | High | High | High | 50 hours | Sensitive data protection
REQ-008 | Security | Threat Protection | High | Advanced Threat Protection | Deploy ATP for email SharePoint and Teams protection | ATP policies active with threat detection and automated response | Security Team | EO Engineer (Security) | Completed | Threat simulation and detection testing | M365 E5 licensing | Medium | High | Medium | Medium | 35 hours | Advanced threat detection and response
REQ-009 | Integration | Identity | Critical | Azure AD Connect Hybrid Identity | Configure Azure AD Connect for hybrid identity synchronization | Directory synchronization working with on-premises AD integration | IT Infrastructure | EO Engineer (Identity) | Completed | Identity sync testing and authentication validation | On-premises AD and Azure AD | High | Medium | High | High | 40 hours | Hybrid identity foundation
REQ-010 | Integration | Directory | High | Active Directory Integration | Integrate with existing on-premises Active Directory for seamless user experience | Users can authenticate with existing credentials across M365 services | IT Infrastructure | EO Engineer (Identity) | Completed | Single sign-on testing and user validation | Azure AD Connect configuration | Medium | Medium | High | Medium | 30 hours | Seamless authentication experience
REQ-011 | Performance | Availability | Critical | 99.9% Service Availability | Ensure M365 services meet 99.9% uptime availability requirements | Service availability monitoring shows 99.9% uptime or better | IT Operations | EO Delivery Engineer (Technical Leadership) | Completed | Availability monitoring and reporting | Proper M365 service configuration | Low | Medium | High | Low | 20 hours | Business continuity requirement
REQ-012 | Performance | Response Time | High | Email Response Time Under 3 Seconds | Email operations must complete within 3 seconds for optimal user experience | Email send receive and folder operations complete within 3 seconds | End Users | EO Delivery Engineer (Technical Leadership) | Completed | Performance testing and user feedback | Network optimization and Exchange configuration | Medium | Low | Medium | Medium | 25 hours | User experience optimization
REQ-013 | Performance | Throughput | High | File Sync Performance | OneDrive file sync must handle large files and bulk operations efficiently | Files up to 15GB sync successfully with reasonable performance | End Users | EO Engineer (Collaboration) | Completed | File sync testing with various file sizes | OneDrive configuration and network optimization | Medium | Low | Medium | Medium | 20 hours | File collaboration efficiency
REQ-014 | Compliance | Data Residency | High | Data Storage Location Control | Ensure M365 data is stored in approved geographic regions | Data residency reports confirm data storage in specified regions | Compliance Team | EO Engineer (Security) | Completed | Data residency validation and reporting | M365 tenant configuration | Low | High | Medium | Low | 15 hours | Regulatory compliance requirement
REQ-015 | Compliance | Audit Trail | High | Comprehensive Audit Logging | Enable audit logging for all M365 activities for compliance monitoring | Audit logs capture all user and admin activities across services | Compliance Team | EO Engineer (Security) | Completed | Audit log validation and reporting | M365 E5 licensing and security configuration | Low | High | Medium | Medium | 25 hours | Compliance and security monitoring
REQ-016 | Compliance | Data Retention | Medium | Email Retention Policies | Implement email retention policies according to organizational requirements | Email retention policies applied with automated deletion and preservation | Legal Team | EO Engineer (Security) | Completed | Retention policy testing and validation | Exchange Online configuration | Low | High | Medium | Medium | 20 hours | Legal and compliance requirement
REQ-017 | Business | Productivity | High | Improved Collaboration Efficiency | M365 deployment must improve team collaboration efficiency by 40% | User surveys and productivity metrics show 40% improvement | Business Stakeholders | EO Sales Engineer (Business Analysis) | Completed | User productivity surveys and metrics analysis | Complete M365 service deployment | Low | Low | High | Low | 10 hours | Business value measurement
REQ-018 | Business | Cost Optimization | High | Infrastructure Cost Reduction | Achieve 30% reduction in email infrastructure costs through cloud migration | Cost analysis shows 30% reduction in email infrastructure expenses | Finance Team | EO Project Manager | Completed | Cost analysis and budget comparison | Exchange Online migration completion | Low | Low | High | Low | 15 hours | Financial benefit realization
REQ-019 | Business | User Adoption | Critical | 90% User Adoption Rate | Achieve 90% active user adoption across core M365 services within 3 months | Usage analytics show 90% of users actively using M365 services | Training Team | EO Engineer (Training) | Completed | Usage analytics and adoption metrics | Training program completion | Medium | Low | High | Medium | 40 hours | Solution success measurement
REQ-020 | Technical | Network | High | Network Optimization for M365 | Optimize network connectivity for M365 services including ExpressRoute consideration | Network performance meets M365 connectivity requirements | IT Infrastructure | EO Delivery Engineer (Infrastructure) | Completed | Network performance testing and optimization | Network infrastructure assessment | Medium | Low | Medium | High | 35 hours | Performance and user experience
REQ-021 | Technical | Backup | Medium | Third-Party Backup Solution | Implement third-party backup for additional M365 data protection | Backup solution operational with regular backup and restore testing | IT Operations | EO Engineer (Support) | Completed | Backup and restore testing validation | M365 services deployment | Low | Medium | Medium | Medium | 30 hours | Additional data protection
REQ-022 | Technical | Monitoring | High | Comprehensive M365 Monitoring | Deploy monitoring solution for M365 services performance and availability | Monitoring dashboard shows real-time M365 service health and performance | IT Operations | EO Delivery Engineer (Monitoring) | Completed | Monitoring functionality and alerting testing | M365 services configuration | Low | Low | Medium | Medium | 25 hours | Proactive service management
REQ-023 | Migration | Email Migration | Critical | Zero Data Loss Email Migration | Migrate all email data with zero data loss and minimal downtime | All email data successfully migrated with validation reports | IT Operations | EO Delivery Engineer (Technical Leadership) | Completed | Migration validation and data integrity testing | Exchange Online configuration | High | Medium | High | High | 60 hours | Critical business data migration
REQ-024 | Migration | File Migration | High | Complete File Server Migration | Migrate all file server data to SharePoint and OneDrive | All file data accessible in SharePoint/OneDrive with proper permissions | IT Operations | EO Engineer (Collaboration) | Completed | File access testing and permission validation | SharePoint and OneDrive deployment | High | Medium | High | High | 50 hours | Document and file consolidation
REQ-025 | Migration | User Profile Migration | Medium | User Profile and Settings Migration | Migrate user profiles and settings where possible to maintain user experience | User settings and preferences preserved in M365 environment | End Users | EO Engineer (Identity) | Completed | User experience testing and preference validation | Identity integration completion | Medium | Low | Medium | Medium | 20 hours | User experience continuity
REQ-026 | Training | Administrator Training | Critical | IT Administrator Certification | All IT administrators must be trained and certified in M365 administration | IT staff complete M365 administrator training with certification | IT Leadership | EO Engineer (Training) | Completed | Training completion and certification validation | M365 deployment completion | Low | Low | High | Low | 40 hours | Administrative capability building
REQ-027 | Training | End User Training | Critical | Comprehensive User Training | Deliver comprehensive training program for all M365 users | All users complete basic M365 training with competency validation | HR Leadership | EO Engineer (Training) | Completed | Training completion and user competency testing | M365 services availability | Medium | Low | High | Medium | 80 hours | User adoption and competency
REQ-028 | Training | Change Management | High | Change Management Program | Implement change management program to support M365 adoption | Change management plan executed with stakeholder communication | Change Management | EO Sales Engineer (Business Analysis) | Completed | Change readiness assessment and stakeholder feedback | Training program development | Low | Low | High | Medium | 30 hours | Adoption success enabler
REQ-029 | Support | Help Desk Readiness | High | Help Desk M365 Support Capability | Prepare help desk team for M365 user support | Help desk can resolve 90% of M365 user issues within SLA | IT Support | EO Engineer (Support) | Completed | Support capability testing and SLA measurement | M365 deployment and training completion | Medium | Low | Medium | Medium | 25 hours | User support capability
REQ-030 | Support | Documentation | High | Comprehensive Support Documentation | Create complete documentation for M365 administration and user support | Documentation available for all M365 services and common issues | IT Operations | EO Engineer (Support) | Completed | Documentation review and completeness validation | M365 implementation completion | Low | Low | Medium | Low | 35 hours | Knowledge management and support
REQ-031 | Governance | Information Governance | Medium | Information Governance Framework | Implement information governance policies for M365 content | Information governance policies active with automated classification | Compliance Team | EO Engineer (Security) | Completed | Governance policy testing and validation | M365 services deployment | Medium | High | Medium | Medium | 30 hours | Content management and compliance
REQ-032 | Governance | Access Governance | Medium | Regular Access Reviews | Establish process for regular access reviews and privilege management | Access review process documented and scheduled with compliance tracking | Security Team | EO Engineer (Security) | Completed | Access review process validation and scheduling | Identity management configuration | Low | Medium | Medium | Low | 20 hours | Security and compliance maintenance
REQ-033 | Integration | LOB Applications | Medium | Line of Business Application Integration | Integrate key LOB applications with M365 for SSO and data sharing | LOB applications integrated with M365 authentication and data flow | Business Units | EO Delivery Engineer (Platform Implementation) | Completed | Integration testing and user validation | M365 identity configuration | High | Low | High | High | 45 hours | Business process integration
REQ-034 | Performance | Scalability | Medium | Future Scalability Planning | Design M365 implementation to support 50% user growth over 3 years | Architecture supports planned growth with performance validation | IT Planning | EO Sales Engineer (Solution Architecture) | Completed | Scalability testing and capacity planning | Complete M365 architecture | Low | Low | Medium | Medium | 20 hours | Future growth accommodation
REQ-035 | Security | Device Management | Medium | Mobile Device Management | Implement Intune for mobile device management and application protection | Mobile devices managed with compliance policies and app protection | Security Team | EO Engineer (Security) | Completed | Device management testing and policy validation | M365 E5 licensing | Medium | Medium | Medium | High | 40 hours | Mobile security and management
REQ-036 | Business | Analytics and Reporting | Medium | Usage Analytics and Reporting | Implement M365 usage analytics for adoption monitoring and optimization | Usage reports and analytics dashboard available for administrators | IT Leadership | EO Delivery Engineer (Monitoring) | Completed | Analytics functionality and report validation | M365 services operational | Low | Low | Medium | Low | 15 hours | Adoption monitoring and optimization
REQ-037 | Technical | Disaster Recovery | Medium | Disaster Recovery Planning | Develop disaster recovery procedures for M365 services | DR procedures documented and tested with recovery validation | IT Operations | EO Engineer (Support) | Completed | DR procedure testing and validation | M365 backup solution implementation | Medium | Medium | Medium | Medium | 25 hours | Business continuity planning
REQ-038 | Compliance | Privacy Protection | High | Privacy Compliance Framework | Implement privacy protection measures for GDPR and other regulations | Privacy controls active with data subject rights capabilities | Legal Team | EO Engineer (Security) | Completed | Privacy control testing and compliance validation | M365 security configuration | Medium | High | Medium | Medium | 30 hours | Privacy regulation compliance
REQ-039 | Integration | Telephony Integration | Medium | Phone System Integration | Integrate existing phone system with Teams for unified communications | Phone calls routed through Teams with existing number preservation | IT Infrastructure | EO Engineer (Collaboration) | Completed | Call routing testing and number portability validation | Teams deployment completion | High | Low | Medium | High | 50 hours | Unified communications enhancement
REQ-040 | Performance | User Experience | High | Optimal User Experience | Ensure M365 provides optimal user experience across all devices and locations | User satisfaction surveys show 85% or higher satisfaction rating | End Users | EO Sales Engineer (Business Analysis) | Completed | User experience testing and satisfaction surveys | Complete M365 deployment | Low | Low | High | Medium | 20 hours | User satisfaction and adoption