## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Dgx Superpod
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Type | Priority | Requirement Description | Acceptance Criteria | Source | Owner | Status | Dependencies | Test Method | Compliance | Notes | Estimated Effort
REQ-001 | Infrastructure | DGX Deployment | Critical | Deploy DGX SuperPOD with 32 DGX A100 systems | DGX cluster with InfiniBand fabric and parallel storage | Infrastructure Team | NVIDIA Team | Draft | Data center readiness | System validation | NVIDIA certification | Exascale AI computing capability | 120 hours
REQ-002 | Infrastructure | Storage System | Critical | Deploy high-performance parallel file system | Multi-petabyte Lustre storage with 100GB/s throughput | Storage Team | Storage Vendor | Draft | Storage hardware | Performance testing | Storage certification | AI workload storage requirements | 80 hours
REQ-003 | Network | InfiniBand Fabric | Critical | Configure HDR InfiniBand networking fabric | 400Gb/s InfiniBand with ultra-low latency for GPU communication | Network Team | NVIDIA Team | Draft | Network hardware | Network testing | InfiniBand certification | High-performance GPU interconnect | 64 hours
REQ-004 | Software | Base Command | High | Deploy NVIDIA Base Command for workload management | Container orchestration with GPU scheduling and monitoring | Platform Team | NVIDIA Team | Draft | REQ-001 | Platform testing | NVIDIA licensing | AI workload orchestration | 72 hours
REQ-005 | Software | AI Frameworks | High | Install optimized AI/ML frameworks and libraries | NGC containers with TensorFlow PyTorch and RAPIDS | AI Team | Data Science Team | Draft | REQ-004 | Framework testing | Framework optimization | Accelerated AI development | 56 hours
REQ-006 | Security | Multi-tenancy | High | Implement secure multi-tenant access controls | Isolated workspaces with RBAC and resource quotas | Security Team | Platform Team | Draft | Identity system | Security testing | Security compliance | Secure shared infrastructure | 48 hours
REQ-007 | Operations | Monitoring | Medium | Deploy comprehensive system and workload monitoring | Real-time dashboards for GPU utilization and job performance | Operations Team | Monitoring Team | Draft | REQ-004 | Monitoring validation | Operations integration | Proactive system management | 44 hours
REQ-008 | Performance | Optimization | Medium | Optimize system performance for large-scale training | Multi-node training with 90%+ GPU utilization efficiency | Performance Team | AI Team | Draft | REQ-005 | Performance benchmarking | Performance tuning | Training efficiency optimization | 60 hours
REQ-009 | Data | Data Pipeline | High | Implement high-throughput data ingestion pipeline | Data pipeline supporting TB-scale datasets with preprocessing | Data Engineering | AI Team | Draft | REQ-002 | Data testing | Data management | Efficient training data access | 68 hours
REQ-010 | Support | Enterprise Support | Medium | Establish enterprise support and maintenance procedures | 24/7 support with guaranteed response times and escalation | Support Team | NVIDIA Team | Draft | Support contracts | Support validation | Enterprise SLA | Mission-critical system support | 32 hours