## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Gpu Compute Cluster
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Format | Success Metrics
Project Kickoff | All Stakeholders | One-time | Research Forum | Project Manager | GPU cluster strategy, AI research acceleration, performance targets, research impact | Presentation and Q&A | 100% stakeholder attendance
Research Updates | Research Teams | Weekly | Research Meetings | Research Coordinator | Cluster utilization, research progress, performance metrics, resource allocation | Research briefing | 95% researcher engagement
Executive Dashboard | Leadership Team | Bi-weekly | Executive Portal | Program Manager | Research impact, utilization metrics, ROI analysis, innovation outcomes | Executive dashboard | Leadership satisfaction >4.5
Technical Reviews | HPC Engineers | Weekly | Technical Committee | HPC Architect | Performance optimization, system health, capacity planning, technology updates | Technical documentation | System optimization >95%
NVIDIA Partnership | NVIDIA Teams | Monthly | Partner Meetings | Technical Lead | Platform optimization, feature updates, support escalations, roadmap alignment | Partnership review | Partner satisfaction >95%
Researcher Training | Faculty and Students | Monthly | Training Center | Training Manager | GPU programming, CUDA development, framework optimization, best practices | Hands-on workshops | Certification rate >85%
Performance Reports | Research Directors | Weekly | Performance Portal | Performance Analyst | Benchmark results, utilization analytics, research throughput, optimization opportunities | Performance dashboard | Performance target achievement >90%
Resource Allocation | Department Heads | Bi-weekly | Resource Committee | Resource Manager | Allocation policies, queue management, fair-share usage, priority scheduling | Resource briefing | Resource satisfaction >90%
Innovation Showcase | Research Community | Monthly | Innovation Labs | Innovation Lead | Research breakthroughs, AI discoveries, publication highlights, technology demos | Innovation presentations | Research impact >high
System Operations | Operations Team | Daily | Operations Center | Operations Manager | System health, maintenance schedules, performance monitoring, incident management | Operations dashboard | System uptime >99.5%
Safety and Compliance | Safety Committee | Monthly | Compliance Reviews | Safety Officer | Safety protocols, compliance status, environmental monitoring, risk assessments | Safety briefing | Compliance score >98%
Budget Management | Finance Team | Monthly | Financial Reviews | Budget Manager | Cost analysis, energy efficiency, ROI metrics, budget forecasting | Financial dashboard | Budget variance <5%
Grant Communications | Funding Agencies | Quarterly | Grant Reports | Grant Manager | Research progress, publications, student training, facility utilization | Grant reporting | Funding renewal >95%
Industry Partnerships | Industry Partners | Quarterly | Partnership Reviews | Partnership Manager | Collaboration outcomes, technology transfer, joint research, publication sharing | Partnership briefing | Partnership value >high
Student Programs | Graduate Students | Monthly | Student Forums | Student Coordinator | Training opportunities, research projects, career development, skill building | Student engagement | Student satisfaction >4.5
Publication Support | Research Authors | As needed | Publication Portal | Publication Coordinator | Computational resources, acknowledgments, data sharing, reproducibility | Publication guidance | Publication success >high
Outreach Programs | External Community | Quarterly | Outreach Events | Outreach Manager | Facility tours, educational programs, community engagement, STEM promotion | Outreach activities | Community engagement >high
Technology Transfer | Industry Relations | Quarterly | Transfer Meetings | Transfer Manager | Research commercialization, IP licensing, startup incubation, industry applications | Transfer briefing | Transfer success >medium
Facility Management | Facilities Team | Weekly | Facility Reviews | Facility Manager | Infrastructure status, environmental controls, space planning, equipment maintenance | Facility reports | Facility performance >95%
Emergency Communications | All Users | As needed | Emergency System | Emergency Coordinator | System outages, safety incidents, emergency procedures, recovery status | Emergency alerts | Response time <15 minutes
Research Ethics | Ethics Committee | Quarterly | Ethics Reviews | Ethics Officer | Research ethics, data privacy, responsible AI, compliance monitoring | Ethics briefing | Ethics compliance >98%
International Collaboration | Global Partners | Monthly | Global Forums | International Coordinator | Global research initiatives, data sharing agreements, joint proposals, exchanges | International briefing | Global engagement >high