## Cover
Communication Plan
Delivery Document
Generated: | November 15, 2025
Solution: | Omniverse Enterprise
Customer Name: | Data table for communication plan
Version: | 1.0

## Comm Plan
Communication Type | Audience | Frequency | Channel | Responsible Party | Content | Purpose | Success Metrics
Executive Updates | C-Level Leadership | Weekly | Executive Dashboard | Project Manager, CTO | Project status and KPIs | Strategic oversight and decision making | 90% executive engagement rate
Steering Committee Meeting | Project Steering Committee | Bi-weekly | Conference Room + Virtual | Project Manager | Progress review and issue escalation | Governance and strategic direction | 100% attendance for critical decisions
Technical Status Report | IT Leadership Team | Weekly | Email + Project Portal | Technical Lead | Infrastructure status and performance metrics | Technical oversight and resource planning | 95% report review completion
Creative Team Standup | 3D Artists and Designers | Daily | Omniverse Platform | Creative Director | Daily workflow coordination and blocking issues | Operational efficiency and collaboration | Daily participation tracking
User Training Sessions | End Users by Department | Weekly during rollout | Training Center + Virtual | Training Coordinator | Skills development and platform adoption | User competency and adoption | 85% training completion rate
Support Ticket Updates | All Platform Users | Real-time | Help Desk System | Support Team | Issue resolution and status updates | User satisfaction and productivity | <4 hour response time
Performance Reports | Operations Team | Daily | Monitoring Dashboard | Systems Administrator | Platform performance and usage analytics | Proactive issue identification | 99.5% uptime target
Security Briefings | Security Team | Weekly | Secure Conference Room | Security Officer | Security posture and compliance status | Risk management and compliance | 100% security review completion
Vendor Coordination | NVIDIA Support Team | As needed | Dedicated Channel | Technical Lead | Technical issues and feature requests | Vendor relationship and support | 24-hour vendor response time
Change Advisory Board | Change Management Team | Bi-weekly | CAB Meeting Room | Change Manager | Change requests and impact assessment | Change control and risk mitigation | All changes properly evaluated
User Feedback Sessions | Power Users and Champions | Monthly | Focus Group Rooms | User Experience Lead | Platform feedback and improvement suggestions | Continuous improvement and adoption | Monthly feedback collection
Department Liaison Updates | Department Representatives | Weekly | Department Meetings | Project Coordinator | Department-specific updates and requirements | Departmental alignment and support | 100% department representation
Quality Assurance Reports | QA Team | Bi-weekly | QA Portal | QA Manager | Testing results and quality metrics | Quality control and defect management | Zero critical defects in production
Budget Review Meetings | Finance Team | Monthly | Finance Conference Room | Project Manager | Financial status and budget tracking | Financial oversight and cost control | On-budget delivery tracking
Risk Assessment Updates | Risk Management Team | Weekly | Risk Management Portal | Risk Manager | Risk register updates and mitigation status | Risk identification and management | 95% risk mitigation completion
Partner Coordination | External Integration Partners | Bi-weekly | Partner Portal | Integration Lead | Integration status and collaboration needs | Partner relationship and delivery | Partner deliverable tracking
Compliance Reviews | Compliance Team | Monthly | Compliance Meeting Room | Compliance Officer | Regulatory compliance and audit status | Regulatory adherence and documentation | 100% compliance requirement met
All-Hands Updates | Entire Organization | Monthly | Town Hall + Webcast | Executive Sponsor | Organization-wide progress and achievements | Organizational awareness and engagement | 75% employee participation
Success Story Communications | All Stakeholders | Quarterly | Internal Newsletter + Portal | Communications Lead | Project wins and user success stories | Momentum building and recognition | Quarterly story publication
Knowledge Transfer Sessions | Future Support Team | Weekly during transition | Training Rooms | Subject Matter Experts | Operational procedures and troubleshooting | Knowledge retention and continuity | 100% procedure documentation
Business Value Reports | Business Stakeholders | Monthly | Executive Reports | Business Analyst | ROI metrics and business impact analysis | Value demonstration and justification | Monthly value tracking
Innovation Showcases | Creative Community | Quarterly | Innovation Lab | Innovation Lead | New techniques and creative possibilities | Innovation adoption and exploration | Quarterly showcase events
Customer Success Stories | External Clients | Quarterly | Marketing Channels | Marketing Team | Client outcomes and platform benefits | External validation and case studies | Quarterly case study publication