## Cover
Requirements
Delivery Document
Generated: | November 15, 2025
Solution: | Omniverse Enterprise
Customer Name: | Data table for requirements
Version: | 1.0

## Requirements
Requirement ID | Category | Requirement Description | Priority | Type | Status | Validation Criteria | Business Justification | Technical Specification | Acceptance Criteria
REQ-001 | Infrastructure | Deploy high-availability Nucleus server cluster | Critical | Functional | Completed | 99.9% uptime with automatic failover | Business continuity and collaboration reliability | 3-node cluster with load balancing and redundancy | Cluster operational with tested failover procedures
REQ-002 | Hardware | NVIDIA RTX A6000 workstations for creative teams | Critical | Functional | Completed | Real-time ray tracing performance benchmarks | Professional 3D content creation requirements | RTX A6000 48GB VRAM with certified drivers | Workstations meet performance specifications
REQ-003 | Software | Omniverse Enterprise licensing for 300+ users | Critical | Functional | Completed | Valid licenses for all active users | Legal compliance and feature access | Enterprise subscription with concurrent user management | License compliance verification completed
REQ-004 | Network | 10Gbps backbone network infrastructure | Critical | Performance | Completed | 10Gbps throughput with <5ms latency | High-bandwidth 3D asset collaboration | Fiber optic backbone with managed switches | Network performance targets achieved
REQ-005 | Storage | 500TB high-performance shared storage system | Critical | Functional | Completed | IOPS and throughput benchmarks met | Large 3D asset storage and versioning | NVMe SSD array with redundancy | Storage performance and capacity validated
REQ-006 | Security | Enterprise SSO integration with MFA | Critical | Security | Completed | 100% authentication through corporate SSO | Security policy compliance and user convenience | SAML 2.0 integration with Active Directory | SSO authentication functioning for all users
REQ-007 | Integration | Maya 2024 connector deployment | High | Functional | Completed | Seamless Maya-Omniverse workflow | Artist productivity and workflow continuity | Omniverse Connector for Maya with USD support | 150 Maya seats successfully integrated
REQ-008 | Integration | 3ds Max 2024 connector deployment | High | Functional | Completed | Real-time 3ds Max synchronization | 3ds Max workflow integration requirements | Omniverse Connector for 3ds Max with live sync | 75 3ds Max seats successfully integrated
REQ-009 | Integration | Blender LTS connector deployment | Medium | Functional | Completed | Blender-Omniverse collaborative workflows | Open-source tool integration and cost optimization | Blender Omniverse Connector with USD export/import | 50 Blender seats successfully integrated
REQ-010 | Performance | Sub-second asset synchronization | High | Performance | Completed | <1 second sync for assets under 100MB | Real-time collaboration efficiency | Optimized network protocols and caching | Synchronization performance targets met
REQ-011 | Backup | Automated daily backup of all USD assets | Critical | Operational | Completed | Daily backup completion with 99.5% success rate | Data protection and business continuity | Automated backup system with versioning | Backup system operational and tested
REQ-012 | Monitoring | Real-time platform performance monitoring | High | Operational | Completed | Comprehensive performance dashboards | Proactive issue identification and resolution | Performance monitoring with alerting | Monitoring system deployed and configured
REQ-013 | Training | Comprehensive user training program | High | Operational | Completed | 85% user training completion rate | User adoption and productivity | Multi-tier training curriculum with certification | Training program completed successfully
REQ-014 | Documentation | Complete technical and user documentation | Medium | Operational | Completed | Documentation coverage for all major workflows | Knowledge transfer and self-service support | Comprehensive documentation portal | Documentation portal live and accessible
REQ-015 | Compliance | ISO 27001 security compliance | Critical | Security | Completed | Security audit passed | Regulatory compliance and risk management | Security controls and audit trail | Compliance certification maintained
REQ-016 | Scalability | Support for 500+ concurrent users | High | Performance | Completed | Platform performance under maximum load | Future growth and adoption scalability | Load balancing and resource optimization | Load testing passed for 500+ users
REQ-017 | Disaster Recovery | RTO of 4 hours and RPO of 1 hour | Critical | Operational | Completed | Disaster recovery testing validates targets | Business continuity and data protection | Geographic redundancy and backup systems | DR testing completed successfully
REQ-018 | Mobile Access | Read-only mobile access for executives | Medium | Functional | In Progress | Mobile app functionality for iOS and Android | Executive visibility and remote access | Omniverse View mobile application | Mobile access functionality validated
REQ-019 | Analytics | Usage analytics and reporting dashboard | Medium | Operational | Completed | Comprehensive usage and performance reports | Data-driven decision making and optimization | Analytics platform with custom dashboards | Analytics dashboards operational
REQ-020 | API Integration | REST API for custom integrations | Medium | Technical | Completed | API functionality and documentation | Third-party tool integration flexibility | RESTful API with authentication and rate limiting | API documentation and testing completed
REQ-021 | Content Library | Centralized asset library with tagging | High | Functional | Completed | Asset discovery and metadata management | Asset reuse and collaboration efficiency | USD-based asset library with search capabilities | Asset library functional with metadata
REQ-022 | Version Control | Comprehensive version control for all assets | High | Functional | Completed | Version history and branching capabilities | Asset management and collaboration safety | Git-based version control with USD integration | Version control system operational
REQ-023 | Rendering | Distributed rendering capabilities | Medium | Performance | Completed | Render farm integration and job scheduling | High-quality output generation efficiency | Omniverse Farm deployment with job management | Render farm operational and tested
REQ-024 | Collaboration | Real-time multi-user scene editing | Critical | Functional | Completed | Simultaneous editing without conflicts | Core collaboration value proposition | Live sync with conflict resolution | Multi-user editing functionality validated
REQ-025 | Quality Assurance | Automated quality checks for USD assets | Medium | Operational | Completed | Asset validation and quality reporting | Asset quality and workflow consistency | USD validation tools and automated checking | Quality assurance system operational
REQ-026 | Notification | Real-time collaboration notifications | Medium | Functional | Completed | Push notifications for collaboration events | User awareness and workflow coordination | In-platform and email notification system | Notification system functional and tested
REQ-027 | Workspace | Virtual workspaces for project organization | Medium | Functional | Completed | Project-based workspace management | Project organization and access control | Workspace creation and permission management | Workspace functionality operational
REQ-028 | Extension | Support for custom Omniverse extensions | Low | Technical | Completed | Extension development and deployment framework | Platform customization and specialized workflows | Extension SDK and deployment infrastructure | Extension framework available and documented
REQ-029 | Localization | Multi-language support for global teams | Low | Functional | Planned | UI localization for primary languages | Global team collaboration and accessibility | Internationalization framework with language packs | Localization requirements defined
REQ-030 | Physics | Real-time physics simulation capabilities | Medium | Functional | Completed | Physics simulation performance and accuracy | Advanced simulation and visualization requirements | PhysX integration with real-time capabilities | Physics simulation functionality validated
REQ-031 | AI Integration | AI-powered asset optimization | Low | Functional | Planned | AI model integration and performance | Workflow automation and asset optimization | NVIDIA AI model integration framework | AI integration requirements defined
REQ-032 | Cloud Hybrid | Hybrid cloud and on-premises deployment | High | Architecture | Completed | Seamless cloud and on-premises integration | Flexibility and scalability for global teams | Omniverse Cloud integration with local Nucleus | Hybrid deployment operational
REQ-033 | Materials | Advanced material authoring and sharing | Medium | Functional | Completed | Material library and real-time preview | High-quality visual content creation | MDL material support with real-time rendering | Material authoring system operational
REQ-034 | Audio | Spatial audio integration for immersive content | Low | Functional | Planned | 3D audio positioning and playback | Immersive content creation capabilities | Spatial audio framework with USD integration | Audio integration requirements defined
REQ-035 | VR/AR | Virtual and augmented reality preview modes | Low | Functional | Planned | VR/AR headset integration and performance | Immersive content preview and review | VR/AR SDK integration with real-time rendering | VR/AR integration requirements defined
REQ-036 | Automation | Workflow automation and scripting | Medium | Operational | Completed | Custom script execution and scheduling | Repetitive task automation and efficiency | Python scripting framework with API access | Automation framework operational
REQ-037 | Collaboration | External partner collaboration capabilities | Medium | Functional | Completed | Secure external user access and permissions | Client and vendor collaboration requirements | Guest access with limited permissions | External collaboration functionality tested
REQ-038 | Performance | GPU cluster management and optimization | High | Performance | Completed | GPU resource allocation and monitoring | Maximum GPU utilization and performance | GPU cluster management with workload balancing | GPU cluster operational and optimized
REQ-039 | Standards | USD format compliance and optimization | High | Technical | Completed | Full USD specification compliance | Industry standard adoption and interoperability | USD 23.x compliance with optimization | USD compliance validated and tested
REQ-040 | Workflow | Custom workflow templates and automation | Medium | Operational | Completed | Template creation and workflow automation | Standardized processes and efficiency | Workflow template system with automation | Workflow templates operational
REQ-041 | Support | 24/7 technical support during implementation | High | Operational | Completed | Support response time and resolution SLAs | Implementation risk mitigation | Dedicated support channel with escalation | Support SLAs met during implementation
REQ-042 | Migration | Legacy asset migration to USD format | Medium | Operational | Completed | Asset conversion accuracy and completeness | Existing asset value preservation | Automated migration tools with validation | Asset migration completed successfully
REQ-043 | Testing | Comprehensive testing environment | High | Operational | Completed | Full testing coverage for all workflows | Quality assurance and risk mitigation | Isolated testing environment with test data | Testing environment operational
REQ-044 | Capacity | Auto-scaling for variable workloads | Medium | Performance | Completed | Dynamic resource allocation based on demand | Cost optimization and performance | Cloud-based auto-scaling with monitoring | Auto-scaling functionality validated
REQ-045 | Integration | CAD application integration support | Medium | Functional | Completed | SolidWorks and Fusion 360 connectivity | Engineering workflow integration | CAD connector deployment with data exchange | CAD integration operational and tested
REQ-046 | Governance | Data governance and lifecycle management | High | Operational | Completed | Data retention and archival policies | Compliance and storage optimization | Automated lifecycle management with policies | Data governance policies implemented
REQ-047 | Innovation | Innovation lab for experimental features | Low | Operational | Planned | Sandbox environment for feature testing | Innovation and competitive advantage | Isolated environment with experimental access | Innovation lab requirements defined
REQ-048 | Metrics | Business value and ROI tracking | High | Operational | Completed | ROI measurement and reporting framework | Business justification and optimization | Analytics platform with business metrics | ROI tracking system operational
REQ-049 | Knowledge | Knowledge base and self-service support | Medium | Operational | Completed | Comprehensive knowledge base with search | User self-service and support efficiency | Knowledge management platform with content | Knowledge base operational and populated
REQ-050 | Future | Roadmap planning for future enhancements | Medium | Strategic | Planned | Strategic roadmap with timeline and priorities | Continuous improvement and evolution | Roadmap framework with stakeholder input | Future planning process established