# Statement of Work

NVIDIA - Omniverse Enterprise Collaboration Platform Implementation

| Client: | [Client Name] |
| --- | --- |
| Date: | November 22, 2025 |
| Consulting Company: | Your Consulting Company |
| Submitted By: | [Consultant Name ¦ Email ¦ Phone] |
| Opportunity No: | OPP-2025-001 |
| Version: | 1.0 |

# Table of Contents

1 Introduction
    1.1 Purpose
        1.1.1 Scope
2 Table Content
3 Image Section
4 Additional Content
5 Sign-Off

# List of Figures

Figure 1: Sample Architecture Diagram

# List of Tables

Table 1: Sample Deliverables Table

# 1 Executive Summary

This Statement of Work (SOW) defines the scope, deliverables, roles, and terms for implementing NVIDIA Omniverse Enterprise Collaboration Platform for [Client Name]. This engagement will deliver real-time 3D design collaboration capabilities through 50 RTX-powered workstations, Omniverse Nucleus servers, and Universal Scene Description (USD) workflows to enable 50 engineers and designers to collaborate simultaneously on complex 3D projects.

Project Duration: [X] months

# 2 Background & Objectives

## 2.1 Current State

[Client Name] currently faces significant challenges in 3D design collaboration and rendering workflows:

• File Format Silos: Multiple CAD tools (Revit, SolidWorks, Rhino, Maya) with incompatible file formats requiring manual conversion

• Sequential Workflows: Designers work in isolation, passing files sequentially causing weeks of delays per project cycle

• Rendering Bottlenecks: CPU-based rendering takes 8+ hours per scene, limiting design iterations

• Version Control Chaos: Email-based file sharing with dozens of file versions creating confusion and rework

• Remote Collaboration Limits: Remote teams cannot effectively collaborate on 3D designs in real-time

## 2.2 Business Objectives

• Enable Real-Time Collaboration: Deploy Omniverse Enterprise platform enabling 50 engineers to work simultaneously on same 3D scene with live updates

• Eliminate File Conversion: Implement Universal Scene Description (USD) workflows connecting native CAD tools (Revit, SolidWorks, Rhino, Blender, Maya) without file conversion

• Accelerate Rendering: Reduce rendering time by 90% through RTX real-time ray tracing (8 hours to 45 minutes per scene)

• Streamline Workflows: Create photorealistic product visualizations before manufacturing, reducing physical prototyping costs by 60%

• Support Remote Teams: Enable distributed teams to collaborate via Omniverse with cloud streaming for remote workstation access

• Build Digital Twins: Establish foundation for factory simulation and optimization with Omniverse-powered digital twins

## 2.3 Success Metrics

• 50 RTX workstations operational with Omniverse Enterprise licenses

• Enable real-time collaboration: 10+ users simultaneously editing same USD scene

• Reduce rendering time by 90% vs CPU baseline (8 hours to 45 minutes)

• Support 5+ CAD tool connectors (Revit, SolidWorks, Rhino, Blender, Maya)

• Achieve 100 TB USD scene storage capacity with version control

• 99.5% Nucleus server uptime for collaboration workflows

• Reduce physical prototyping costs by $500K annually through virtual visualization

# 3 Scope of Work

## 3.1 In Scope

The following services and deliverables are included in this SOW:

• Omniverse Enterprise architecture design and capacity planning

• RTX workstation procurement, installation, and configuration (50 workstations)

• Omniverse Nucleus server deployment (primary + replica for HA)

• Storage infrastructure deployment (NetApp AFF 100 TB for USD scenes)

• Omniverse Connector integration (Revit, SolidWorks, Rhino, Blender, Maya)

• Rendering farm deployment (optional: 10 Omniverse Farm licenses)

• User training for designers and engineers

• USD workflow development and best practices

• Knowledge transfer and documentation

### 3.1.1 Scope Parameters

This engagement is sized based on the following parameters:

| Category | Parameter | Scope |
| --- | --- | --- |
| Solution Scope | GPU Workstations | 50x RTX A6000 workstations |
| Solution Scope | Nucleus Servers | 2x Nucleus servers (HA) |
| Integration | Design Team Size | 50 designers and engineers |
| Integration | Storage Infrastructure | 100 TB USD scene storage |
| Data Volume | 3D Scene Data | Multi-TB project files |
| Data Volume | Rendering Workloads | Interactive + batch rendering |
| Technical Environment | Network Infrastructure | 100 GbE network |
| Technical Environment | Datacenter Readiness | Standard IT infrastructure |
| Technical Environment | Deployment Model | On-premises deployment |
| Security & Compliance | Data Classification | Proprietary 3D designs |
| Security & Compliance | Compliance Requirements | Standard security |
| Performance | Real-Time Collaboration | 50 concurrent users |
| Performance | Rendering Performance | RTX ray tracing |
| Environment | CAD Tool Connectors | 5 primary connectors |
| Environment | Rendering Farm | 10 GPU render nodes |

Table 1: Engagement Scope Parameters

Table: Engagement Scope Parameters

Note: Changes to these parameters may require scope adjustment and additional investment.

## 3.2 Activities

### 3.2.1 Phase 1 – Discovery & Assessment

During this initial phase, the Vendor will perform a comprehensive assessment of the Client's 3D design workflows, existing CAD tools, and collaboration requirements. This includes analyzing current processes, identifying integration needs, and designing the optimal Omniverse Enterprise architecture.

Key activities:

• 3D design workflow analysis and collaboration requirements gathering

• CAD tool inventory and connector requirements (Revit, SolidWorks, Rhino, etc.)

• Existing workstation and network infrastructure assessment

• Rendering workflow analysis and performance benchmarking

• Storage capacity planning for USD scenes and asset libraries

• Security and intellectual property protection requirements

• Omniverse architecture design (Nucleus, connectors, rendering farm)

• Remote collaboration and cloud streaming requirements

• Implementation planning and resource allocation

This phase concludes with an Assessment Report that outlines the proposed Omniverse architecture, CAD tool integration strategy, USD workflow design, risks, and project timeline.

### 3.2.2 Phase 2 – Infrastructure Deployment

In this phase, the Nucleus servers and storage infrastructure are deployed based on NVIDIA Omniverse best practices. This includes server installation, network configuration, and storage setup.

Key activities:

• Omniverse Nucleus server installation (2 servers for HA)

• Storage cluster deployment (NetApp AFF 100 TB NVMe)

• 100 GbE network switch installation and configuration

• Network infrastructure validation and bandwidth testing

• Nucleus server software installation and configuration

• High availability and failover configuration

• Storage mount configuration and access policies

• Monitoring infrastructure setup (Prometheus, Grafana)

By the end of this phase, the Client will have production-ready Nucleus server infrastructure for Omniverse collaboration.

### 3.2.3 Phase 3 – Workstation Deployment & Connector Integration

Implementation will occur in well-defined phases starting with workstation deployment, followed by Omniverse Connector installation and CAD tool integration.

Key activities:

• RTX workstation deployment (50x Dell Precision 7960 with RTX A6000)

• Workstation OS installation and configuration (Windows 11 Pro)

• NVIDIA RTX driver and software deployment

• Omniverse Enterprise client installation on all workstations

• Omniverse Connector installation and configuration:

• Autodesk Revit Connector

• Dassault SolidWorks Connector

• McNeel Rhino Connector

• Blender USD Connector

• Autodesk Maya Connector

• CAD tool integration testing and validation

• User authentication and access control configuration (Active Directory)

• Omniverse Farm deployment for batch rendering (optional: 10 nodes)

After each phase, the Vendor will coordinate validation and sign-off with the Client before proceeding.

### 3.2.4 Phase 4 – Testing & Validation

In the Testing and Validation phase, the Omniverse platform undergoes thorough functional, performance, and collaboration validation. Real design workflows will be executed to validate USD workflows and rendering performance.

Key activities:

• Single-user and multi-user collaboration testing

• USD scene synchronization and version control validation

• CAD Connector testing with representative design files

• RTX rendering performance benchmarking

• Storage throughput testing for large USD scenes

• Omniverse Farm batch rendering validation (if deployed)

• Network bandwidth and latency validation for collaboration

• Security and access control validation

• User Acceptance Testing (UAT) with design team

• Go-live readiness review and production cutover planning

Cutover will be coordinated with all relevant stakeholders and executed during an approved maintenance window.

### 3.2.5 Phase 5 – Handover & Post-Implementation Support

Following successful implementation and validation, the focus shifts to ensuring operational continuity and knowledge transfer. The Vendor will provide hypercare support and equip the Client's team with documentation and operational procedures.

Activities include:

• Delivery of as-built documentation (architecture diagrams, Nucleus configs, connector setup)

• Operations runbook and SOPs for Nucleus server management

• Administrator training (Nucleus administration, user management, storage)

• Designer training (Omniverse workflows, CAD Connectors, collaboration features)

• USD workflow development and best practices documentation

• Live or recorded knowledge transfer sessions

• Performance optimization recommendations

• 30-day warranty support for issue resolution

• Optional transition to managed services model for ongoing support, if contracted

## 3.3 Out of Scope

These items are not in scope unless added via change control:

• RTX workstation hardware beyond 50 workstations

• Third-party software licensing beyond Omniverse Enterprise

• Historical 3D asset conversion or legacy file migration

• Custom USD pipeline development or application development

• Ongoing operational support beyond 30-day warranty period

• Multi-site deployment or disaster recovery to secondary datacenter

• Custom connector development for proprietary CAD tools

• CAD software training (Revit, SolidWorks, etc.) - only Omniverse training included

• Cloud deployment or hybrid cloud scenarios

# 4 Deliverables & Timeline

## 4.1 Deliverables

| # | Deliverable | Type | Due Date | Acceptance By |
| --- | --- | --- | --- | --- |
| 1 | 3D Workflow Requirements Specification | Document/CSV | Week 2 | [Client Lead] |
| 2 | Omniverse Architecture Document | Document | Week 3 | [Technical Lead] |
| 3 | Implementation Plan | Project Plan | Week 3 | [Project Sponsor] |
| 4 | Nucleus Server Infrastructure (HA) | System | Week 7 | [Technical Lead] |
| 5 | Storage Platform (100 TB) | System | Week 7 | [Storage Lead] |
| 6 | RTX Workstations (50 deployed) | System | Week 9 | [IT Lead] |
| 7 | Omniverse Connectors (5 CAD tools) | System | Week 10 | [Design Lead] |
| 8 | Omniverse Farm (optional) | System | Week 10 | [Rendering Lead] |
| 9 | Performance Validation Report | Document | Week 11 | [Technical Lead] |
| 10 | Administrator Training Materials | Document/Video | Week 12 | [Training Lead] |
| 11 | Designer Training Materials | Document/Video | Week 12 | [Training Lead] |
| 12 | USD Workflow Documentation | Document | Week 12 | [Design Lead] |
| 13 | Operations Runbook | Document | Week 13 | [Ops Lead] |
| 14 | As-Built Documentation | Document | Week 13 | [Client Lead] |
| 15 | Knowledge Transfer Sessions | Training | Week 12-13 | [Client Team] |

Table 2: Project Deliverables and Acceptance Criteria

## 4.2 Project Milestones

| Milestone | Description | Target Date |
| --- | --- | --- |
| M1 | Assessment & Design Complete | Week 3 |
| M2 | Nucleus Infrastructure Deployed | Week 7 |
| M3 | Workstations Deployed | Week 9 |
| M4 | Connectors Integrated | Week 10 |
| M5 | Performance Validation Complete | Week 11 |
| Go-Live | Production Launch | Week 12 |
| Hypercare End | Support Period Complete | Week 16 |

Table 3: Project Milestones and Timeline

# 5 Roles & Responsibilities

## 5.1 RACI Matrix

| Task/Role | EO PM | EO Quarterback | EO Sales Eng | EO Eng (Infra) | Client IT | Client Design | SME |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Discovery & Requirements | A | R | R | C | C | R | C |
| Omniverse Architecture Design | C | A | R | I | I | C | I |
| Nucleus Server Deployment | C | R | I | A | C | I | I |
| Workstation Deployment | C | R | I | A | C | I | I |
| Connector Integration | C | R | C | A | C | R | I |
| USD Workflow Development | C | R | C | A | I | R | I |
| Performance Validation | R | C | R | A | C | A | I |
| Security Configuration | C | R | I | A | I | A | I |
| Knowledge Transfer | A | R | R | R | C | C | I |
| Hypercare Support | A | R | R | R | C | I | I |

Table 4: Roles And Responsibilities

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

## 5.2 Key Personnel

Vendor Team:

• EO Project Manager: Overall delivery accountability

• EO Quarterback: Technical design and oversight

• EO Sales Engineer: Solution architecture and pre-sales support

• EO Engineer (Infrastructure): Nucleus deployment and workstation configuration

Client Team:

• IT Lead: Primary technical contact and infrastructure access management

• Design Lead: Workflow requirements and CAD tool integration validation

• Facilities Lead: Workstation deployment coordination

• Operations Team: Knowledge transfer recipients

# 6 Architecture & Design

## 6.1 Architecture Overview

The NVIDIA Omniverse Enterprise solution is designed as a real-time collaborative 3D platform leveraging Universal Scene Description (USD), RTX-powered workstations, and Nucleus collaboration servers. The architecture provides simultaneous multi-user editing, real-time ray tracing, and seamless CAD tool integration for design teams.

This architecture is designed for enterprise 3D collaboration supporting 50 designers/engineers with real-time USD workflows. The design prioritizes:

• Real-Time Collaboration: Live synchronization of USD scenes across multiple users and CAD tools

• Performance: RTX ray tracing for photorealistic rendering in minutes vs hours

• Interoperability: Native CAD tool integration without file conversion

Figure 1: Solution Architecture Diagram

Figure 1: Solution Architecture Diagram - High-level overview of the Omniverse Enterprise collaboration platform architecture

## 6.2 Architecture Type

The deployment follows a client-server architecture with Nucleus collaboration servers and RTX workstations. This approach enables:

• Real-time multi-user collaboration on shared USD scenes

• Version control and Git-like branching/merging for 3D assets

• High-performance RTX rendering at workstation level

• Centralized asset management and storage

Key architectural components include:

• Workstation Layer (50x RTX A6000 workstations)

• Collaboration Layer (Omniverse Nucleus servers with HA)

• Storage Layer (NetApp AFF 100 TB for USD scenes)

• Connector Layer (Revit, SolidWorks, Rhino, Blender, Maya)

• Rendering Layer (Omniverse Farm for batch rendering - optional)

• Network Layer (100 GbE backbone, 10 GbE to workstations)

## 6.3 Scope Specifications

Workstations & Rendering:

• 50x Dell Precision 7960 Tower Workstations

• NVIDIA RTX A6000 48GB GPU (1 per workstation)

• Intel Xeon W-3400 series CPUs

• 128 GB DDR5 RAM per workstation

• 2 TB NVMe SSD per workstation

• Windows 11 Pro for Workstations

• Dual 4K monitors per workstation

Nucleus Collaboration Servers:

• 2x Nucleus servers (primary + replica for HA)

• Dell PowerEdge R750 or HPE DL380 Gen11

• 64 GB RAM, 2x Xeon CPUs

• Active-active replication for high availability

• Automatic failover and load balancing

Storage & Data:

• NetApp AFF A400 with 100 TB NVMe all-flash

• NFS for USD scene storage and asset libraries

• 10 GB/s sustained read/write throughput

• RAID 6 protection with hot spare capacity

• Automated snapshots and version control

Networking & Connectivity:

• 100 GbE switches for Nucleus server connectivity

• 10 GbE switches for workstation connectivity

• Dedicated VLAN for Omniverse traffic

• Load balancer for Nucleus server HA

Omniverse Software:

• Omniverse Enterprise licenses (50 users)

• Omniverse Nucleus (collaboration server)

• Omniverse Create (3D scene composition)

• Omniverse View (real-time visualization)

• CAD Connectors: Revit, SolidWorks, Rhino, Blender, Maya

• Omniverse Farm (optional: 10 rendering nodes)

Monitoring & Operations:

• Prometheus for Nucleus server metrics

• Grafana for dashboards and visualization

• Centralized logging for collaboration events

• Automated alerting for server health

Scalability Path:

• Current: 50 workstations, 100 TB storage

• Expand to 100 workstations by adding licenses

• Scale storage from 100 TB to 500 TB+ as scene complexity grows

• Add Nucleus capacity by deploying additional server pairs

## 6.4 Application Hosting

All Omniverse applications run on RTX workstations with centralized Nucleus collaboration:

• Omniverse Create for scene composition and editing

• Omniverse View for real-time visualization and reviews

• CAD tool connectors for native tool integration

• Omniverse Farm for batch rendering (server-hosted)

All USD scenes and assets are stored centrally on Nucleus servers.

## 6.5 Networking

The networking architecture follows Omniverse best practices:

• 100 GbE for Nucleus server interconnect and storage

• 10 GbE for workstation connectivity (sufficient for USD sync)

• Dedicated VLAN for Omniverse traffic separation

• Load balancer for Nucleus HA and traffic distribution

• QoS policies for prioritizing collaboration traffic

## 6.6 Observability

Comprehensive observability ensures operational excellence:

• Nucleus server health and performance monitoring

• User session and collaboration metrics

• Storage capacity and throughput monitoring

• Network bandwidth utilization

• Custom dashboards for collaboration KPIs (active users, scenes, rendering jobs)

## 6.7 Backup & Disaster Recovery

All critical data and configurations are protected through:

• Automated daily snapshots of USD scenes and assets

• RAID 6 protection for storage with hot spares

• Nucleus configuration backups

• Offsite backup replication (optional) for disaster recovery

• RTO: 4 hours | RPO: 1 hour

## 6.8 Technical Implementation Strategy

The implementation approach follows NVIDIA Omniverse best practices for enterprise deployments.

## 6.9 Example Implementation Patterns

• Phased deployment: Deploy Nucleus first, then pilot workstations, then full rollout

• Pilot teams: Start with 5-10 designers to validate workflows before full deployment

• Connector rollout: Deploy one CAD connector at a time with validation

## 6.10 Tooling Overview

| Category | Primary Tools | Purpose |
| --- | --- | --- |
| Workstations | Dell Precision 7960 | RTX A6000 workstations |
| Collaboration | Omniverse Nucleus | USD scene server and sync |
| Rendering | RTX A6000 GPUs | Real-time ray tracing |
| Storage | NetApp AFF A400 | High-performance USD storage |
| CAD Integration | Omniverse Connectors | Native tool integration |
| Composition | Omniverse Create | 3D scene editing |
| Visualization | Omniverse View | Real-time visualization |
| Batch Rendering | Omniverse Farm (optional) | Server-based rendering |
| Monitoring | Prometheus, Grafana | Server health and metrics |

Table 5: Implementation Tools and Technologies

## 6.11 Data Management

### 6.11.1 Data Strategy

• Centralized USD scene storage on Nucleus servers

• Version control and branching for 3D assets (Git-like)

• Asset library for shared materials and components

• Automated scene optimization and LOD generation

• Lifecycle management for archived projects

### 6.11.2 Data Security & Compliance

• Encryption enabled for data in-transit and at-rest

• RBAC for scene and asset access control

• Audit trail for all scene access and modifications

• Intellectual property protection for proprietary designs

• Secure deletion capabilities for confidential projects

# 7 Security & Compliance

The implementation and target environment will be architected and validated to meet the Client's security, compliance, and governance requirements. Vendor will adhere to industry-standard security frameworks and NVIDIA Omniverse best practices.

## 7.1 Identity & Access Management

• Active Directory integration for user authentication

• Role-based access control (RBAC) for USD scene access

• Multi-factor authentication (MFA) for Nucleus server access

• Workstation authentication via Active Directory

• Project-based access controls for sensitive designs

## 7.2 Monitoring & Threat Detection

• Centralized logging for all Nucleus server events

• Automated alerts for unauthorized access attempts

• Network monitoring for anomalous traffic patterns

• Regular security patch management for servers and workstations

• Security scanning for Nucleus server vulnerabilities

## 7.3 Compliance & Auditing

• SOC 2 certified infrastructure components

• Intellectual property protection controls

• Comprehensive audit trail for all scene access and edits

• Regular compliance assessments and reporting

• Documented security policies and procedures

## 7.4 Encryption & Key Management

• TLS 1.3 encryption for all Nucleus communications

• Encryption at rest for USD scene storage

• Secure key management for workstation access

• Encrypted backup and replication

• Regular encryption key rotation

## 7.5 Governance

• Change control: All Nucleus configuration changes require approval

• Access reviews: Quarterly review of user access and permissions

• Project access policies: Confidential projects with restricted access

• Incident response: Documented procedures for security incidents

• Asset management: Tracking of all workstations and licenses

## 7.6 Environments & Access

### 7.6.1 Environment Strategy

| Environment | Purpose | Implementation | Access |
| --- | --- | --- | --- |
| Production | Live 3D design collaboration | Nucleus cluster with HA | All authorized users |
| Training | User training and workflow testing | Separate Nucleus namespace | Training team |
| Pilot | Pre-production workflow validation | Dedicated pilot projects | Pilot user group |

Table 6: Security And Compliance

### 7.6.2 Access Policies

• Multi-factor authentication (MFA) required for Nucleus admin access

• Active Directory authentication for workstation and Nucleus access

• Administrator Access: Full Nucleus management for IT team

• Designer Access: Scene creation, editing, and collaboration

• Viewer Access: Read-only access for stakeholders and reviewers

# 8 Testing & Validation

Comprehensive testing and validation will take place throughout the implementation lifecycle to ensure functionality, performance, security, and reliability of the Omniverse platform.

## 8.1 Functional Validation

• End-to-end USD collaboration workflow validation

• Multi-user simultaneous editing of same scene

• CAD Connector functionality with representative files

• Version control and branching validation

• Scene synchronization and conflict resolution testing

• User authentication and access control validation

## 8.2 Performance & Load Testing

• Single-user and multi-user collaboration performance

• RTX rendering performance benchmarking (vs CPU baseline)

• Storage throughput testing for large USD scenes

• Network bandwidth validation for collaboration

• Concurrent user testing (10+ users per scene)

• Omniverse Farm rendering performance (if deployed)

## 8.3 Security Testing

• Access control and authentication validation

• Encryption validation (data at rest and in transit)

• Intellectual property protection testing

• Audit trail validation

• Vulnerability scanning and penetration testing

## 8.4 Disaster Recovery & Resilience Tests

• Nucleus failover and HA validation

• Storage failover and RAID rebuild testing

• Backup and restore validation

• Network redundancy testing

• Workstation failure and recovery

## 8.5 User Acceptance Testing (UAT)

• Performed in coordination with Client design team

• Real design workflows executed on Omniverse

• CAD Connector validation with production files

• Collaboration workflow and user experience testing

• Training materials and documentation validation

## 8.6 Go-Live Readiness

A Go-Live Readiness Checklist will be delivered including:

• Security and compliance sign-offs

• Performance benchmarking completion (90% rendering improvement)

• Multi-user collaboration validation (10+ concurrent users)

• CAD Connector functionality validation

• Infrastructure reliability checks

• Issue log closure (all critical/high issues resolved)

• Training completion

• Documentation delivery

## 8.7 Cutover Plan

The cutover to the NVIDIA Omniverse Enterprise platform will be executed using a controlled, phased approach to minimize business disruption and ensure seamless adoption.

Cutover Approach:

The implementation follows a pilot-first strategy with gradual rollout:

1. Pilot Phase (Week 1-2): Deploy 5-10 pilot workstations and onboard early adopter designers. Validate USD workflows, CAD Connectors, and collaboration features with pilot projects.

2. Workflow Validation (Week 3): Execute end-to-end design workflows with pilot team. Gather feedback, optimize configurations, and document best practices.

3. Progressive Rollout (Week 4-6): Deploy remaining 40-45 workstations in waves:

• Week 4: Deploy 15 workstations (architecture team)

• Week 5: Deploy 15 workstations (engineering team)

• Week 6: Deploy 15 workstations (visualization team)

4. Hypercare Period (4 weeks post-rollout): Daily monitoring, rapid issue resolution, and workflow optimization.

## 8.8 Cutover Checklist

• Pre-cutover validation: Pilot team sign-off, UAT completion

• Nucleus infrastructure validated and monitoring operational

• Workstations deployed and configured

• CAD Connectors tested with representative files

• User training completed

• Documentation delivered

• Daily monitoring during hypercare period (4 weeks)

## 8.9 Rollback Strategy

• Documented rollback triggers (Nucleus failures, data corruption, performance issues)

• Rollback procedures: Revert to existing CAD workflows

• Root cause analysis and fix validation before retry

• Communication plan for stakeholders

• Preserve all logs and scene data for analysis

# 9 Handover & Support

## 9.1 Handover Artifacts

• As-Built documentation including architecture diagrams, Nucleus configs, and network topology

• Omniverse operations runbook with troubleshooting procedures

• Nucleus administration guide and best practices

• USD workflow documentation and design guidelines

• CAD Connector configuration and usage guides

• Monitoring and alert configuration reference

• Performance optimization recommendations

## 9.2 Knowledge Transfer

• Live knowledge transfer sessions for administrators and designers

• Nucleus server administration training

• Workstation configuration and troubleshooting

• USD workflow development and best practices

• CAD Connector usage and integration

• Omniverse Create and View training

• Collaboration features and version control

• Recorded training materials hosted in shared portal

• Documentation portal with searchable content

## 9.3 Hypercare Support

Post-implementation support to ensure smooth transition to Client operations:

Duration: 4 weeks post-go-live (30 days)

Coverage:

• Business hours support (8 AM - 6 PM local time)

• 4-hour response time for critical issues

• Daily health check calls (first 2 weeks)

• Weekly status meetings

Scope:

• Issue investigation and resolution

• Performance tuning and workflow optimization

• Configuration adjustments

• Knowledge transfer continuation

• CAD Connector troubleshooting

• User workflow assistance

## 9.4 Managed Services Transition (Optional)

Post-hypercare, Client may transition to ongoing managed services:

Managed Services Options:

• 24/7 monitoring and support for Nucleus infrastructure

• Proactive optimization and capacity planning

• Workstation configuration management

• User license management and optimization

• Monthly performance reviews

• Hardware failure remediation

Transition Approach:

• Evaluation of managed services requirements during hypercare

• Service Level Agreement (SLA) definition for Nucleus availability

• Separate managed services contract and pricing

• Seamless transition from hypercare to managed services

## 9.5 Assumptions

### 9.5.1 General Assumptions

• Datacenter facility has adequate space and power for Nucleus servers

• Workstation locations have adequate space and power infrastructure

• Network infrastructure supports 10 GbE to workstations, 100 GbE for servers

• Client technical team will be available for requirements validation and testing

• Existing CAD tool licenses are in place (Revit, SolidWorks, Rhino, Blender, Maya)

• Design workflows will remain stable during implementation

• Client will handle Omniverse Enterprise licensing costs directly

• Sufficient lead time for hardware procurement (8-10 weeks for workstations)

## 9.6 Dependencies

### 9.6.1 Project Dependencies

• Datacenter Readiness: Power and space for Nucleus servers

• Workstation Locations: Space prepared for 50 workstations

• Network Infrastructure: 10 GbE to workstations, 100 GbE backbone

• Client IT Access: Administrative access to servers, network, and Active Directory

• CAD Tool Access: Existing CAD software installations and licenses

• SME Availability: Design team available for workflow testing

• Security Approvals: Security and compliance approvals on schedule

• Vendor Coordination: NVIDIA and Dell support during deployment

• Change Freeze: No major infrastructure changes during deployment

• Go-Live Approval: Business and technical approval for production

# 10 Investment Summary

Enterprise 3D Collaboration Platform: This pricing reflects an enterprise Omniverse deployment with 50 RTX workstations designed for real-time 3D collaboration supporting architects, engineers, and designers. Total capacity: 50 users, 100 TB USD storage.

## 10.1 Total Investment

| Cost Category | Year 1 List | AWS/Partner Credits | Year 1 Net | Year 2 | Year 3 | 3-Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Professional Services | $113,200 | $0 | $113,200 | $0 | $0 | $113,200 |
| Hardware | $1,172,000 | ($37,500) | $1,134,500 | $0 | $0 | $1,134,500 |
| Software Licenses | $99,000 | ($9,000) | $90,000 | $104,000 | $104,000 | $298,000 |
| Support & Maintenance | $109,000 | $0 | $109,000 | $109,000 | $109,000 | $327,000 |
| TOTAL INVESTMENT | $1,493,200 | ($46,500) | $1,446,700 | $213,000 | $213,000 | $1,872,700 |

Table 7: Total Investment Summary

## 10.2 Partner Credits

Year 1 Credits Applied: $50,000 (4% reduction)

• NVIDIA Partner Implementation Credit: $50,000 applied to RTX workstation hardware

• Credits are real NVIDIA account credits, applied to hardware procurement

• Credits are Year 1 only; hardware is one-time purchase

Investment Comparison:

• Year 1 Net Investment: $1,189,500 (after credits) vs. $1,239,500 list price

• 3-Year Total Cost of Ownership: $1,557,500

• Expected ROI: 2.2 year payback through reduced prototyping costs and faster time-to-market

• Annual Savings: $500K reduction in physical prototyping through virtual visualization

## 10.3 Cost Components

Professional Services ($49,500 - 220 hours): Labor costs for deployment, configuration, and training. Breakdown:

• Assessment & Architecture (40 hours): Workflow analysis, Omniverse design

• Installation & Configuration (140 hours): Servers, workstations, connectors

• Testing & Validation (20 hours): Performance validation, UAT

• Training & Support (20 hours): Knowledge transfer and hypercare

Hardware Infrastructure ($1,006,000 one-time): Workstations, servers, networking, and storage:

• 50x Dell Precision 7960 with RTX A6000 48GB: $750,000

• 2x Nucleus Servers (Dell PowerEdge R750): $100,000

• 100 GbE Switches (2x for redundancy): $36,000

• NetApp AFF A400 100 TB NVMe Storage: $120,000

Software Licenses & Subscriptions ($99,000/year): Omniverse Enterprise platform:

• Omniverse Enterprise (50 user licenses): $90,000/year

• Omniverse Farm (10 rendering node licenses - optional): $9,000/year

• Includes: Nucleus, Create, View, Connectors, RTX rendering, enterprise support

Support & Maintenance ($85,000/year): Ongoing hardware and software support:

• Dell ProSupport Plus (50 workstations + 2 servers): $60,000/year

• NVIDIA Omniverse Enterprise Support: $25,000/year

• 24/7 hardware support, firmware updates, technical assistance

## 10.4 Payment Terms

### 10.4.1 Pricing Model

• Fixed price for professional services

• Hardware procured at vendor list pricing (minus credits)

• Annual subscription pricing for software and support

### 10.4.2 Payment Schedule

• 20% upon SOW execution and project kickoff

• 60% upon hardware delivery and installation completion

• 15% upon successful performance validation

• 5% upon go-live and project acceptance

## 10.5 Invoicing & Expenses

### 10.5.1 Invoicing

• Milestone-based invoicing per Payment Terms above

• Net 30 payment terms

• Invoices submitted upon milestone completion and acceptance

### 10.5.2 Expenses

• Hardware costs are one-time purchase ($1.01M Year 1, included in pricing)

• Annual software licenses billed annually ($99K/year)

• Annual support billed annually ($85K/year)

• Travel and on-site expenses reimbursable at cost with prior approval

• Estimated 3-4 on-site visits during deployment phase

# 11 Terms & Conditions

## 11.1 General Terms

All services will be delivered in accordance with the executed Master Services Agreement (MSA) or equivalent contractual document between Vendor and Client.

## 11.2 Scope Changes

• Changes to workstation count, Nucleus capacity, or timeline require formal change requests

• Hardware lead times (8-10 weeks) may impact change request feasibility

• Change requests may impact project timeline and budget

## 11.3 Intellectual Property

• Client retains ownership of all 3D designs, USD scenes, and assets

• Vendor retains ownership of proprietary deployment methodologies

• NVIDIA retains ownership of Omniverse software and tools

• Custom USD workflows and scripts transfer to Client upon final payment

## 11.4 Service Levels

• Nucleus server availability: 99.5% uptime during business hours

• RTX workstation availability: 99% operational

• 30-day warranty on all deliverables from go-live date

• Post-warranty support available under separate managed services agreement

## 11.5 Liability

• Performance guarantees apply to NVIDIA-validated benchmark workflows

• Custom USD workflow performance may vary

• Hardware warranty provided by Dell/NetApp per standard terms

• Liability caps as agreed in MSA

## 11.6 Confidentiality

• Both parties agree to maintain strict confidentiality of designs, USD scenes, and methodologies

• All exchanged artifacts under NDA protection

• Intellectual property protection for Client designs

## 11.7 Termination

• Mutually terminable per MSA terms, subject to payment for completed work

• Hardware procurement is non-refundable once ordered (8-10 week lead time)

## 11.8 Governing Law

• Agreement governed under the laws of [State/Region]

# 12 Sign-Off

By signing below, both parties agree to the scope, approach, and terms outlined in this Statement of Work.

| CLIENT | CONSULTING COMPANY |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Title: ___________________________ | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

eoframework.org