## Cover
[DOCUMENT TITLE]
Level of Effort
HASHICORP - Cloud - Multi Cloud Platform
| Generated: | November 16, 2025
| Solution: | [Solution Name]
| Customer: | [Customer Name]
| Version: | 1.0
| Status: | Draft
eoframework.org

## Scope Assumptions
SCOPE ASSUMPTIONS - BASELINE (MULTIPLIER 1.0)
Category | Baseline Assumption | Current Scope | Small (1x) | Medium (2x) | Large (3x) | Notes
Solution Scope | Managed Cloud Providers | 3 clouds (AWS Azure GCP) | 2 clouds | 3 clouds | 4+ clouds + on-prem | Number of cloud platforms to manage
Solution Scope | Infrastructure Resources | 2500 total resources | 500 resources | 2500 resources | 10000+ resources | Total managed infrastructure across all clouds
Solution Scope | Terraform Workspaces | 100 workspaces | 25 workspaces | 100 workspaces | 500+ workspaces | Isolated environment and team workspaces
Integration | External System Integrations | 4 integrations (GitHub Datadog Slack ServiceNow) | 2 integrations | 4-6 integrations | 8+ integrations | VCS monitoring ITSM tools
Integration | VCS Platform | GitHub | GitHub or GitLab | Multiple VCS platforms | Complex multi-VCS with custom workflows | Version control system integration
User Base | Total Platform Users | 50 users | 10 users | 50 users | 200+ users | Platform operators and developers
User Base | User Roles | 5 roles (viewer operator admin security auditor) | 3 roles | 5 roles | 8+ roles with complex permissions | RBAC and access control structure
Data Volume | Concurrent Infrastructure Runs | 15 concurrent runs | 5 concurrent | 15 concurrent | 50+ concurrent | Parallel Terraform operations
Data Volume | State Storage Volume | 2 TB | 500 GB | 2 TB | 10+ TB | Terraform state files and backups
Technical Environment | Deployment Regions | Multi-region (us-east-1 eu-west-1 ap-southeast-1) | Single region | Multi-region | Global multi-region HA | Platform deployment footprint
Technical Environment | Availability Requirements | High (99.9%) | Standard (99.5%) | High (99.9%) | Mission critical (99.95%+) | Platform uptime SLA
Technical Environment | Infrastructure Complexity | Multi-cloud with networking | Single cloud basic | Multi-cloud with networking | Multi-cloud with service mesh | Terraform Vault Consul integration
Security & Compliance | Security Requirements | Enterprise (Vault SSO RBAC) | Basic IAM | Enterprise security | Advanced with HSM | Secrets management and access control
Security & Compliance | Compliance Frameworks | SOC2 ISO27001 | 1-2 basic standards | 2-3 standards | Multiple complex frameworks | Governance and audit requirements
Performance | Policy Governance | 50 Sentinel policies | 10 policies | 50 policies | 200+ policies | Policy as code enforcement rules
Performance | Processing Mode | Self-service with approvals | Manual approval | Self-service with approvals | Fully automated GitOps | Infrastructure provisioning workflow
Environment | Deployment Environments | 3 environments (dev staging prod) | 2 environments | 3 environments | 4+ environments | Platform environment management

## Estimate Settings
ESTIMATE SETTINGS
Phase | Variable Name | Multiplier | Description / Applies To Tasks
Discovery | DISCOVERY_MX | 1 | All Discovery phase tasks (Requirements Gathering, Current State Assessment, HashiCorp Assessment, Multi-Cloud Strategy)
Planning | PLANNING_MX | 1 | All Planning phase tasks (Platform Architecture, Vault Design, Consul Design, Network Design, Migration Planning)
Development | DEVELOPMENT_MX | 1 | All Development phase tasks (Terraform Cloud Setup, Vault Implementation, Consul Deployment, Policy Development, Integration)
Testing | TESTING_MX | 1 | All Testing phase tasks (Unit Testing, Integration Testing, Policy Testing, Security Testing, Multi-Cloud Testing)
Deployment | DEPLOYMENT_MX | 1 | All Deployment phase tasks (Production Deployment, Workspace Migration, Go-Live Support)
Training | TRAINING_MX | 1 | All Training phase tasks (Platform Training, Vault Training, Policy Training, Documentation)
Closeout | CLOSEOUT_MX | 1 | All Closeout phase tasks (Knowledge Transfer, Performance Baseline)
Management | MANAGEMENT_MX | 1.5 | Project Management overhead - 10% of actual engineering hours
Leadership | LEADERSHIP_MX | 1.5 | Quarterback/Technical Leadership overhead - 10% of actual engineering hours
EO Sales Engineer Updates Multipliers Based on Customer Scope

## LOE
Level of Effort
Phase | Work Package | Task Description | Resource Type | Base Hours | Effort Multiplier | Actual Hours | Rate | Cost Estimate | Dependencies | Notes
Discovery | Requirements Gathering | Conduct stakeholder interviews for multi-cloud platform requirements | EO Engineer | 40 | 1 |  | 150 |  |  | Includes requirements documentation and current state analysis
Discovery | Current State Assessment | Analyze existing infrastructure automation and cloud environments | EO Engineer | 32 | 1 |  | 200 |  |  | Customer must provide access to existing Terraform code and cloud accounts
Discovery | HashiCorp Assessment | Evaluate HashiCorp product usage and enterprise readiness | EO Engineer | 24 | 1 |  | 200 |  |  | Assess current Terraform Vault Consul usage and licensing
Discovery | Multi-Cloud Strategy | Define multi-cloud strategy and workload distribution | EO Engineer | 16 | 1 |  | 175 |  |  | Includes cloud provider selection and governance model
Planning | Platform Architecture Design | Design Terraform Cloud/Enterprise architecture and deployment | EO Engineer | 48 | 1 |  | 200 |  |  | Includes workspace organization state management and HA design
Planning | Vault Architecture Design | Design HashiCorp Vault secrets management architecture | EO Engineer | 32 | 1 |  | 180 |  |  | Includes auth methods secrets engines and multi-cloud integration
Planning | Consul Architecture Design | Design HashiCorp Consul service mesh and discovery architecture | EO Engineer | 24 | 1 |  | 175 |  |  | Includes service mesh networking and cross-cloud connectivity
Planning | Network Architecture Design | Design multi-cloud networking VPN and connectivity | EO Engineer | 24 | 1 |  | 175 |  |  | Includes VPC/VNet peering VPN and network security
Planning | Migration Planning | Develop Terraform state migration and workspace transition plan | EO Engineer | 24 | 1 |  | 140 |  |  | Plan for migrating existing Terraform to centralized platform
Planning | Policy Development | Design Sentinel policies for security cost and compliance | EO Engineer | 32 | 1 |  | 150 |  |  | Develop policy as code framework and governance rules
Development | Terraform Cloud Setup | Deploy and configure Terraform Cloud/Enterprise platform | EO Engineer | 48 | 1 |  | 160 |  |  | Includes Kubernetes deployment database setup and HA configuration
Development | Workspace Migration | Migrate Terraform workspaces and state to centralized platform | EO Engineer | 60 | 1 |  | 145 |  |  | Customer must provide existing Terraform code and state files
Development | Vault Implementation | Deploy HashiCorp Vault and configure secrets management | EO Engineer | 40 | 1 |  | 160 |  |  | Includes Vault cluster deployment unsealing and auth configuration
Development | Vault Integration | Integrate Vault with Terraform and cloud providers | EO Engineer | 32 | 1 |  | 150 |  |  | Configure dynamic credentials for AWS Azure GCP
Development | Consul Deployment | Deploy HashiCorp Consul service mesh across clouds | EO Engineer | 32 | 1 |  | 145 |  |  | Includes Consul server deployment and agent configuration
Development | Policy Implementation | Implement Sentinel policies and governance controls | EO Engineer | 40 | 1 |  | 140 |  |  | Deploy security cost and compliance policies
Development | VCS Integration | Configure GitHub/GitLab integration and webhooks | EO Engineer | 24 | 1 |  | 140 |  |  | Setup GitOps workflow and PR automation
Development | CI/CD Integration | Integrate platform with CI/CD pipelines | EO Engineer | 24 | 1 |  | 135 |  |  | Connect to Jenkins GitHub Actions GitLab CI
Development | Monitoring Setup | Configure monitoring logging and alerting | EO Engineer | 32 | 1 |  | 130 |  |  | Integrate with Datadog CloudWatch and Azure Monitor
Testing | Unit Testing | Develop automated tests for platform components | EO Engineer | 32 | 1 |  | 120 |  |  | Test Terraform modules and infrastructure code
Testing | Integration Testing | Test multi-cloud provisioning and cross-cloud connectivity | EO Engineer | 40 | 1 |  | 120 |  |  | End-to-end testing across AWS Azure GCP
Testing | Policy Testing | Validate Sentinel policies and governance enforcement | EO Engineer | 24 | 1 |  | 125 |  |  | Test security cost and compliance policy rules
Testing | Security Testing | Perform security assessments and compliance validation | EO Engineer | 16 | 1 |  | 175 |  |  | Vault security Consul mTLS and RBAC testing
Testing | Performance Testing | Conduct platform performance and scalability testing | EO Engineer | 24 | 1 |  | 140 |  |  | Test concurrent runs workspace performance state operations
Testing | User Acceptance Testing | Coordinate UAT with platform users and teams | EO Engineer | 32 | 1 |  | 150 |  |  | Infrastructure teams test self-service workflows
Deployment | Production Deployment | Deploy platform to production with monitoring | EO Engineer | 24 | 1 |  | 160 |  |  | Production cutover and validation
Deployment | Production Migration | Migrate production workspaces to new platform | EO Engineer | 40 | 1 |  | 150 |  |  | Critical path for production infrastructure
Deployment | Go-Live Support | Provide comprehensive support during platform launch | EO Engineer | 48 | 1 |  | 110 |  |  | 24/7 support for initial production period
Training | Platform Training | Train users on Terraform Cloud/Enterprise platform | EO Engineer | 24 | 1 |  | 130 |  |  | Workspace management state operations
Training | Vault Training | Train teams on HashiCorp Vault secrets management | EO Engineer | 16 | 1 |  | 130 |  |  | Secrets retrieval dynamic credentials
Training | Policy Training | Train teams on Sentinel policy development | EO Engineer | 16 | 1 |  | 120 |  |  | Policy as code development and testing
Training | Administrator Training | Train platform administrators on operations | EO Engineer | 24 | 1 |  | 140 |  |  | Platform maintenance troubleshooting upgrades
Training | Documentation | Create comprehensive platform and operational documentation | EO Engineer | 32 | 1 |  | 110 |  |  | Runbooks troubleshooting guides best practices
Closeout | Knowledge Transfer | Transfer platform ownership to operations team | EO Engineer | 16 | 1 |  | 140 |  |  | Operational procedures escalation maintenance
Closeout | Performance Baseline | Establish platform performance metrics and SLAs | EO Engineer | 8 | 1 |  | 130 |  |  | KPI definition monitoring setup reporting
Management | Project Management | Project coordination and stakeholder management | EO Project Manager |  | 1.5 |  | 150 |  |  | 10% of engineering effort with 1.5x multiplier
Leadership | Technical Leadership | Quarterback technical oversight and architecture review | EO Quarterback |  | 1.5 |  | 180 |  |  | 10% of engineering effort with 1.5x multiplier