# Statement of Work

Cisco Systems - Cisco HyperFlex Hybrid Infrastructure

| Client: | [Client Name] |
| --- | --- |
| Date: | [Month DD] |
| Consulting Company: | [Consulting Company Name] |
| Submitted By: | [Contact Name ¦ Email ¦ Phone] |
| Opportunity No: | [OPP-YYYY-###] |
| Version: | [1.0] |

# Table of Contents

1 Introduction
    1.1 Purpose
        1.1.1 Scope
2 Table Content
3 Image Section
4 Additional Content
5 Sign-Off

# List of Figures

Figure 1: Sample Architecture Diagram

# List of Tables

Table 1: Sample Deliverables Table

# 1 Executive Summary

This Statement of Work (SOW) defines the scope, deliverables, roles, and terms for the Cisco HyperFlex Hybrid Infrastructure project for [Client Name]. This engagement will deliver a hyperconverged infrastructure platform to consolidate 40+ servers and SAN storage, reducing data center footprint by 70% and achieving 90% faster VM provisioning through integrated compute and storage.

Project Duration: 12 weeks

# 2 Background & Objectives

## 2.1 Current State

[Client Name] currently operates traditional 3-tier infrastructure with separate compute, storage, and network silos. Key challenges include:

• Large Data Center Footprint: 40+ rack-mounted servers and dedicated SAN consuming 42U of rack space

• Slow VM Provisioning: New virtual machine deployment takes 4-8 hours with manual configuration

• High Capital Costs: Traditional 3-tier infrastructure requires $600K investment vs $294K for hyperconverged

• Management Complexity: Separate management tools for compute (vCenter), storage (SAN), and network

• Limited Scalability: Difficulty scaling compute and storage independently

## 2.2 Business Objectives

• Consolidate Infrastructure: Reduce data center footprint by 70% from 42U to 8U rack space with 4-node HyperFlex cluster

• Accelerate VM Provisioning: Enable 90% faster deployments (10 minutes vs 4-8 hours) with integrated platform

• Reduce Capital Costs: Achieve 50% CapEx savings ($294K HyperFlex vs $600K traditional)

• Simplify Management: Unified Cisco Intersight management reducing 75% management time

• Improve Efficiency: Realize $85K annual savings from reduced power/cooling and $45K from simplified operations

• Enable Growth: Scalable platform supporting 200-400 VMs with room for expansion

## 2.3 Success Metrics

• 70% data center space reduction (42U → 8U)

• 90% faster VM provisioning (4-8 hours → 10 minutes)

• 50% CapEx savings vs traditional infrastructure

• 30-month ROI through consolidation and efficiency

• 99.9% availability with N+1 fault tolerance

# 3 Scope of Work

## 3.1 In Scope

• Infrastructure assessment and VM workload analysis

• HyperFlex sizing and architecture design with HA redundancy

• Network integration planning and migration strategy

• HyperFlex 4-node all-flash cluster deployment

• VMware vSphere 8 installation and configuration

• Cisco Intersight cloud management integration

• Phased VM migration in 4 waves (pilot → Wave 1 → Wave 2 → Wave 3)

• Veeam backup integration with snapshot-based backups

• Performance tuning and optimization

• Team training (24 hours) on HyperFlex operations

• Hypercare support (60 hours) over 4 weeks

• Legacy infrastructure decommission planning

### 3.1.1 Scope Parameters

This engagement is sized based on the following parameters:

| Category | Parameter | Scope |
| --- | --- | --- |
| Solution Scope | Primary Features/Capabilities | HyperFlex 4-node for 200-300 VMs |
| Solution Scope | Customization Level | Standard HyperFlex deployment |
| Integration | External System Integrations | 2 systems (vCenter + backup) |
| Integration | Data Sources | VM inventory only |
| User Base | Total Users | 10 infrastructure admins |
| User Base | User Roles | 2 roles (admin + operator) |
| Data Volume | Data Processing Volume | 200-300 VMs workload |
| Data Volume | Data Storage Requirements | 20 TB usable storage |
| Technical Environment | Deployment Regions | Single data center |
| Technical Environment | Availability Requirements | Standard (99.5%) |
| Technical Environment | Infrastructure Complexity | Basic 3-tier compute storage network |
| Security & Compliance | Security Requirements | Basic encryption and RBAC |
| Security & Compliance | Compliance Frameworks | Basic logging |
| Performance | Performance Requirements | Standard IOPS and latency |
| Environment | Deployment Environments | Production only |

Table 1: Engagement Scope Parameters

Table: Engagement Scope Parameters

Note: Changes to these parameters may require scope adjustment and additional investment.

## 3.2 Out of Scope

These items are not in scope unless added via change control:

• Hardware procurement beyond HyperFlex nodes and fabric interconnects

• Network switch upgrades or replacements

• Disaster recovery site deployment (optional add-on)

• Application refactoring or optimization

• End-user training (infrastructure team only)

• Managed services post-hypercare period

• Legacy hardware decommissioning and disposal

## 3.3 Activities

### 3.3.1 Phase 1 – Design & Planning (Weeks 1-2)

During this phase, the current infrastructure is assessed and HyperFlex solution designed.

Key activities:

• Infrastructure assessment and VM workload analysis (72 hours)

• HyperFlex sizing and architecture design with HA redundancy

• Network integration planning for UCS fabric interconnects

• Migration strategy definition with application dependencies

• Data center preparation (rack space, power, cooling, network)

Deliverable: Infrastructure Assessment and HyperFlex Design Document

### 3.3.2 Phase 2 – Infrastructure Deployment (Weeks 3-4)

HyperFlex cluster is deployed and integrated with network fabric.

Key activities:

• HyperFlex 4-node cluster deployment with HA configuration (80 hours)

• UCS 6454 Fabric Interconnect installation and configuration

• VMware vSphere 8 installation and cluster setup (72 hours)

• Cisco Intersight integration and monitoring configuration (20 hours)

• Network connectivity validation and performance baseline

Deliverable: Deployed HyperFlex Cluster and vSphere Environment

### 3.3.3 Phase 3 – VM Migration (Weeks 5-8)

Virtual machines are migrated in phased waves with validation.

Key activities:

• Pilot migration: 20 non-critical VMs for validation (30 hours)

• Wave 1: 50 business application VMs via vMotion (40 hours)

• Wave 2: 50 critical VMs including databases (50 hours)

• Wave 3: Remaining VMs and final validation (40 hours)

• Application testing and validation after each wave

• Performance monitoring and troubleshooting

Deliverable: Migrated VM Workloads with Validation Reports

### 3.3.4 Phase 4 – Optimization (Weeks 9-12)

The platform is optimized and operations team trained.

Key activities:

• Performance tuning and resource optimization (45 hours)

• Veeam backup integration with snapshot-based backups

• Team training on HyperFlex operations (24 hours)

• Knowledge transfer and documentation delivery

• Hypercare support (60 hours) over 4 weeks

• Legacy infrastructure decommission planning

Deliverable: As-Built Documentation and Operational Runbooks

# 4 Deliverables & Timeline

## 4.1 Deliverables

| # | Deliverable | Type | Due Date | Acceptance By |
| --- | --- | --- | --- | --- |
| 1 | Infrastructure Assessment | Document | Week 2 | Client IT Lead |
| 2 | HyperFlex Cluster Deployment | Infrastructure | Week 4 | Infrastructure Lead |
| 3 | VM Migration Reports | Document | Week 8 | Operations Lead |
| 4 | As-Built Documentation | Document | Week 12 | Client IT Lead |
| 5 | Training Sessions | Live/Recorded | Week 12 | Infrastructure Team |

Table 2: Project Deliverables and Acceptance Criteria

## 4.2 Project Milestones

| Milestone | Description | Target Date |
| --- | --- | --- |
| M1 - Design Complete | HyperFlex architecture approved | Week 2 |
| M2 - Cluster Deployed | HyperFlex cluster operational | Week 4 |
| M3 - Pilot Complete | 20 VMs migrated successfully | Week 5 |
| M4 - Migration Complete | All VMs migrated and validated | Week 8 |
| M5 - Go-Live | Production operational handoff | Week 12 |
| Hypercare End | Support period complete | Week 16 |

Table 3: Project Milestones and Timeline

# 5 Roles & Responsibilities

## 5.1 RACI Matrix

| Task/Role | EO PM | EO Quarterback | EO HCI Eng | EO Virtualization | Client Infra | Client Apps | SME |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Discovery & Requirements | A | R | R | C | C | I | C |
| HyperFlex Design | C | A | R | C | C | I | I |
| Cluster Deployment | C | A | R | R | C | I | I |
| vSphere Configuration | C | R | C | A | C | I | I |
| VM Migration | R | R | C | A | C | A | I |
| Testing & Validation | R | R | C | R | A | A | I |
| Knowledge Transfer | A | R | R | R | C | I | I |

Table 4: Roles And Responsibilities

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

## 5.2 Key Personnel

Vendor Team:

• EO Project Manager: Overall delivery accountability

• EO Quarterback: Technical design and architecture oversight

• EO HCI Engineer: HyperFlex deployment and configuration

• EO Virtualization Engineer: vSphere and VM migration

Client Team:

• Infrastructure Lead: Primary technical contact

• Virtualization Lead: vSphere administration and VM validation

• Application Owners: Application testing and validation

• Operations Team: Day-to-day operations and monitoring

# 6 Architecture & Design

## 6.1 Architecture Overview

Figure 1: Solution Architecture

Figure 1: HyperFlex Hyperconverged Infrastructure Architecture - Integrated compute and storage

The proposed architecture consolidates compute and storage into a unified HyperFlex platform. Key components include:

• Compute Layer: 4x HyperFlex HX240c M5 nodes with dual Xeon Gold processors

• Storage Layer: NVMe all-flash storage with inline deduplication and compression

• Network Layer: Cisco UCS 6454 Fabric Interconnects providing unified 25GbE fabric

• Management Layer: Cisco Intersight cloud-based management and VMware vCenter

## 6.2 Architecture Type

This solution follows a hyperconverged infrastructure (HCI) architecture pattern. Key characteristics:

• Scaling Approach: Scale-out by adding nodes to cluster (linear scalability)

• Deployment Model: On-premises with cloud management (Intersight)

• Storage Architecture: Distributed data platform with erasure coding

• Fault Tolerance: N+1 redundancy (cluster survives single node failure)

The architecture supports 200-400 VMs with scalability to 8+ nodes.

## 6.3 Scope Specifications

This engagement is scoped for a Medium (4-node) deployment:

Cluster Configuration:

• Medium (4-node): 256 vCPUs, 3 TB RAM, 20 TB usable storage

• Large (6-node): 384 vCPUs, 4.5 TB RAM, 30 TB usable storage

• Enterprise (8-node): 512 vCPUs, 6 TB RAM, 40 TB usable storage

Performance Tier:

• All-Flash NVMe: 30.7 TB raw capacity per cluster

• Hybrid (SSD+HDD): Lower cost with reduced performance

• All-NVMe: Maximum performance for latency-sensitive workloads

Availability:

• N+1 Fault Tolerance: Cluster survives single node failure

• N+2 Fault Tolerance: Requires 5+ nodes (optional)

## 6.4 Technical Implementation Strategy

The deployment follows a conservative phased migration approach:

Pilot Phase (Week 5):

• Migrate 20 non-critical VMs (file servers, development)

• Validate vMotion process and application performance

• Establish rollback procedures

Production Waves (Weeks 6-8):

• Wave 1: 50 business application VMs

• Wave 2: 50 critical VMs (databases, ERP)

• Wave 3: Remaining VMs and edge cases

• Validation and performance testing after each wave

Parallel Operation:

• Dual-run period with legacy and HyperFlex

• Rollback capability maintained until validation complete

• Legacy decommission only after 4-week stabilization

# 7 Security & Compliance

## 7.1 Identity & Access Management

• Role-based access control (RBAC) for vCenter and Intersight

• Active Directory integration for authentication

• Multi-factor authentication (MFA) for administrative access

• Audit logging for all administrative actions

## 7.2 Data Protection

• Self-encrypting NVMe drives for data-at-rest encryption

• VMware VM encryption for sensitive workloads

• Veeam backup with immutable snapshots

• Cross-site replication for disaster recovery (optional)

## 7.3 Compliance & Auditing

• Configuration compliance scanning

• Audit trails for all infrastructure changes

• Compliance reporting for PCI DSS or HIPAA

• Automated vulnerability scanning

# 8 Testing & Validation

## 8.1 Functional Validation

Comprehensive testing ensures the platform works correctly:

Infrastructure Testing:

• Cluster formation and health validation

• Storage performance and deduplication testing

• Network fabric connectivity and failover

• vSphere integration and features

VM Migration Testing:

• vMotion live migration validation

• Application functionality post-migration

• Performance comparison (before/after)

• Data integrity verification

## 8.2 Performance Testing

Performance validation ensures SLA requirements:

Load Testing:

• VM density testing (target: 200-300 VMs)

• Storage IOPS and throughput benchmarking

• Network bandwidth validation

• CPU and memory utilization profiling

Benchmarking:

• Application performance baselines

• Storage latency validation (target: < 5ms)

• vMotion duration for different VM sizes

## 8.3 Resilience Testing

Disaster recovery and failover validation:

Failure Scenarios:

• Single node failure and automatic failover

• Network path failure and redundancy

• Disk failure and rebuild

• Power failure and UPS validation

Backup/Restore:

• Veeam backup job validation

• VM restore testing

• Recovery time validation

# 9 Handover & Support

## 9.1 Handover Artifacts

Upon successful implementation:

Documentation Deliverables:

• As-built architecture diagrams

• HyperFlex cluster configuration documentation

• vSphere configuration and VM inventory

• Network topology and fabric interconnect configuration

• Intersight integration and monitoring guide

Operational Deliverables:

• Operations runbooks for daily tasks

• Troubleshooting guides

• VM provisioning procedures

• Backup and restore procedures

• Performance monitoring and capacity planning guide

Knowledge Assets:

• Recorded training sessions

• HyperFlex and vSphere administrator credentials

• Intersight portal access

• Vendor support contacts and escalation paths

## 9.2 Knowledge Transfer

Training Sessions:

• 24 hours of hands-on training

• HyperFlex architecture and operations

• vSphere administration on HyperFlex

• Intersight cloud management

• VM provisioning and migration

• Backup and restore operations

• Troubleshooting and performance tuning

Documentation Package:

• As-built architecture documentation

• Configuration management guide

• Operational runbooks and SOPs

• Troubleshooting guide

## 9.3 Hypercare Support

Duration: 4 weeks post-go-live

Coverage:

• Business hours support (8 AM - 6 PM local time)

• 4-hour response time for critical issues

• Daily health check calls (first 2 weeks)

• Weekly status meetings

Scope:

• Issue investigation and resolution

• Performance tuning and optimization

• Configuration adjustments

• Knowledge transfer continuation

## 9.4 Assumptions

### 9.4.1 General Assumptions

Client Responsibilities:

• Client will provide data center rack space, power, and cooling

• Client virtualization team available for VM migration and testing

• Client application owners available for post-migration validation

• Client will handle internal change approvals and stakeholder communication

Technical Environment:

• Data center meets power and cooling requirements (30A per node)

• Network infrastructure supports 25GbE connectivity

• vCenter Server compatible with vSphere 8 (or will be upgraded)

• Veeam Backup & Replication compatible with HyperFlex snapshots

Project Execution:

• Project scope and requirements remain stable

• Resources available per project plan

• Application downtime windows available for critical VM migrations

• Hardware delivery within 6-8 week lead time

# 10 Investment Summary

## 10.1 Total Investment

| Cost Category | Year 1 List | AWS/Partner Credits | Year 1 Net | Year 2 | Year 3 | 3-Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Professional Services | $63,900 | $0 | $63,900 | $0 | $0 | $63,900 |
| Hardware | $294,000 | ($15,000) | $279,000 | $0 | $0 | $279,000 |
| Software | $106,000 | ($20,000) | $86,000 | $106,000 | $106,000 | $298,000 |
| Support | $52,000 | $0 | $52,000 | $52,000 | $52,000 | $156,000 |
| TOTAL INVESTMENT | $515,900 | ($35,000) | $480,900 | $158,000 | $158,000 | $796,900 |

Table 5: Total Investment Summary

## 10.2 Partner Credits

Year 1 Credits Applied: $35,000 (server trade-in + VMware ELA credit)

Annual Recurring Cost: $158,000/year (software licenses and support)

## 10.3 Payment Terms

Pricing Model: Fixed price with milestone-based payments

Payment Schedule:

• 30% upon SOW execution and project kickoff ($19,170)

• 30% upon completion of Phase 2 - Cluster Deployed ($19,170)

• 25% upon completion of Phase 3 - Migration Complete ($15,975)

• 15% upon successful go-live and project acceptance ($9,585)

Invoicing: Monthly invoicing based on milestones completed. Net 30 payment terms.

# 11 Terms & Conditions

## 11.1 General Terms

All services will be delivered in accordance with the executed Master Services Agreement (MSA) between Vendor and Client.

## 11.2 Scope Changes

Any changes to scope, schedule, or cost require a formal Change Request approved by both parties.

## 11.3 Intellectual Property

• Client retains ownership of all deliverables and configurations

• Vendor retains proprietary methodologies and tools

• Pre-existing IP remains with original owner

## 11.4 Confidentiality

• All artifacts under NDA protection

• Client data handled per security requirements

• No disclosure to third parties without consent

# 12 Sign-Off

By signing below, both parties agree to the scope, approach, and terms outlined in this Statement of Work.

| CLIENT | CONSULTING COMPANY |
| --- | --- |
| Name: ___________________________ | Name: ___________________________ |
| Title: ___________________________ | Title: ___________________________ |
| Signature: ___________________________ | Signature: ___________________________ |
| Date: ___________________________ | Date: ___________________________ |

eoframework.org